## MADHURA (new)
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | MADHURA RANI GANJ AND SARAOULI | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | OHT | j1(1) | 250 | 35 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j1(1) | j1 | 200 | 605 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j1(1) | j2 | 200 | 26 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j2 | j23 | 200 | 106 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j590 | j592 | 63 | 219 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j162 | j230 | 63 | 525 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j38 | j138 | 63 | 325.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j21 | j22 | 63 | 300 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j44 | j44(1) | 63 | 156.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j112 | j112(1) | 63 | 205.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## brahupur hydro2
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j205 | j202 | 63 | 3.5 | 6 | 3 | 1 | 4 | no
2 | j205 | j202 | 63 | 89.1 | 6 | 3 | 1 | 4 | no
3 | j205 | j202 | 63 | 105.3 | 6 | 3 | 1 | 4 | no
4 | j234 | j220 | 63 | 61.1 | 6 | 3 | 1 | 4 | no
5 | j220 | j218 | 63 | 27 | 6 | 3 | 1 | 4 | no
6 | j218 | j200 | 63 | 83.3 | 6 | 3 | 1 | 4 | no
7 | j291 | j263 | 63 | 51.1 | 6 | 3 | 1 | 4 | no
8 | j326 | 286 | 63 | 96.3 | 6 | 3 | 1 | 4 | no
9 | j286 | j282 | 63 | 35 | 6 | 3 | 1 | 4 | no
10 | j286 | j293 | 63 | 36.1 | 6 | 3 | 1 | 4 | no
11 | j326 | j169 | 63 | 98.1 | 6 | 3 | 1 | 4 | no
12 | j224 | j273 | 63 | 70.2 | 6 | 3 | 1 | 4 | no
13 | j175 | j273 | 63 | 77.1 | 6 | 3 | 1 | 4 | no
14 | j224 | j273 | 63 | 7 | 6 | 3 | 1 | 4 | no
15 | j273 | j247 | 63 | 56 | 6 | 3 | 1 | 4 | no
16 | j247 | j303 | 63 | 30.9 | 6 | 3 | 1 | 4 | no
17 | j247 | j294 | 63 | 9.6 | 6 | 3 | 1 | 4 | no
18 | j246 | j294 | 63 | 246.3 | 6 | 3 | 1 | 4 | no
19 | j259 | j102 | 110 | 53.4 | 6 | 3 | 1 | 4 | no
20 | j246 | j294 | 63 | 5 | 6 | 3 | 1 | 4 | no
21 | j248 | j171 | 110 | 89.1 | 6 | 3 | 1 | 4 | no
22 | j109 | j145 | 63 | 110.7 | 6 | 3 | 1 | 4 | no
23 | j194 | j122 | 63 | 29.3 | 6 | 3 | 1 | 4 | no
24 | j122 | j170 | 63 | 11.2 | 6 | 3 | 1 | 4 | no
25 | j122 | j170 | 63 | 21.7 | 6 | 3 | 1 | 4 | no
26 | j170 | j296 | 63 | 62.2 | 6 | 3 | 1 | 4 | no
27 | j296 | j145 | 63 | 19.3 | 6 | 3 | 1 | 4 | no
28 | j229 | j197 | 140 | 39.1 | 6 | 3 | 1 | 4 | no
29 | j177 | j168 | 63 | 55.3 | 6 | 3 | 1 | 4 | no
30 | j138 | j48 | 63 | 56.3 | 6 | 3 | 1 | 4 | no
31 | j159 | j173 | 63 | 66.8 | 6 | 3 | 1 | 4 | no
32 | j235 | j158 | 63 | 290.3 | 6 | 3 | 1 | 4 | no
33 | j158 | j167 | 63 | 4.7 | 6 | 3 | 1 | 4 | no
34 | j158 | j167 | 63 | 46 | 6 | 3 | 1 | 4 | no
35 | j7a | j7b | 200 | 38.3 | 6 | 3 | 1 | 4 | no
36 | j138 | j48 | 63 | 4 | 6 | 3 | 1 | 4 | no
37 | j92 | j329 | 63 | 157 | 6 | 3 | 1 | 4 | no
38 | j271(1) | j271(2) | 63 | 270 | 6 | 3 | 1 | 4 | no
39 | j155 | j155(1) | 63 | 105 | 6 | 3 | 1 | 4 | no
40 | j265 | j284 | 63 | 46 | 6 | 3 | 1 | 4 | no
41 | j265 | j280 | 63 | 49 | 6 | 3 | 1 | 4 | no
42 | j265 | j314 | 63 | 19 | 6 | 3 | 1 | 4 | no
43 | j102 | j80 | 63 | 130.2 | 6 | 3 | 1 | 4 | no
44 | j307 | j308 | 63 | 68.5 | 6 | 3 | 1 | 4 | no
45 | j6(1) | j6(2) | 63 | 383.2 | 6 | 3 | 1 | 4 | no
46 | j20 | j20(1) | 63 | 275.3 | 6 | 3 | 1 | 4 | no
47 | j246 | j351 | 63 | 219.3 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## madhura arani ganj 4
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :madhura rani ganj
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | OHT | j1(1) | 250 |  | 35 | 0.55 | 1.25
2 | j1(1) | j1 | 200 |  | 605 | 0.5 | 1.2
3 | j1(1) | j2 | 200 |  | 26 | 0.5 | 1.2 |  | brick road | 0.5 | 26 | 13 | 0.5 | 26 | 13 | done
4 | j2 | j23 | 200 |  | 106 | 0.5 | 1.2
5 | j590 | j592 | 63 |  | 219 | 0.36 | 1.06
6 | j162 | j230 | 63 |  | 525 | 0.36 | 1.06
7 | j38 | j138 | 63 |  | 325.4 | 0.36 | 1.06
8 | j21 | j22 | 63 |  | 300 | 0.36 | 1.06 | [10 empty] | 22411
9 | j44 | j44(1) | 63 |  | 156.2 | 0.36 | 1.06
10 | j112 | j112(1) | 63 |  | 205.3 | 0.36 | 1.06 | [10 empty] | 36545.2
2502.9
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## brahapur 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :brahapur 2
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j205 | j202 | 63 |  | 3.5 | 0.363 | 1.063 |  | b.t crossing | 3.5 | 0.363 | 1.2705 | 3.5 | 0.363 | 1.2705 | done
2 | j205 | j202 | 63 |  | 89.1 | 0.363 | 1.063 |  | brick road | 89.1 | 0.363 | 32.3433 | 89.1 | 0.363 | 32.3433 | done
3 | j205 | j202 | 63 |  | 105.3 | 0.363 | 1.063
4 | j234 | j220 | 63 |  | 61.1 | 0.363 | 1.063
5 | j220 | j218 | 63 |  | 27 | 0.363 | 1.063 |  | brick road | 27 | 0.363 | 9.801 | 27 | 0.363 | 9.801 | done
6 | j218 | j200 | 63 |  | 83.3 | 0.363 | 1.063
7 | j291 | j263 | 63 |  | 51.1 | 0.363 | 1.063 |  | brick road | 51.1 | 0.363 | 18.5493 | 51.1 | 0.363 | 18.5493 | done
8 | j326 | 286 | 63 |  | 96.3 | 0.363 | 1.063 |  | brick road | 96.3 | 0.363 | 34.9569 | 96.3 | 0.363 | 34.9569 | done
9 | j286 | j282 | 63 |  | 35 | 0.363 | 1.063
10 | j286 | j293 | 63 |  | 36.1 | 0.363 | 1.063
11 | j326 | j169 | 63 |  | 98.1 | 0.363 | 1.063
12 | j224 | j273 | 63 |  | 70.2 | 0.363 | 1.063 |  | brick road | 70.2 | 0.363 | 25.4826 | 70.2 | 0.363 | 25.4826 | done
13 | j175 | j273 | 63 |  | 77.1 | 0.363 | 1.063
14 | j224 | j273 | 63 |  | 7 | 0.363 | 1.063 |  | b.t road crossing | 7 | 0.363 | 2.541 | 7 | 0.363 | 2.541 | done
15 | j273 | j247 | 63 |  | 56 | 0.363 | 1.063 |  | brick road | 56 | 0.363 | 20.328 | 56 | 0.363 | 20.328 | done
16 | j247 | j303 | 63 |  | 30.9 | 0.363 | 1.063
17 | j247 | j294 | 63 |  | 9.6 | 0.363 | 1.063
18 | j246 | j294 | 63 |  | 246.3 | 0.363 | 1.063
19 | j259 | j102 | 110 |  | 53.4 | 0.41 | 1.11
20 | j246 | j294 | 63 |  | 5 | 0.363 | 1.063 |  | b.t road crossing | 5 | 0.363 | 1.815 | 5 | 0.363 | 1.815 | done
21 | j248 | j171 | 110 |  | 89.1 | 0.41 | 1.11 |  | brick road | 89.1 | 0.41 | 36.531 | 89.1 | 0.41 | 36.531 | done
22 | j109 | j145 | 63 |  | 110.7 | 0.363 | 1.063
23 | j194 | j122 | 63 |  | 29.3 | 0.363 | 1.063
24 | j122 | j170 | 63 |  | 11.2 | 0.363 | 1.063 |  | brick road | 11.2 | 0.363 | 4.0656 | 11.2 | 0.363 | 4.0656 | done
25 | j122 | j170 | 63 |  | 21.7 | 0.363 | 1.063
26 | j170 | j296 | 63 |  | 62.2 | 0.363 | 1.063 |  | brick road | 62.2 | 0.363 | 22.5786 | 62.2 | 0.363 | 22.5786 | done
27 | j296 | j145 | 63 |  | 19.3 | 0.363 | 1.063
28 | j229 | j197 | 140 |  | 39.1 | 0.44 | 1.14
29 | j177 | j168 | 63 |  | 55.3 | 0.363 | 1.063
30 | j138 | j48 | 63 |  | 56.3 | 0.363 | 1.063
31 | j159 | j173 | 63 |  | 66.8 | 0.363 | 1.063
32 | j235 | j158 | 63 |  | 290.3 | 0.363 | 1.063
33 | j158 | j167 | 63 |  | 4.7 | 0.363 | 1.063 |  | b.t road crossing | 4.7 | 0.363 | 1.7061 | 4.7 | 0.363 | 1.7061 | done
34 | j158 | j167 | 63 |  | 46 | 0.363 | 1.063
35 | j7a | j7b | 200 |  | 38.3 | 0.5 | 1.2
36 | j138 | j48 | 63 |  | 4 | 0.363 | 1.063 |  | road crossing | 4 | 0.363 | 1.452 | 4 | 0.363 | 1.452 | done
37 | j92 | j329 | 63 | 174 | 157 | 0.363 | 1.063
38 | j271(1) | j271(2) | 63 |  | 270 | 0.363 | 1.063 | [10 empty] | 24037
39 | j155 | j155(1) | 63 |  | 105 | 0.363 | 1.063 | [10 empty] | 375
40 | j265 | j284 | 63 | 33 | 46 | 0.363 | 1.063 | [10 empty] | 20509
41 | j265 | j280 | 63 | 29 | 49 | 0.363 | 1.063
42 | j265 | j314 | 63 | 15 | 19 | 0.363 | 1.063
43 | j102 | j80 | 63 |  | 130.2 | 0.363 | 1.063 | [10 empty] | 531
44 | j307 | j308 | 63 |  | 68.5 | 0.363 | 1.063
45 | j6(1) | j6(2) | 63 |  | 383.2 | 0.363 | 1.063
46 | j20 | j20(1) | 63 |  | 275.3 | 0.363 | 1.063 | [10 empty] | 6410.4
47 | j246 | j351 | 63 | 191 | 219.3 | 0.363 | 1.063
[5 empty] | 3908.2 | [9 empty] | 213.4209
Representative PMPL - BRCCPL (JV) Pratapgarh | [5 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh | [5 empty] | Representative UP Jal Nigam (Rural) Pratapgarh
7241.3

## aurangabad 2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :aurangabad
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j4 | j5 | 250 | 274 | 274 | 0.55 | 1.25
2 | j5 | j7 | 250 | 54 | 54 | 0.55 | 1.25
3 | j7 | j9 | 250 | 159 | 159 | 0.55 | 1.25
4 | j91 | j91(1) | 63 |  | 200 | 0.363 | 1.06
5 | 176 | 177 | 63 | 82 | 143.2 | 0.363 | 1.06
Representative PMPL - BRCCPL (JV) Pratapgarh | [6 empty] | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## auranga hydro
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | aurangabad | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j4 | j5 | 250 | 274 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j5 | j7 | 250 | 54 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j7 | j9 | 250 | 159 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j91 | j91(1) | 63 | 200 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 176 | 177 | 63 | 143.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date