## Sheet1
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP_____shulka construction________Block______mangraura_____________ Pipeline Laying Measurement Sheet
Name of the Contractor : shukla construction
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 160mm | 180mm | 200mm
1 | j52 | j39 |  |  | HDPE | 460.7
2 | j39 | j35 |  |  | HDPE | 40.5 | [10 empty] | 14
3 | j35 | j24 |  |  | HDPE | 58.4 | [10 empty] | 105
4 | j24 | j28 |  |  | HDPE | 52.3 | [10 empty] | 78.5
5 | j24 | j21 |  |  | HDPE | 23 | [10 empty] | 23.8
6 | j21 | j15 |  |  | HDPE | 33.3 | [10 empty] | 41.2
7 | J15 | J16 |  |  | HDPE | 19.1 | [10 empty] | 74.8
8 | J15 | J11 |  |  | HDPE | 14.2 | [10 empty] | 24.5
9 | J9(A) | J9(b) |  |  | HDPE | 25.7 | [10 empty] | 18.5
10 | J75(A) | J75(B) |  |  | HDPE | 133.8 | [10 empty] | 60
11 | J75(A) | J75(B) | BRICK ROAD |  | HDPE | 2.6 | [10 empty] | 29.5
12 | J2(A) | J6 |  |  | HDPE | 77.4 | [10 empty] | 55.4
13 | J6 | J8 | BRICK ROAD |  | HDPE | 33.4 | [10 empty] | 25.4
14 | J6 | J8 | BRICK ROAD |  | HDPE | 10.4 | [10 empty] | 15.4
15 | J6 | J4 |  |  | HDPE | 25.1 | [10 empty] | 77.3
16 | J6 | J4 | BRICK ROAD |  | HDPE | 15 | [10 empty] | 24.5
16 | J4 | J5 |  |  | HDPE | 194.3 | [10 empty] | 22.1
17 | J4 | J5 |  |  | HDPE | 3 | [10 empty] | 47.5
18 | J4 | J5 | BRICK ROAD |  | HDPE | 62.9 | [10 empty] | 19
19 | J3 | J4 | BRICK ROAD |  | HDPE | 14.4 | [10 empty] | 39.9
20 | J3 | J4 |  |  | HDPE | 7.5 | [10 empty] | 18.4
21 | J67(A) | J84 | BRICK ROAD |  | HDPE | 89.4 | [10 empty] | 123.5
22 | J67(A) | J82 |  |  | HDPE | 141.5 | [10 empty] | 68.2
23 | J67(A) | J79 |  |  | HDPE | 101.5 | [10 empty] | 95.7
24 | J67(A) | J67 | B.T ROAD |  | HDPE | 4.2 | [10 empty] | 61.5
25 | J67(A) | J67 |  |  | HDPE | 85.7 | [10 empty] | 8.4
26 | J67 | J82 |  |  | HDPE | 165.5 | [10 empty] | 157
27 | J67 | J61 |  |  | HDPE | 86.5 | [10 empty] | 22.2
28 | J46 | J61 | B.T ROAD |  | HDPE | 4.2 | [10 empty] | 69.8
29 | J46 | J61 |  |  | HDPE | 4.1 | [10 empty] | 84.2
30 | J61 | J45 |  |  | HDPE | 185.5 | [10 empty] | 28.5
31 | J61 | J45 | BRICK ROAD |  | HDPE | 49.5 | [10 empty] | 117.2
32 | J45 | J40 | BRICK ROAD |  | HDPE | 3 | [10 empty] | 16
33 | J45 | J40 |  |  | HDPE | 73.2 | [10 empty] | 96.3
34 | J40 | J91 |  |  | HDPE | 51.6 | [10 empty] | 288.8
35 | J40 | J39 | B.T ROAD |  | HDPE | 3 | [10 empty] | 115.1
36 | J40 | J39 |  |  | HDPE | 41.4 | [10 empty] | 34.2
37 | j45 | j53 | BRICK ROAD |  | HDPE | 7.8 | [10 empty] | 73.5
38 | j45 | j53 |  |  | HDPE | 48.5 | [10 empty] | 47
39 | j53 | j49 | BRICK ROAD |  | HDPE | 5.8 | [10 empty] | 637
40 | j53 | j49 |  |  | HDPE | 9 | [10 empty] | 7
41 | j53 | j49 |  |  | HDPE | 32.5 | [10 empty] | 275.6
42 | j53 | j58 | BRICK ROAD |  | HDPE | 6.1 | [10 empty] | 11
43 | j53 | j58 |  |  | HDPE | 16.11 | [10 empty] | 3
44 | j53 | j58 |  |  | HDPE | 9 | [10 empty] | 8
45 | j58 | j58(1) |  |  | HDPE | 4
46 | j58 | j58(1) | BRICK ROAD |  | HDPE | 3.8
47 | j58(1) | j64a | BRICK ROAD |  | HDPE | 9.8
48 | j58(1) | j64a |  |  | HDPE | 37.6
49 | j64a | j64b |  |  | HDPE | 49
50 | j64a | j64 |  |  | HDPE | 104.7
51 | j64 | j66 |  |  | HDPE | 27.2
52 | j64a | j65 |  |  | HDPE | 9
53 | j64a | j65 | BRICK ROAD |  | HDPE | 11
54 | j58(1) | j59 |  |  | HDPE | 35.5
55 | j58 | j60 | BRICK ROAD |  | HDPE | 85.2
56 | j58 | j60 |  |  | HDPE | 15.7
57 | j35 | j35(a) |  |  | HDPE | 22.9
58 | j35a | j35b | BRICK ROAD |  | HDPE | 1.9
59 | j35a | j35b |  |  | HDPE | 14.5
60 | j35(1a) | j35(1b) |  |  | HDPE | 42.4
61 | j35(3b) | j35(4b) |  |  | HDPE | 10.3
62 | j35(a) | j30a |  |  | HDPE | 6.4
63 | j30(1) | j30(2) |  |  | HDPE | 31.1
64 | j30a | j30 |  |  | HDPE | 59.4
65 | j30a | j30 | BRICK ROAD |  | HDPE | 5.6
66 | j73a | j73b | B.T ROAD |  | HDPE | 2.4
67 | j73a | j73b |  |  | HDPE | 37.1
68 | j73 | j73a |  |  | HDPE | 3.7
69 | j73a | j72 |  |  | HDPE | 36.6
70 | j72 | j74 |  |  | HDPE | 65.1
71 | j72 | j74 | BRICK ROAD |  | HDPE | 45.7
72 | j72 | j70 |  |  | HDPE | 69.7
73 | j70 | j71 |  |  | HDPE | 54.6
74 | j70 | j71 | B.T ROAD |  | HDPE | 3.2
75 | j70 | j68 |  |  | HDPE | 52.3
76 | j68 | j69 |  |  | HDPE | 12.6
77 | j68 | j69 | BRICK ROAD |  | HDPE | 37
78 | j68 | j67(a) |  |  | HDPE | 284
79 | j99 | j99a | BRICK ROAD |  | HDPE | 3.3
80 | j99 | j99a |  |  | HDPE | 8.1
81 | j99 | j99a | BRICK ROAD |  | HDPE | 6.9
82 | j99a | j99b | BRICK ROAD |  | HDPE | 2.2
83 | j99a | j99b |  |  | HDPE | 20.4
84 | j99(a) | j102 | BRICK ROAD |  | HDPE | 19.1
85 | j102 | j106 | BRICK ROAD |  | HDPE | 29.5
86 | j106 | j112 | BRICK ROAD |  | HDPE | 88.2
87 | j106 | j112 |  |  | HDPE | 63.1
88 | j106 | j110 | BRICK ROAD |  | HDPE | 20
| j106 | j110 |  |  | HDPE | 55.1
89 | j111 | j110 |  |  | HDPE | 33.9
90 | j110 | j109 |  |  | HDPE | 34
91 | j103 | j101 |  |  | HDPE | 126.4
92 | j101 | j115 |  |  | HDPE | 136.6
93 | j101 | j115 |  |  | HDPE | 57.1
94 | j115 | j118 |  |  | HDPE | 55.2
95 | j101 | j97 |  |  | HDPE | 74.7
96 | j97 | j99 |  |  | HDPE | 115.7
97 | j91 | j90 |  |  | HDPE | 128.8
98 | j94 | j88 |  |  | HDPE | 160
99 | j87 | j88 |  |  | HDPE | 156
100 | j46 | j61 |  |  | HDPE | 115.1
101 | j46 | j33a |  |  | HDPE | 169
102 | j33a | j33b |  |  | HDPE | 27
103 | j33a | j33 |  |  | HDPE | 12.5
104 | j33 | j29 |  |  | HDPE | 22.3
105 | j33 | j29 | BRICK ROAD |  | HDPE | 20.6
106 | j33 | j30 |  |  | HDPE | 12
107 | j33 | j30 | ccroad |  | HDPE | 21
108 | j33 | j30 | BRICK ROAD |  | HDPE | 19.8
109 | j33 | j30 |  |  | HDPE | 91
110 | j21 | j26 |  |  | HDPE | 13.2
111 | j21 | j26 | BRICK ROAD |  | HDPE | 32.2
112 | j26 | j30 | BRICK ROAD |  | HDPE | 30.5
113 | j26 | j17a | BRICK ROAD |  | HDPE | 11.6
114 | j26 | j17a |  |  | HDPE | 52.5
115 | j17a | j17b |  |  | HDPE | 13.6
116 | j17a | j17 |  |  | HDPE | 46.2
117 | j90 | j94 |  |  | HDPE |  | 128.3
118 | j90 | j87 |  |  | HDPE |  | 220
119 | j87 | j76 |  |  | HDPE |  | 162.3
120 | j97 | j94 |  |  | HDPE |  | 122.5
121 | j97 | j94 |  |  | HDPE |  | 748
122 | j76 | j43 |  |  | HDPE |  | 262
123 | j43 | j46 |  |  | HDPE |  | 163
124 | j17a | j9 |  |  | HDPE |  | 123
125 | j17 | j9 | B.T ROAD |  | HDPE |  | 3.8
126 | j9 | j43 |  |  | HDPE |  | 241.9
127 | j9 | j43 | B.T ROAD |  | HDPE |  | 3
128 | j9 | j9a |  |  | HDPE |  | 55.5
129 | j11 | j9a |  |  | HDPE |  | 116.1
130 | j9(1) | j9(2) |  |  | HDPE |  | 8.7
131 | j1 | 75(a) |  |  | HDPE |  | 197.4
132 | j75a | J75(B) | BRICK ROAD |  | HDPE |  | 5.1
133 | j75a | J75(B) |  |  | HDPE |  | 305.6
134 | j2 | j3 |  |  | HDPE |  | 34.8
135 | j9 | j2 |  |  | HDPE |  |  | 13.1
136 | j2 | j2(a) |  |  | HDPE |  |  |  | 15.6
137 | j2(a) | j1 |  |  | HDPE |  |  |  | 68.9
138 | OHT | j1 |  |  | HDPE |  |  |  |  | 29.6
Work Done Qty In ( Rmt ) : | [5 empty] | 5927.01 | 2901 | 13.1 | 84.5 | 29.6 | 0 |  |  | 8955.21
Restricting Exceeded Qty's to WO Qty's
Total Quantity Considered for bill ( In RMT )=
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% | [6 empty] | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks
1.1 | 63 mm HDPE | 7371 | 5927.01 | 5927.01 | 1711 | 4216.01 |  |  |  | 0 | 10411.9 |  | 10411.9 |  |  | 0
1.2 | 75 mm HDPE | 2841 | 2901 | 2901 | 2228 | 673 |  |  |  | 0 | 2054.4 |  | 2054.4 |  |  | 0
1.3 | 90 mm HDPE | 21 | 13.1 | 13.1 |  | 13.1 |  |  |  | 0 | 1402.8 |  | 1402.8 |  |  | 0
1.4 | 110mm HDPE | 63 | 84.5 | 84.5 |  | 84.5 |  |  |  | 0 | 1819 |  | 1819 |  |  | 0
1.5 | 125mm HDPE | 42 | 29.6 | 29.6 |  | 29.6 |  |  |  | 0 | 528 |  | 528 |  |  | 0
1.6 | 140mm HDPE |  | 0 | 0 | 0 |  |  |  |  | 0 | 982 |  | 982 |  |  | 0
1.7 | 160mm HDPE |  |  | 0 | 0 |  |  |  |  | 0 | 228 |  | 228 |  |  | 0
1.8 | 180mm HDPE |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
1.9 | 200mm HDPE |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
Sub Total = |  | 10338 | 8955.21 | 8955.21 | 3939 | 5016.21 | [5 empty] | 0 | 17426.1 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ AM-SMX ) (Dy.M-PMX ) AGM Project Incharge

## MALAAK
| HYDROSTATIC TEST FOR PRESSURE PIPES | [12 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-MALAK | [12 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK | [11 empty] | Block: MANGRAURA, G.P-MALAK
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | [5 empty] | Date of Testing | [6 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [10 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 160 | J92 | J55 | 131 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 1 | HDPE | 110 | j130 | j124 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 110 | j139 | j116 | 110.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 90 | j35 | j91 | 234 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE |  | j136 | j126 | 218.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
2 | HDPE | 160 | J92 | J97 | 11.7 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 2 | HDPE | 110 | j130 | j124 | 354.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 110 | j116 | j118 | 14 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | j113 | j139 | 26.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE |  | j136 | j126 | 101.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
3 | HDPE | 140 | j92 | j91 | 488 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 3 | HDPE | 63 | j232 | j229 | 102 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | j57 | j67 | 11.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 90 | j80 | j86 | 43 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE |  | j136 | j126 | 6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
4 | HDPE | 125 | j94 | j124 | 423 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 4 | HDPE | 63 | j229 | j221 | 93 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 63 | j67 | j83 | 45 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | j86 | j104 | 44.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE |  | j136 | j126 | 322.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
5 | HDPE | 125 | j118 | j97 | 121.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 5 | HDPE | 63 | j221 | j235 | 10 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 63 | j67 | j88 | 66 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 63 | j233 | j161 | 54.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE |  | j136 | j126 | 18.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
6 | HDPE | 63 | j128 | j123 | 30 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 6 | HDPE | 63 | j221 | j241 | 70 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | j88 | j73 | 45.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | j161 | j210 | 33.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE |  | j160 | j156 | 33.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
7 | HDPE | 63 | j123 | j58 | 65.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 7 | HDPE | 63 | j77 | j96 | 34 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | j88 | j134 | 133 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | j243 | j196 | 86.4 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE |  | j160 | j169 | 92 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
8 | HDPE | 63 | j58 | j53 | 422 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 8 | HDPE | 63 | j229a | j241a | 116 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 63 | j47 | j30 | 37.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 63 | j210 | j219 | 61.4 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE |  | j169 | j208 | 30.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
9 | HDPE | 63 | j123 | j71 | 65.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 9 | HDPE | 63 | j229 | j234 | 142 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | j30 | j36 | 39.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 63 | j219 | j240 | 114.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE |  | j169 | j125 | 56.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
10 | HDPE | 63 | j71 | j72 | 5.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 10 | HDPE | 63 | j64 | j138 | 217.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 63 | j30 | j35 | 127.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | j240 | j239 | 38.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE |  | j169 | j125 | 13.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
11 | HDPE | 63 | j72 | j46 | 126 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 11 | HDPE | 63 | j138 | j177 | 10.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 63 | j124 | j120 | 10.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | j240 | j242 | 7.1 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE |  | j169 | j125 | 15.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
12 | HDPE | 63 | j72 | j53 | 44.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 12 | HDPE | 63 | j177 | j183 | 16.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 63 | j120 | j27 | 281.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | j242 | j243 | 11.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE |  | j125 | j113 | 19.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
13 | HDPE | 63 | j53 | j29 | 82.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 13 | HDPE | 63 | j177 | j187 | 19.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 63 | j27 | j11 | 112.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 63 | j242 | j243 | 116 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE |  | j142 | j127 | 39.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
14 | HDPE | 63 | j29 | j20 | 43.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 14 | HDPE | 63 | j187 | j98 | 70 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | j11 | j14 | 44.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 63 | j243 | j233 | 188 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE |  | j142 | j131 | 25.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
15 | HDPE | 63 | j29 | j20 | 64.8 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 15 | HDPE | 63 | j98 | j40 | 65 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 63 | j11 | j10 | 14.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 63 | j242 | j197 | 182 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE |  | j131 | j170 | 37.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
16 | HDPE | 63 | j20 | j2 | 15.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 16 | HDPE | 63 | j40 | j74 | 63.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | j10 | j5 | 37.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 63 | j111 | j111a | 150.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE |  | j131 | j135 | 12 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
17 | HDPE | 63 | j20 | j2 | 112 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 17 | HDPE | 63 | j74 | j75 | 54 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 63 | j5 | j9 | 32 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 63 | j230 | j230a | 31 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE |  | j131 | j135 | 27 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
18 | HDPE | 63 | j2 | j1 | 57.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 18 | HDPE | 63 | j187 | j179 | 74.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 63 | j9 | J63 | 121 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 63 | j89 | j89a | 56.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE |  | j81a | j81b | 37 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
19 | HDPE | 63 | j2 | j24 | 59.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 19 | HDPE | 63 | j190 | j40 | 62.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 63 | j63 | j93 | 53 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 63 | j197 | j236 | 65 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE |  | j110a | j110b | 36 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
20 | HDPE | 63 | j2 | j24 | 113.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 20 | HDPE | 63 | j190 | j74 | 112.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 63 | j93 | j94 | 112 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | j223 | j238 | 78 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE |  | j100 | j100b | 96 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
21 | HDPE | 63 | j71 | j70 | 42.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 21 | HDPE | 63 | j138 | j106 | 32.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | j94 | j133 | 133.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | j238 | j201 | 17 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 21 | HDPE |  | j152 | j99 | 108.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
22 | HDPE | 63 | j70 | j44 | 40.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 22 | HDPE | 63 | j106 | j165 | 77.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 63 | j133 | j108 | 58.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 63 | j201 | j217 | 54.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 22 | HDPE |  | j99 | j188 | 103.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
23 | HDPE | 63 | j70 | j44 | 3 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 23 | HDPE | 63 | j165 | j167 | 84.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | j108 | j134 | 96 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 63 | j217 | j213 | 100.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 23 | HDPE |  | j99 | j200 | 75.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
24 | HDPE | 63 | j70 | j37 | 95.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 24 | HDPE | 63 | j106 | j152 | 108.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 63 | j54 | j65 | 61.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | j217 | j220 | 4.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 24 | HDPE |  | j216 | j207 | 71.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
25 | HDPE | 63 | j37 | j19 | 92.7 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 25 | HDPE | 63 | j152 | 167 | 43.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 25 | HDPE | 63 | j55 | j43 | 9.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 25 | HDPE | 63 | j217 | j220 | 49.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 25 | HDPE |  | j198 | j150 | 142.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
26 | HDPE | 63 | j37 | j19 | 2.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 26 | HDPE | 63 | j167 | j178 | 21.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 26 | HDPE | 63 | j43 | j41 | 109.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 26 | HDPE | 63 | j220 | j211 | 73.3 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 26 | HDPE |  | j207 | j200 | 21.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
27 | HDPE | 63 | j31 | j18 | 15.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 27 | HDPE | 63 | j178 | j203 | 56.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 27 | HDPE | 63 | j122 | j147 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 27 | HDPE | 63 | j220 | j204 | 114.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 27 | HDPE |  | j200 | j192 | 68.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
28 | HDPE | 63 | j26 | j56 | 33.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 28 | HDPE | 63 | j178 | j216 | 12.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 28 | HDPE | 63 | j147 | j119 | 23.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 28 | HDPE | 63 | j204 | j193 | 56 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 28 | HDPE |  | j150 | j168 | 28.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
29 | HDPE | 63 | j26 | j34 | 22.4 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 29 | HDPE | 63 | j27 | j32 | 48.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 29 | HDPE | 63 | j147 | j139 | 51.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 29 | HDPE | 63 | j204 | j146 | 61 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 29 | HDPE |  | j168 | j164 | 109.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
30 | HDPE | 63 | j34 | j42 | 84.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 30 | HDPE | 63 | j32 | j61 | 81.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 30 | HDPE | 63 | j116 | j117 | 7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 30 | HDPE | 63 | j191 | j185 | 51.9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 30 | HDPE |  | j164 | j112 | 61.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
31 | HDPE | 63 | j19 | j26 | 64.9 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 31 | HDPE | 63 | j61 | j68 | 128.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 31 | HDPE | 63 | j116 | j117 | 14 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 31 | HDPE | 63 | j191 | j223 | 45.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 31 | HDPE |  | j168 | j181 | 82.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
32 | HDPE | 63 | j225 | j224 | 24 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 32 | HDPE | 63 | j61 | j68 | 110.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 32 | HDPE | 63 | j116 | j116a | 165 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 32 | HDPE | 63 | j223 | j223a | 23.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 32 | HDPE |  | j181 | j132 | 144.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
33 | HDPE | 63 | j212 | j213 | 83.6 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 33 | HDPE | 63 | j61 | j68 | 49 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 33 | HDPE | 63 | j116 | j116a | 26.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 33 | HDPE | 63 | j223a | j189 | 35.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 33 | HDPE |  | j192 | j136 | 149.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
34 | HDPE | 63 | j213 | j206 | 8.2 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 34 | HDPE | 63 | j82 | j94 | 40 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 34 | HDPE | 63 | j122 | j122a | 55.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 34 | HDPE | 63 | j223a | j189 | 76.9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 34 | HDPE |  | j154 | j107 | 14.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
35 | HDPE | 63 | j206 | j172 | 20.1 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 35 | HDPE | 63 | j32 | j81 | 5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 35 | HDPE | 63 | j35 | j21 | 154 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 35 | HDPE | 63 | j236a | j236b | 15.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 35 | HDPE |  | j150a | j150b | 124 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
36 | HDPE | 63 | j172 | j182 | 25 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 36 | HDPE | 63 | j32 | j81 | 48 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 36 | HDPE | 63 | j27 | j21 | 3.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 36 | HDPE | 63 | j236 | j189 | 98.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 36 | HDPE |  | j150c | j150d | 32 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
37 | HDPE | 63 | j172 | j175 | 200 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 37 | HDPE | 63 | j81 | j95 | 46 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 37 | HDPE | 63 | j27 | j21 | 8.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 37 | HDPE | 63 | j189 | j173 | 69 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 37 | HDPE |  | j150c | j150d | 3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
38 | HDPE | 63 | j206 | j172 | 7 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 38 | HDPE | 63 | j95 | j96 | 66.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 38 | HDPE | 63 | j55 | j54 | 10.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 38 | HDPE | 63 | j173 | j162 | 18.5 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 38 | HDPE |  | j207 | j200 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
39 | HDPE | 63 | j206 | j211 | 57 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 39 | HDPE | 63 | j96 | j133 | 100.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 39 | HDPE | 63 | j228 | j230 | 163.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 39 | HDPE | 63 | j162 | j237 | 53.1 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 39 | HDPE |  | j154 | j107 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
40 | HDPE | 63 | j211 | j232 | 121.5 | 6kg/cm2 | 3 | 1 | 4 | NO |  |  | 40 | HDPE | 63 | j96 | j133 | 8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 40 | HDPE | 63 | j230 | j89 | 58.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 40 | HDPE | 63 | j162 | j146 | 81 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 40 | HDPE |  | j147 | j139 | 7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | 41 | HDPE | 63 | j96 | j82 | 49.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 41 | HDPE | 63 | j230 | j231 | 52.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 41 | HDPE | 63 | j197 | j184 | 62 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 41 | HDPE |  | j225 | j195 | 8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Name: | [12 empty] | 42 | HDPE | 63 | j21 | j62 | 59.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 42 | HDPE | 63 | j231 | j89 | 86.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 42 | HDPE | 63 | j184 | j189 | 68 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 42 | HDPE |  | j172 | j175 | 46.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Designation: | [12 empty] | 43 | HDPE | 63 | j62 | j81 | 69.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 43 | HDPE | 63 | j231 | j186 | 43.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 43 | HDPE | 63 | j212 | j224 | 104 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 43 | HDPE |  | J131A | J131B | 15.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Signature: | [12 empty] | 44 | HDPE | 63 | j62 | j47 | 12.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 44 | HDPE | 63 | j186 | j114 | 37.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 44 | HDPE | 63 | j222 | j245 | 25 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 44 | HDPE |  | J131A | J131B | 17 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
Date: | [12 empty] | 45 | HDPE | 63 | j47 | j48 | 52 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 45 | HDPE | 63 | j114 | j111 | 70.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 45 | HDPE | 63 | j224 | j222 | 91 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 45 | HDPE |  | J125 | J142 | 26.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[13 empty] | 46 | HDPE | 63 | j48 | j95 | 58 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 46 | HDPE | 63 | j111 | j161 | 170.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 46 | HDPE | 63 | j227 | j225 | 29.8 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 46 | HDPE |  | J125 | J142 | 50.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[5 empty] | 3525.7 | [7 empty] | 47 | HDPE | 63 | j48 | j57 | 33.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 47 | HDPE | 63 | j110 | j151 | 83.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 47 | HDPE | 63 | j225 | j224 | 9 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 47 | HDPE |  | J186 | J231 | 43.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[13 empty] | 48 | HDPE | 63 | j57 | j77 | 23.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 48 | HDPE | 63 | j145 | j140 | 45 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 48 | HDPE | 63 | j225 | j195 | 36.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 48 | HDPE |  | J80 | J79 | 30.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[13 empty] | 49 | HDPE | 63 | j57 | j77 | 49.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 49 | HDPE | 63 | j145 | j174 | 25.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 49 | HDPE | 63 | j79 | j103 | 19.2 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 49 | HDPE |  | j37 | j130 | 260.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[13 empty] | 50 | HDPE | 63 | j77 | j73 | 38.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 50 | HDPE | 63 | j174 | j226 | 27 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 50 | HDPE | 63 | j79 | j110 | 128.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 50 | HDPE |  | j139 | j212 | 355 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[13 empty] | 51 | HDPE | 63 | j73 | j108 | 73.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 51 | HDPE | 63 | j186 | j226 | 80.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 51 | HDPE | 63 | j110 | j141 | 52.6 | 5KG/CM2 | 3 | 1 | 4 | NO |  | 51 | HDPE |  | j196 | j113 | 202.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO
[15 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 52 | HDPE | 63 | j226 | j233 | 29.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 52 | HDPE | 63 | j86 | j90 | 33 | 5KG/CM2 | 3 | 1 | 4 | NO
[13 empty] | Name: | [13 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 53 | HDPE | 63 | j90 | j87 | 22 | 5KG/CM2 | 3 | 1 | 4 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[13 empty] | Designation: | [11 empty] | Name: | [11 empty] | 54 | HDPE | 63 | j90 | j118 | 122.7 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Name:
[13 empty] | Signature: | [11 empty] | Designation: | [11 empty] | 55 | HDPE | 63 | j100 | j148 | 63 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Designation:
[13 empty] | Date: | [11 empty] | Signature: | [11 empty] | 56 | HDPE | 63 | j100 | j163 | 69 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Signature:
[25 empty] | Date: | [11 empty] | 57 | HDPE | 63 | j104 | j143 | 29 | 5KG/CM2 | 3 | 1 | 4 | NO |  | Date:
Abstract (Bill Breakup) | [17 empty] | 3381.2 | [18 empty] | 58 | HDPE | 63 | j143 | j149 | 26 | 5KG/CM2 | 3 | 1 | 4 | NO
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% | [6 empty] | FHTC Stretch - 10% | [15 empty] | 3449.1 | [6 empty] | 59 | HDPE | 63 | j143 | j153 | 18 | 5KG/CM2 | 3 | 1 | 4 | NO | [6 empty] | 3654.7
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks | [19 empty] | 60 | HDPE | 63 | j143 | j153 | 30 | 5KG/CM2 | 3 | 1 | 4 | NO
1.1 | 63 mm HDPE | 17139 | 0 | 0 | 0 |  | 14319 | 14319 | - | 14319 | 14319 |  | 14319 | [23 empty] | 61 | HDPE | 63 | j153 | j155 | 14.6 | 5KG/CM2 | 3 | 1 | 4 | NO
1.2 | 75 mm HDPE | 813 | 0 | 0 | 0 |  | 811.8 | 811.8 | - | 811.8 | 811.8 |  | 811.8 | [23 empty] | 62 | HDPE | 63 | j155 | j109 | 45.2 | 5KG/CM2 | 3 | 1 | 4 | NO
1.3 | 90 mm HDPE | 1002 | 0 | 0 | 0 |  | 999.9 | 999.9 | - | 999.9 | 999.9 |  | 999.9 | [23 empty] | 63 | HDPE | 63 | j155 | j129 | 55.9 | 5KG/CM2 | 3 | 1 | 4 | NO
1.4 | 110mm HDPE | 483 | 0 | 0 | 0 |  | 480 | 480 | - | 480 | 480 |  | 480 | [23 empty] | 64 | HDPE | 63 | j153 | j160 | 8.3 | 5KG/CM2 | 3 | 1 | 4 | NO
1.5 | 125mm HDPE | 539 | 0 | 0 | 0 |  | 537.1 | 537.1 | - | 537.1 | 537.1 |  | 537.1 | [25 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
1.6 | 140mm HDPE | 566 | 0 | 0 | 0 |  | 564.3 | 564.3 | - | 564.3 | 564.3 |  | 564.3 | [23 empty] | Name: | [17 empty] | 17895
1.7 | 160mm HDPE | 163 |  | 0 | 0 |  | 142.7 | 142.7 | - | 142.7 | 142.7 |  | 142.7 | [23 empty] | Designation:
1.8 | 180mm HDPE |  |  | 0 | 0 | 0 | - | 0 | - | 0 | - |  | - | [23 empty] | Signature:
1.9 | 200mm HDPE |  |  |  |  | 0 | - | 0 | - | 0 | - |  | - | [23 empty] | Date:
Sub Total = |  | 20705 | 0 | 0 | 0 | 0 | - |  |  | 17854.8 | - |  | -
3884.3
| 63 | 75 | 90 | 110 | 125 | 140 | 160
| 14319.7 | 811.8 | 999.9 | 480 | 537.1 | 564.3 | 142.7 | 17855.5
| 17139 | 813 | 1002 | 483 | 539 | 566 | 163 | 20705

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
Name of the Contractor : 209892_M/s. Shukla Construction (CL05) | [11 empty] | RA Bill-10
Sl NO | Description | Units | Bhadausi & Rampur Praan | Karanpur Khujhi | Laulipokhtakam | Sangrampur | Malaak | Total |  | Balance Qty (Available at Site) | SAP Entry-201 & 221 | Remarks
|  |  | Consumed Qty | Consumed Qty | Consumed Qty | Consumed Qty |  | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 19966 | 6502 | 16213 |  |  | 86096 | 69991.4 | 16104.6 | 38932 | 31059.4 | 31059.4 |  | 17352 | 4216.01
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2918.7 | 1072 | 198 |  |  | 12955 | 9951.4 | 3003.6 | 5353.7 | 4597.7 | 4597.7 |  | 2850 | 673
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2123 | 871 | 1090 |  |  | 9580 | 7244.4 | 2335.6 | 5857 | 1387.4 | 1387.4 |  | 1600 | 13.1
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3656.7 | 0 | 685 |  |  | 8075 | 7192.5 | 882.5 | 5921.7 | 1270.8 | 1270.8 |  | 3650 | 84.5
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 0 | 344 | 0 |  |  | 2580 | 2440.4 | 139.6 | 1587 | 853.4 | 853.4 |  |  | 29.6
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 718.8 | 408 | 350 |  |  | 3312 | 2803.1 | 508.9 | 1478.8 | 1324.3 | 1324.3 |  | 528
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 755.5 | 272 | 0 |  |  | 1716 | 1651.1 | 64.9 | 1005.5 | 645.6 | 645.6 |  | 684
| 200mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 950.5 | 0 | 0 |  |  | 972 | 950.5 | 21.5 | 950.5 | 0 | 0 |  | 432
| 200mm dia DI Pipe | [6 empty] | 72 | 67 | 5 |  | 67
| Total Qty In ( Rmt ) = |  | 31089.2 |  |  |  |  | 125358 | 102291.8 | 23066.2
2 | Specials :- | [11 empty] | 0
| Equal Tee | [11 empty] | 0
| 63mm | No's | 61 | 25 |  | 14 |  | 330 | 100 | 230 | 100 | 0 | 0 | 200030286 | 55 | 42
| 75mm | No's | 2 |  |  | 1 |  | 43 | 3 | 40 | 3 | 0 | 0 |  | 9 | 1
| 90mm | No's | 3 |  |  |  |  | 17 | 3 | 14 | 3 | 0 | 0 |  | 7 | 1
| 110mm | No's | 0 |  |  | 1 |  | 19 | 1 | 18 | 1 | 0 | 0 |  | 2
| 140mm | No's | 0 |  |  | 1 |  | 9 | 1 | 8 | 1 | 0 | 0 |  | 1
| 160mm | No's | [5 empty] | 7 | 0 | 7 |  | 0 | 0
| 200mm | No's | 2 |  |  |  |  | 3 | 2 | 1 |  | 2 | 2 |  | 3
| Total Qty In ( No's ) = |  | 68 |  |  |  |  | 428 | 110 | 318
| Branch TEE | [11 empty] | 0
| 75 mm X 63 mm | No's | 16 | 1 |  | 1 |  | 43 | 17 | 26 | 17 | 0 | 0 |  | 18 | 6
| 90 mm X 63 mm | No's | 16 |  |  | 3 |  | 30 | 16 | 14 | 16 | 0 | 0 |  | 8 | 8
| 90 mm X 75 mm | No's | 4 | 2 |  | 1 |  | 13 | 6 | 7 | 6 | 0 | 0 |  | 2 | 2
| 110mm X 63 mm | No's | 7 |  |  | 2 |  | 12 | 7 | 5 | 7 | 0 | 0 |  | 5 | 4
| 110mm X 75 mm | No's | 0 |  |  |  |  | 4 | 0 | 4 |  | 0 | 0
| 110mm X 90 mm | No's | 2 |  |  | 1 |  | 19 | 2 | 17 | 2 | 0 | 0
| 140mm X 63 mm | No's | [5 empty] | 2 | 0 | 2 |  | 0 | 0
| 140mm X 90 mm | No's | [9 empty] | 0 | 0
| 140mm X 110mm | No's | 1 |  |  |  |  | 3 | 1 | 2 | 1 | 0 | 0 |  | 1 | 1
| 160mm X 110 mm | No's | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  | 2
| 160mm X 140 mm | No's | 0 |  |  |  |  | 1 | 0 | 1 |  | 0 | 0
| 200mm X 75 mm | No's | [5 empty] | 1 |  | 1 |  | 0 | 0
| 200mm X 160 mm | No's | 1 |  |  |  |  | 1 | 1 | 0 |  | 1 | 1
| Total Qty In ( No's ) = |  | 47 |  |  |  |  | 129 | 50 | 79
| 4 Way Tee | [11 empty] | 0
| 63 mm | No's |  | 1 |  |  |  | 3 | 1 | 2 | 1 | 0 | 0
| 110mm | No's | 0 |  |  |  |  | 1 | 0 | 1 |  | 0 | 0 |  | 1
| Total Qty In ( No's ) = |  | 0 |  |  |  |  | 4 | 1 | 3
| Reducers | [11 empty] | 0
| 75mm X 63 mm | No's | 4 | 5 |  | 1 |  | 35 | 9 | 26 | 9 | 0 | 0 |  | 11 | 1
| 90mm X 63 mm | No's | 2 |  |  | 1 |  | 10 | 2 | 8 | 2 | 0 | 0 |  | 4
| 90mm X 75 mm | No's | 2 | 1 |  |  |  | 28 | 3 | 25 | 3 | 0 | 0 |  | 4 | 2
| 110 mm X 63 mm | No's | 1 |  |  | 2 |  | 9 | 1 | 8 | 1 | 0 | 0 |  | 4 | 1
| 110 mm X 75 mm | No's | 0 |  |  |  |  | 7 | 0 | 7 |  | 0 | 0
| 110 mm X 90 mm | No's | 3 |  |  |  |  | 9 | 3 | 6 | 3 | 0 | 0 |  | 4 | 2
| 110 mm X 140 mm |  |  |  |  | 1 |  | 1 | 0 | 1 |  | 0 | 0
| 140mm X 63 mm | No's | 0 |  |  |  |  | 1 | 0 | 1 |  | 0 | 0 |  | 1
| 140mm X 75 mm | No's | [5 empty] | 1 | 0 | 1 |  | 0 | 0
| 140mm X 90 mm | No's | 0 |  |  |  |  | 3 | 0 | 3 |  | 0 | 0
| 140mm X 110mm | No's | 1 |  |  |  |  | 3 | 1 | 2 | 1 | 0 | 0 |  | 2 | 1
| 140mm X 125 mm | No's | [5 empty] | 3 | 0 | 3 |  | 0 | 0
| 160mm X 75mm | No's | [5 empty] | 1 | 0 | 1 |  | 0 | 0
| 160mm X 140mm | No's | 0 |  |  |  |  | 4 | 0 | 4 |  | 0 | 0 |  | 2
| 200mm X 110mm | No's | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  | 1
| 200mm X 140mm | No's | 1 |  |  |  |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 1
| 200mm X 160mm | No's | 1 |  |  |  |  | 2 | 1 | 1 | 1 | 0 | 0 |  | 1
| Total Qty In ( No's ) = |  | 15 |  |  |  |  | 118 | 21 | 97
| End Caps | [11 empty] | 0
| 63mm | No's | 20 | 16 |  |  |  | 290 | 36 | 254 | 36 | 0 | 0 |  | 20 | 1
| Total Qty In ( No's ) = |  | 20 |  |  |  |  | 290 | 36 | 254
| Bends | [11 empty] | 0
| 75mm ( 90 Deg ) | No's | 2 |  |  |  |  | 13 | 2 | 11 | 2 | 0 | 0 |  | 1
| 90mm ( 90 Deg ) | No's | 0 |  |  |  |  | 9 | 0 | 9 |  | 0 | 0
| 110mm ( 90 Deg ) | No's | 0 |  |  |  |  | 8 | 0 | 8 |  | 0 | 0
| 160mm ( 90 Deg ) | No's | 0 |  |  |  |  | 2 | 0 | 2 |  | 0 | 0 |  | 3
| 200mm ( 90 Deg ) | No's | 1 |  |  |  |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 1
| Total Qty In ( No's ) = |  | 3 |  |  |  |  | 33 | 3 | 30
| FHTCs Materials | [11 empty] | 0
| GI Pipe | No's | [5 empty] | 1522 | 129 | 1393 | 129 | 0 | 0
| MDPE pipe 20 mm | No's | [5 empty] | 2500 | 593 | 1907 | 593 | 0 | 0
| PPCLamps saddle-63*1/2" | No's | [5 empty] | 1060 | 115 | 945 | 115 | 0 | 0 | 1200000410
| PPCLamps saddle-75*1/2" | No's | [5 empty] | 170 | 10 | 160 | 10 | 0 | 0 | 1200000425
| PPCLamps saddle-90*1/2" | No's | [5 empty] | 145 | 4 | 141 | 4 | 0 | 0 | 1200000411
| PPCLamps saddle-110*1/2" | No's | [5 empty] | 52 |  | 52 |  | 0 | 0 | 1200000412
| PPCLamps saddle-140*1/2" | No's | [5 empty] | 2 |  | 2 |  | 0 | 0 | 1200000426
| PPCLamps saddle-160*1/2" | No's | [5 empty] | 2 |  | 2 |  | 0 | 0 | 1200000427
| PPCLamps saddle-200*1/2" | No's | [7 empty] | 0 |  | 0 | 0 | 1200000429
| PP comp fm theard adapter-20mm | No's | [5 empty] | 775 | 129 | 646 | 129 | 0 | 0 | 1200000414
| PP comp fm theard elb off taken-20mm | No's | [5 empty] | 940 | 129 | 811 |  | 129 | 129
| MDPE ELBOW-20MM | No's | [5 empty] | 1140 |  | 1140 |  | 0 | 0 | 1200000415
| Threaded FCV-1/2"(15nb) | No's | [5 empty] | 1475 | 129 | 1346 | 129 | 0 | 0 | 1200000417
| GI elbow | No's | [5 empty] | 2710 | 258 | 2452 | 258 | 0 | 0
| GI socket | No's | [5 empty] | 1435 | 129 | 1306 | 129 | 0 | 0
| Wall Mount Saddle GI Pipe - 15 MM (Clamp) | No's | [5 empty] | 2190 | 129 | 2061 | 129 | 0 | 0 | 1200000418
| 15mm nipple-0.3mm | No's | [5 empty] | 1535 | 129 | 1406 | 129 | 0 | 0
| 15mm nipple-0.5 mm | No's | [5 empty] | 1535 | 129 | 1406 | 129 | 0 | 0
| bib cock ptmt(taps) | No's | [5 empty] | 1435 | 129 | 1306 | 129 | 0 | 0
| Teflon tape | No's | [5 empty] | 630 |  | 630 |  | 0 | 0
| GI Nails | No's | [5 empty] | 1360 |  | 1360 |  | 0 | 0
[6 empty] | ok | [5 empty] | 0 | 0
0
0
0
Prepared by Checked By Stores DM-PMX Project Incharge

## VALVES
BLOCK | MANGRAURA
GP NAME | SHIVAPUR KHURD
AGENCY | SHUKLA CONSTRUCTION
SL NO. | STARTING NODE | ENDING NODE | DIA OF PIPE | SLUICE VALVE(100MM) | SLUICE VALVE(80MM) | SCOUR VALVE(80MM) | AIR VALVE(50MM) | REMARK
1 | J1 | J2 | 110 |  | 1
2 | J1 | J75 | 75 |  | 1
3 | J9 | J43 | 75 |  | 1
BLOCK | MANGRAURA
GP NAME | MALAAK
AGENCY | SHUKLA CONSTRUCTION
SL NO. | STARTING NODE | ENDING NODE | DIA OF PIPE | SLUICE VALVE(100MM) | SLUICE VALVE(80MM) | SCOUR VALVE(80MM) | AIR VALVE(50MM) | REMARK
1 | J130 | J37 | 75 |  | 1
2 | J130 | J154 | 90 |  | 1
3 | J124 | J130 | 110 |  | 1
4 | J92 | J91 | 140 |  |  |  |  | 150MM SLUICE-1
5 | J97 | J118 | 125 | 1
6 | J97 | J80 | 140 |  |  |  |  | 150MM SLUICE-1
7 | J116 | J139 | 110 |  |  |  | 1
8 | J113 | J196 | 75 |  | 1
9 | J92 | J55 | 160 |  |  |  |  | 150MM SLUICE-1