## amuwahi restoration
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of JMR - Road Dismantling & Restoration
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : Amuwahi
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | J16 | J17 | 63 | Brick road | 5.8 | 0.363 | 2.1054 | 5.8 | 0.363 | 2.1054
2 | J16 | J17 | 63 | Brick road | 5.9 | 0.363 | 2.1417 | 5.9 | 0.363 | 2.1417
3 | J21 | J23 | 63 | Interlocking | 4.6 | 0.46 | 2.116 | 4.6 | 0.46 | 2.116
4 | J23 | J26 | 63 | Brick road | 21.9 | 0.363 | 7.9497 | 21.9 | 0.363 | 7.9497
5 | J26 | J40 | 63 | Brick road | 15.8 | 0.363 | 5.7354 | 15.8 | 0.363 | 5.7354
6 | J40 | J52 | 63 | Brick road | 17.4 | 0.363 | 6.3162 | 17.4 | 0.363 | 6.3162
7 | J40 | J52 | 63 | Brick road | 4.9 | 0.363 | 1.7787 | 4.9 | 0.363 | 1.7787
8 | J52 | J53 | 63 | Brick road | 44.3 | 0.363 | 16.0809 | 44.3 | 0.363 | 16.0809
9 | J52 | J52A | 63 | Brick road | 15.2 | 0.363 | 5.5176 | 15.2 | 0.363 | 5.5176
10 | J52A | J73 | 63 | Brick road | 22.9 | 0.363 | 8.3127 | 22.9 | 0.363 | 8.3127
11 | J99 | J104 | 63 | Brick road | 79.5 | 0.363 | 28.8585 | 79.5 | 0.363 | 28.8585
12 | J104 | J103 | 63 | Brick road | 216.6 | 0.363 | 78.6258 | 216.6 | 0.363 | 78.6258
13 | J90 | J103 | 63 | Brick road | 240 | 0.363 | 87.12 | 240 | 0.363 | 87.12
14 | J104 | J122 | 63 | Brick road | 4.5 | 0.363 | 1.6335 | 4.5 | 0.363 | 1.6335
15 | J104 | J122 | 63 | Brick road | 212.6 | 0.363 | 77.1738 | 212.6 | 0.363 | 77.1738
16 | J122 | J126 | 63 | Brick road | 219.5 | 0.363 | 79.6785 | 219.5 | 0.363 | 79.6785
17 | j98 | j105 | 63 | Interlocking | 5.7 | 0.46 | 2.622 | 5.7 | 0.46 | 2.622
18 | J106 | J107 | 63 | Interlocking | 23.8 | 0.46 | 10.948 | 23.8 | 0.46 | 10.948
19 | J106 | J101 | 63 | Interlocking | 23.4 | 0.46 | 10.764 | 23.4 | 0.46 | 10.764
20 | J106 | J101 | 63 | Interlocking | 106.7 | 0.46 | 49.082 | 106.7 | 0.46 | 49.082
21 | J101 | J100 | 63 | Interlocking | 11.1 | 0.46 | 5.106 | 11.1 | 0.46 | 5.106
22 | J101 | J100 | 63 | Interlocking | 18.4 | 0.46 | 8.464 | 18.4 | 0.46 | 8.464
23 | J49 | J37 | 63 | Interlocking | 10.4 | 0.46 | 4.784 | 10.4 | 0.46 | 4.784
24 | J90 | J90A | 63 | Interlocking | 51 | 0.46 | 23.46 | 51 | 0.46 | 23.46
25 | J86 | J85 | 63 | Interlocking | 2.8 | 0.46 | 1.288 | 2.8 | 0.46 | 1.288
26 | J85 | J89 | 63 | Interlocking | 30.3 | 0.46 | 13.938 | 30.3 | 0.46 | 13.938
27 | J83 | J85 | 63 | Interlocking | 32.6 | 0.46 | 14.996 | 32.6 | 0.46 | 14.996
28 | J83 | J78 | 63 | Interlocking | 57.3 | 0.46 | 26.358 | 57.3 | 0.46 | 26.358
29 | J45 | J49 | 75 | Interlocking | 41.1 | 0.46 | 18.906 | 41.1 | 0.46 | 18.906
30 | J49 | J61 | 75 | Interlocking | 4 | 0.46 | 1.84 | 4 | 0.46 | 1.84
31 | j114 | j113 | 63 | Brick road | 67.5 | 0.363 | 24.5025 | 67.5 | 0.363 | 24.5025
32 | J113 | J115 | 63 | Brick road | 75.7 | 0.363 | 27.4791 | 75.7 | 0.363 | 27.4791
33 | J113 | J111 | 63 | Brick road | 97.1 | 0.363 | 35.2473 | 97.1 | 0.363 | 35.2473
34 | J111 | J110 | 63 | Brick road | 24.1 | 0.363 | 8.7483 | 24.1 | 0.363 | 8.7483
35 | J111 | J108 | 63 | Brick road | 43.7 | 0.363 | 15.8631 | 43.7 | 0.363 | 15.8631
36 | J108 | J106 | 63 | Brick road | 22.1 | 0.363 | 8.0223 | 22.1 | 0.363 | 8.0223
37 | J101 | J100 | 63 | Brick road | 64.7 | 0.363 | 23.4861 | 64.7 | 0.363 | 23.4861
38 | J101 | J100 | 63 | Brick road | 27.7 | 0.363 | 10.0551 | 27.7 | 0.363 | 10.0551
39 | J92 | J72A | 63 | Brick road | 110.4 | 0.363 | 40.0752 | 110.4 | 0.363 | 40.0752
40 | J72A | J72B | 63 | Brick road | 49.4 | 0.363 | 17.9322 | 49.4 | 0.363 | 17.9322
41 | J72A | J64 | 63 | Brick road | 18 | 0.363 | 6.534 | 18 | 0.363 | 6.534
42 | J64 | J65 | 63 | Brick road | 15.5 | 0.363 | 5.6265 | 15.5 | 0.363 | 5.6265
43 | J65 | J66 | 63 | Brick road | 13.6 | 0.363 | 4.9368 | 13.6 | 0.363 | 4.9368
44 | J65 | J67 | 63 | Brick road | 46.4 | 0.363 | 16.8432 | 46.4 | 0.363 | 16.8432
45 | J67 | J68 | 63 | Brick road | 26.9 | 0.363 | 9.7647 | 26.9 | 0.363 | 9.7647
46 | J67 | J70 | 63 | Brick road | 39.7 | 0.363 | 14.4111 | 39.7 | 0.363 | 14.4111
47 | J64 | J61 | 63 | Brick road | 42.4 | 0.363 | 15.3912 | 42.4 | 0.363 | 15.3912
48 | J61 | J59 | 63 | Brick road | 53.7 | 0.363 | 19.4931 | 53.7 | 0.363 | 19.4931
49 | J59 | J57 | 63 | Brick road | 118.5 | 0.363 | 43.0155 | 118.5 | 0.363 | 43.0155
50 | J57 | J55 | 63 | Brick road | 286 | 0.363 | 103.818 | 286 | 0.363 | 103.818
51 | J44 | J45 | 63 | Brick road | 142 | 0.363 | 51.546 | 142 | 0.363 | 51.546
52 | J49 | J61 | 63 | Brick road | 3.2 | 0.363 | 1.1616 | 3.2 | 0.363 | 1.1616
53 | J34 | J49 | 63 | Brick road | 35.3 | 0.363 | 12.8139 | 35.3 | 0.363 | 12.8139
54 | J83 | J78 | 63 | Brick road | 46.9 | 0.363 | 17.0247 | 46.9 | 0.363 | 17.0247
55 | J78 | J71 | 63 | Brick road | 234.5 | 0.363 | 85.1235 | 234.5 | 0.363 | 85.1235
56 | J29 | J30 | 63 | Brick road | 9 | 0.363 | 3.267 | 9 | 0.363 | 3.267
57 | J30 | J32 | 63 | Brick road | 107 | 0.363 | 38.841 | 107 | 0.363 | 38.841
58 | J32 | J33 | 63 | Brick road | 16.6 | 0.363 | 6.0258 | 16.6 | 0.363 | 6.0258
59 | J31 | J32 | 63 | Brick road | 8.4 | 0.363 | 3.0492 | 8.4 | 0.363 | 3.0492
60 | J30 | J37 | 63 | Brick road | 44.6 | 0.363 | 16.1898 | 44.6 | 0.363 | 16.1898
61 | J3 | J10 | 63 | Brick road | 82.5 | 0.363 | 29.9475 | 82.5 | 0.363 | 29.9475
62 | J3 | J10 | 63 | Brick road | 31 | 0.363 | 11.253 | 31 | 0.363 | 11.253
63 | J87 | J88 | 63 | Brick road | 49.5 | 0.363 | 17.9685 | 49.5 | 0.363 | 17.9685
64 | J45 | J49 | 75 | Brick road | 38.6 | 0.375 | 14.475 | 38.6 | 0.375 | 14.475
65 | J45 | J34 | 75 | Brick road | 56.1 | 0.375 | 21.0375 | 56.1 | 0.375 | 21.0375
66 | J34 | J28 | 90 | Brick road | 79 | 0.39 | 30.81 | 79 | 0.39 | 30.81
67 | J28 | J23 | 90 | Brick road | 4.1 | 0.39 | 1.599 | 4.1 | 0.39 | 1.599
68 | J25 | J3 | 110 | Brick road | 242.8 | 0.41 | 99.548 | 242.8 | 0.41 | 99.548
amuwahi restoration
| Sl. No | Road Type | UNITS | WO/DPR Qty's | Qty Executed Up to Date | Qty Executed Billed up to Date | Qty Billed Up to Previous | This Bill(Executed) | Remarks
| 1 | INTERLOCKING | SQM | 0 | 194.672 | 194.672 | - | 194.672 | variation
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge
0