## hasthara road restoration
MADHURA RANI GANJ AND SARAOULI(road restoration)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | sqmeter | REMARK
1 | j125 | j160 | interlocking | 0.363 | 63 | 1.8 | 0.6534
2 | j125 | j160 | interlocking | 0.363 | 63 | 4.3 | 1.5609
3 | j169 | j166 | BRICK ROAD | 0.363 | 63 | 1.8 | 0.6534
4 | J115 | J103 | BRICK ROAD | 0.363 | 63 | 2 | 0.726
5 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 7.7 | 2.7951
6 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 21.7 | 7.8771
7 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 31.1 | 11.2893
8 | J109 | J110 | BRICK ROAD | 0.363 | 63 | 23 | 8.349
9 | J110 | J149 | BRICK ROAD | 0.363 | 63 | 6.5 | 2.3595
10 | J34 | J36 | BRICK ROAD | 0.363 | 63 | 2.4 | 0.8712
11 | J37 | J23 | BRICK ROAD | 0.363 | 63 | 51 | 18.513
12 | J37 | J23 | BRICK ROAD | 0.363 | 63 | 3.6 | 1.3068
13 | J23 | J12 | BRICK ROAD | 0.363 | 63 | 60 | 21.78
14 | J12(1) | J12(2) | BRICK ROAD | 0.363 | 63 | 3 | 1.089
15 | J28 | J21 | BRICK ROAD | 0.363 | 63 | 4 | 1.452
16 | J4 | J16 | interlocking | 0.363 | 63 | 101.3 | 36.7719
17 | J30 | J22 | BRICK ROAD | 0.363 | 63 | 84.5 | 30.6735
18 | J30 | J103 | BRICK ROAD | 0.363 | 63 | 95.5 | 34.6665
19 | J103 | J136 | BRICK ROAD | 0.363 | 63 | 3 | 1.089
20 | J103 | J115 | BRICK ROAD | 0.363 | 63 | 128 | 46.464
21 | J103 | J100 | BRICK ROAD | 0.363 | 63 | 363 | 131.769
22 | J103 | J100 | BRICK ROAD | 0.363 | 63 | 409 | 148.467
23 | J100 | J168 | BRICK ROAD | 0.363 | 63 | 3 | 1.089
24 | J100 | J168 | BRICK ROAD | 0.363 | 63 | 60 | 21.78
25 | J100 | J38 | BRICK ROAD | 0.363 | 63 | 161.6 | 58.6608
26 | J29 | J31 | BRICK ROAD | 0.363 | 63 | 15 | 5.445
27 | J31(1) | J31(2) | BRICK ROAD | 0.363 | 63 | 2.3 | 0.8349
28 | J192(1) | J202 | B.T ROAD | 0.363 | 63 | 3 | 1.089
29 | J163 | J141 | B.T ROAD | 0.363 | 63 | 3.3 | 1.1979
30 | J242 | J227 | B.T ROAD | 0.363 | 63 | 6 | 2.178
31 | J76 | J242 | BRICK ROAD | 0.363 | 63 | 6 | 2.178
32 | J242 | J240 | BRICK ROAD | 0.363 | 63 | 30.8 | 11.1804
33 | J240 | J241 | BRICK ROAD | 0.363 | 63 | 89.6 | 32.5248
34 | J249 | J250 | B.T ROAD | 0.363 | 63 | 3 | 1.089
35 | j42 | j44 | BRICK ROAD | 0.363 | 63 | 29.9 | 10.8537
36 | j44 | j53 | BRICK ROAD | 0.363 | 63 | 37.1 | 13.4673
37 | j44 | j43 | BRICK ROAD | 0.363 | 63 | 37.8 | 13.7214
38 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 41.2 | 14.9556
39 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 31.6 | 11.4708
40 | j48 | j70 | BRICK ROAD | 0.363 | 63 | 88.9 | 32.2707
41 | j49 | j46 | interlocking | 0.363 | 63 | 47.8 | 17.3514
42 | j43 | j41 | BRICK ROAD | 0.363 | 63 | 45.9 | 16.6617
43 | j45 | j40 | interlocking | 0.363 | 63 | 3.1 | 1.1253
44 | j42 | j29 | interlocking | 0.363 | 63 | 77.6 | 28.1688
45 | j42 | j48 | BRICK ROAD | 0.363 | 63 | 31.3 | 11.3619
46 | j40 | j29 | BRICK ROAD |  | 63 | 81.2 | 0
47 | J76 | J74 | interlocking | 0.375 | 75 | 6 | 2.25
48 | J25 | J29 | BRICK ROAD | 0.375 | 75 | 4 | 1.5
49 | J25 | J29 | interlocking | 0.375 | 75 | 3 | 1.125
50 | J187 | J176 | B.T ROAD | 0.375 | 75 | 3 | 1.125
51 | J2 | J5 | BRICK ROAD | 0.41 | 110 | 273.2 | 112.012
52 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 6.6 | 2.706
53 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 76 | 31.16
54 | J5 | J25 | BRICK ROAD | 0.41 | 110 | 55.8 | 22.878
55 | J25 | J34 | BRICK ROAD | 0.41 | 110 | 57.8 | 23.698
56 | J34 | J37 | BRICK ROAD | 0.41 | 110 | 41.2 | 16.892
57 | J37 | J38 | BRICK ROAD | 0.41 | 110 | 39.3 | 16.113
58 | J38 | J39 | BRICK ROAD | 0.41 | 110 | 49.9 | 20.459
59 | J39 | J42 | BRICK ROAD | 0.41 | 110 | 29.8 | 12.218
60 | J42 | J59 | BRICK ROAD | 0.41 | 110 | 48.5 | 19.885
61 | J125(1) | J125 | interlocking | 0.41 | 110 | 6.7 | 2.747
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## hasthara 2
HATHSARA (JMR) BLOCK-MANGRAURA
s.no | Start Node | End Node | Type of Road | WIDTH OF EXCAVATION | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | 97 | 95 | brick road | 0.36 | 63 | 3 | 3
2 | 97 | 96 | brick road | 0.36 | 63 | 23 | 26
3 | 98 | 97 | brick road | 0.36 | 63 | 38.9 | 64.9
4 | 108 | 98 |  |  | 110 | 76 | 140.9
5 | 181a | 181b |  |  | 63 | 150 | 290.9
6 | 125 | 120 | interlocking | 0.46 | 110 | 6.5 | 297.4
7 | 108 | 125 |  |  | 110 | 130.9 | 428.3
8 | 108 | 118 | brick road | 0.36 | 63 | 35 | 463.3
9 | 108 | 118 |  |  | 63 | 150.1 | 613.4
10 | 108 | 118 | brick road | 0.36 | 63 | 3 | 616.4
11 | 108 | 118 |  |  | 63 | 80 | 696.4
12 | 108a | 108b |  |  | 63 | 65 | 761.4
13 | 40 | 29 |  |  | 63 | 20.5 | 781.9
14 | 41 | 40 |  |  | 63 | 15 | 796.9
15 | 189 | 187 |  |  | 75 | 79 | 875.9
16 | 178 | 176 |  |  | 90 | 30 | 905.9
17 | 255 | 256 |  |  | 63 | 80 | 985.9
18 | 255 | 257 |  |  | 63 | 50 | 1035.9
19 | 253 | 255 |  |  | 63 | 123.9 | 1159.8
20 | 253a | 253b |  |  | 63 | 30.1 | 1189.9
21 | 253 | 254 |  |  | 63 | 101.2 | 1291.1
22 | 231a | 231b |  |  | 63 | 10.3 | 1301.4
23 | 231 | 253 |  |  | 63 | 598.5 | 1899.9
24 | 33a | 33b |  |  | 63 | 350.9 | 2250.8
25 | 88a | 88b |  |  | 63 | 16.1 | 2266.9
26 | 77a | 77b |  |  | 63 | 25.6 | 2292.5
27 | 77 | 88 |  |  | 63 | 175.4 | 2467.9
28 | 77 | 80 |  |  | 63 | 125.6 | 2593.5
29 | 77 | 75 | interlocking | 0.46 | 63 | 6.3 | 2599.8
30 | 75 | 74 |  |  | 63 | 56.1 | 2655.9
31 | 70 | 75 |  |  | 63 | 70 | 2725.9
32 | 70 | 55 | brick road | 0.36 | 63 | 3 | 2728.9
33 | 61a | 61b |  |  | 63 | 16.9 | 2745.8
34 | 61 | 70 |  |  | 63 | 91 | 2836.8
35 | 61 | 62 |  |  | 63 | 35.1 | 2871.9
36 | 61 | 62 | brick road | 0.36 | 63 | 3 | 2874.9
37 | 60 | 62 |  |  | 63 | 15 | 2889.9
38 | 64a | 64b |  |  | 63 | 10.9 | 2900.8
39 | 60a | 60b |  |  | 63 | 30.1 | 2930.9
40 | 15 | 93 |  |  | 63 | 250 | 3180.9
41 | 38a | 38b |  |  | 63 | 20 | 3200.9
42 | 249a | 249b |  |  | 63 | 60 | 3260.9
43 | 60 | 64 | brick road | 0.36 | 63 | 87 | 3347.9
44 | 57 | 60 |  |  | 63 | 34 | 3381.9
45 | 57 | 58 |  |  | 63 | 38 | 3419.9 |  |  | 51.5
46 | 49a | 49b |  |  | 63 | 50 | 3469.9
47 | 49 | 57 |  |  | 63 | 93 | 3562.9
48 | 59 | 49 |  |  | 63 | 89.9 | 3652.8
49 | 98 | 59 |  |  | 110 | 55 | 3707.8
50 | 98a | 98b |  |  | 63 | 25 | 3732.8
51 | 97 | 95 |  |  | 63 | 73 | 3805.8
52 | 97a | 97b |  |  | 63 | 80.1 | 3885.9
53 | 5 | 7 |  |  | 63 | 154 | 4039.9
54 | 5 | 8 |  |  | 110 | 30 | 4069.9
55 | 5a | 5b |  |  | 63 | 69 | 4138.9
56 | 43a | 43b |  |  | 63 | 85.3 | 4224.2
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## hathsara hydro
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J1 | OHT | 125 | 6 | 6 | 3 | 1 | 4 | no
2 | J1 | J2 | 125 | 114 | 6 | 3 | 1 | 4 | no
3 | J39 | J42 | 110 | 29.8 | 6 | 3 | 1 | 4 | no
4 | J42 | J59 | 110 | 48.5 | 6 | 3 | 1 | 4 | no
5 | J125(1) | J125 | 110 | 69.3 | 6 | 3 | 1 | 4 | no
6 | J125(1) | J125 | 110 | 6.7 | 6 | 3 | 1 | 4 | no
7 | j59 | j105 | 110 | 48.6 | 6 | 3 | 1 | 4 | no
8 | j105 | j108 | 110 | 64.6 | 6 | 3 | 1 | 4 | no
9 | j108 | j124 | 110 | 125.4 | 6 | 3 | 1 | 4 | no
10 | j125 | j160 | 63 | 1.8 | 6 | 3 | 1 | 4 | no
11 | j125 | j160 | 63 | 80 | 6 | 3 | 1 | 4 | no
12 | j125 | j160 | 63 | 4.3 | 6 | 3 | 1 | 4 | no
13 | j125 | j160 | 63 | 53.2 | 6 | 3 | 1 | 4 | no
14 | j170 | j171 | 63 | 94.8 | 6 | 3 | 1 | 4 | no
15 | j171 | j174 | 63 | 77.1 | 6 | 3 | 1 | 4 | no
16 | j174 | j177 | 63 | 81 | 6 | 3 | 1 | 4 | no
17 | j177 | j181 | 63 | 122.5 | 6 | 3 | 1 | 4 | no
18 | j181 | j184 | 63 | 219.4 | 6 | 3 | 1 | 4 | no
19 | j184 | j185 | 63 | 41.6 | 6 | 3 | 1 | 4 | no
20 | j185 | j183 | 63 | 19.4 | 6 | 3 | 1 | 4 | no
21 | j174 | j168(1) | 63 | 128.3 | 6 | 3 | 1 | 4 | no
22 | j168(1) | j168(2) | 63 | 69.6 | 6 | 3 | 1 | 4 | no
23 | j168(1) | j168 | 63 | 115 | 6 | 3 | 1 | 4 | no
24 | j168 | j169 | 63 | 76.5 | 6 | 3 | 1 | 4 | no
25 | j169 | j166 | 63 | 1.8 | 6 | 3 | 1 | 4 | no
26 | j169 | j166 | 63 | 830.5 | 6 | 3 | 1 | 4 | no
27 | J166 | J165 | 63 | 2 | 6 | 3 | 1 | 4 | no
28 | J166 | J136 | 63 | 192 | 6 | 3 | 1 | 4 | no
29 | J136(1) | J136 | 63 | 8.6 | 6 | 3 | 1 | 4 | no
30 | J136(1) | J137 | 63 | 38.9 | 6 | 3 | 1 | 4 | no
31 | J137 | J143 | 63 | 44.1 | 6 | 3 | 1 | 4 | no
32 | J137 | J134 | 63 | 43 | 6 | 3 | 1 | 4 | no
33 | J136(1) | J134 | 63 | 82 | 6 | 3 | 1 | 4 | no
34 | J134 | J131 | 63 | 38.4 | 6 | 3 | 1 | 4 | no
35 | J131 | J129 | 63 | 28 | 6 | 3 | 1 | 4 | no
36 | J131 | J130 | 63 | 71.2 | 6 | 3 | 1 | 4 | no
37 | J130 | J129 | 63 | 37 | 6 | 3 | 1 | 4 | no
38 | J132 | J115 | 63 | 154 | 6 | 3 | 1 | 4 | no
39 | J130 | J132 | 63 | 48.2 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J2 | J5 | 110 | 273.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J5 | J25 | 110 | 6.6 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J5 | J25 | 110 | 76 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J5 | J25 | 110 | 55.8 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J25 | J34 | 110 | 57.8 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J34 | J37 | 110 | 41.2 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J37 | J38 | 110 | 39.3 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J38 | J39 | 110 | 49.9 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J115 | J103 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J115 | J109 | 63 | 96.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J115 | J101 | 63 | 40 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J109 | J110 | 63 | 7.7 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J109 | J110 | 63 | 21.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J109 | J110 | 63 | 31.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J109 | J110 | 63 | 23 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J110 | J149 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J110 | J149 | 63 | 455.1 | 5.5 | 3.3 | 1 | 4.3 | no
18 | J149 | J155 | 63 | 143.7 | 5.5 | 3.3 | 1 | 4.3 | no
19 | J155 | J154 | 63 | 30.5 | 5.5 | 3.3 | 1 | 4.3 | no
20 | J155 | J156 | 63 | 39.5 | 5.5 | 3.3 | 1 | 4.3 | no
21 | J156 | J153 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
22 | J156 | J161 | 63 | 136 | 5.5 | 3.3 | 1 | 4.3 | no
23 | J161 | 162 | 63 | 14 | 5.5 | 3.3 | 1 | 4.3 | no
24 | J162 | J146 | 63 | 275.5 | 5.5 | 3.3 | 1 | 4.3 | no
25 | J162 | J164 | 63 | 232.7 | 5.5 | 3.3 | 1 | 4.3 | no
26 | J161 | J149 | 63 | 226.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | J180 | J102 | 63 | 167.6 | 5.5 | 3.3 | 1 | 4.3 | no
28 | J102 | J99 | 63 | 50.3 | 5.5 | 3.3 | 1 | 4.3 | no
29 | J102 | J76 | 63 | 223.1 | 5.5 | 3.3 | 1 | 4.3 | no
30 | J3 | J11 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no
31 | J34 | J36 | 63 | 2.4 | 5.5 | 3.3 | 1 | 4.3 | no
32 | J34 | J36 | 63 | 15.5 | 5.5 | 3.3 | 1 | 4.3 | no
33 | J37 | J23 | 63 | 51 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J3 | J1 | 110 | 155 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | J4 | J3 | 90 | 116.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | J163 | J176 | 90 | 188.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | J163 | J125(1) | 90 | 180.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | J37 | J23 | 63 | 11.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | J37 | J23 | 63 | 3.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | J23 | J24 | 63 | 55.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | J23 | J12 | 63 | 60 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | J12(1) | J12(2) | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | J12(1) | J12(2) | 63 | 27.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | J5 | J28 | 63 | 327.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | J28(1) | J28(2) | 63 | 71.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | J28(2) | J28 | 63 | 47.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | J28 | J21 | 63 | 4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | J28 | J21 | 63 | 251 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | J21 | J19 | 63 | 40.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | J19 | J22 | 63 | 18.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | J19 | J17 | 63 | 52.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | J17 | J18 | 63 | 57.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | J17 | J11 | 63 | 101.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | J11 | J13 | 63 | 53.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | J11 | J36 | 63 | 101.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | J4 | J16 | 63 | 101.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | J4 | J16 | 63 | 138.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | J16 | J13 | 63 | 62 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | J16 | J30 | 63 | 87.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | J30 | J22 | 63 | 84.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | J30 | J22 | 63 | 8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | J30 | J103 | 63 | 95.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | J103 | J136 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | J103 | J136 | 63 | 303 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | J103 | J115 | 63 | 128 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | J103 | J115 | 63 | 138.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | J103 | J100 | 63 | 363 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | J103 | J100 | 63 | 409 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J76 | J4 | 75 | 480 | 6 | 3 | 1 | 4 | no
2 | J76 | J74 | 75 | 6 | 6 | 3 | 1 | 4 | no
3 | J25 | J29 | 75 | 4 | 6 | 3 | 1 | 4 | no
4 | J25 | J29 | 75 | 16 | 6 | 3 | 1 | 4 | no
5 | J25 | J29 | 75 | 3 | 6 | 3 | 1 | 4 | no
6 | J187 | J189 | 75 | 92.9 | 6 | 3 | 1 | 4 | no
7 | J187 | J176 | 75 | 3 | 6 | 3 | 1 | 4 | no
8 | J187 | J176 | 75 | 676.3 | 6 | 3 | 1 | 4 | no
9 | J100 | J168 | 63 | 3 | 6 | 3 | 1 | 4 | no
10 | J100 | J168 | 63 | 122.5 | 6 | 3 | 1 | 4 | no
11 | J100 | J168 | 63 | 60 | 6 | 3 | 1 | 4 | no
12 | J100 | J168 | 63 | 127.2 | 6 | 3 | 1 | 4 | no
13 | J100 | J38 | 63 | 161.6 | 6 | 3 | 1 | 4 | no
14 | J29 | J31 | 63 | 27.8 | 6 | 3 | 1 | 4 | no
15 | J29 | J31 | 63 | 25.7 | 6 | 3 | 1 | 4 | no
16 | J29 | J31 | 63 | 15 | 6 | 3 | 1 | 4 | no
17 | J29 | J31 | 63 | 15.5 | 6 | 3 | 1 | 4 | no
18 | J31(1) | J31(2) | 63 | 2.3 | 6 | 3 | 1 | 4 | no
19 | J31(1) | J31(2) | 63 | 32.5 | 6 | 3 | 1 | 4 | no
20 | J31 | J32 | 63 | 31 | 6 | 3 | 1 | 4 | no
21 | J31 | J33 | 63 | 19.5 | 6 | 3 | 1 | 4 | no
22 | J33(1) | J33(2) | 63 | 41 | 6 | 3 | 1 | 4 | no
23 | J33(2) | J33 | 63 | 186.9 | 6 | 3 | 1 | 4 | no
24 | J189 | J90 | 63 | 23.5 | 6 | 3 | 1 | 4 | no
25 | J189 | J191 | 63 | 249.5 | 6 | 3 | 1 | 4 | no
26 | J191 | J201 | 63 | 37.5 | 6 | 3 | 1 | 4 | no
27 | J191 | J192 | 63 | 155 | 6 | 3 | 1 | 4 | no
28 | J192(1) | J202 | 63 | 83.8 | 6 | 3 | 1 | 4 | no
29 | J192(1) | J202 | 63 | 3 | 6 | 3 | 1 | 4 | no
30 | J202 | J206 | 63 | 92 | 6 | 3 | 1 | 4 | no
31 | J202 | J217 | 63 | 135.3 | 6 | 3 | 1 | 4 | no
32 | J217 | J218 | 63 | 25 | 6 | 3 | 1 | 4 | no
33 | J217 | J215 | 63 | 141.2 | 6 | 3 | 1 | 4 | no
34 | J215 | J215(1) | 63 | 42.5 | 6 | 3 | 1 | 4 | no
35 | J215 | J213 | 63 | 16 | 6 | 3 | 1 | 4 | no
36 | J187 | J188 | 63 | 165.5 | 6 | 3 | 1 | 4 | no
37 | J163 | J141 | 63 | 3.3 | 6 | 3 | 1 | 4 | no
38 | J163 | J141 | 63 | 275 | 6 | 3 | 1 | 4 | no
39 | J141(1) | J141 | 63 | 27 | 6 | 3 | 1 | 4 | no
40 | J76 | J242 | 63 | 313.5 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | J242 | J227 | 63 | 683.7 | 5.5 | 3.3 | 1 | 4.3 | no
2 | J242 | J227 | 63 | 6 | 5.5 | 3.3 | 1 | 4.3 | no
3 | J242 | J242(1) | 63 | 153 | 5.5 | 3.3 | 1 | 4.3 | no
4 | J76 | J242 | 63 | 116 | 5.5 | 3.3 | 1 | 4.3 | no
5 | J242(2) | J242(3) | 63 | 38.5 | 5.5 | 3.3 | 1 | 4.3 | no
6 | J242(3) | J242(4) | 63 | 20.5 | 5.5 | 3.3 | 1 | 4.3 | no
7 | J242(5) | J242(6) | 63 | 37.8 | 5.5 | 3.3 | 1 | 4.3 | no
8 | J76 | J242 | 63 | 6 | 5.5 | 3.3 | 1 | 4.3 | no
9 | J242 | J240 | 63 | 30.8 | 5.5 | 3.3 | 1 | 4.3 | no
10 | J240 | J241 | 63 | 89.6 | 5.5 | 3.3 | 1 | 4.3 | no
11 | J240 | J239 | 63 | 62 | 5.5 | 3.3 | 1 | 4.3 | no
12 | J242 | J245 | 63 | 47.5 | 5.5 | 3.3 | 1 | 4.3 | no
13 | J245 | J249 | 63 | 241.1 | 5.5 | 3.3 | 1 | 4.3 | no
14 | J249 | J250 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | J249(1) | J250(1) | 63 | 10.7 | 5.5 | 3.3 | 1 | 4.3 | no
16 | J250(1) | J250(2) | 63 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
17 | J250(1) | J251 | 63 | 127.5 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j39 | j36 | 63 | 34.8 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j42 | j44 | 63 | 29.9 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j44 | j53 | 63 | 37.1 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j44 | j43 | 63 | 37.8 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j48 | j70 | 63 | 41.2 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j48 | j70 | 63 | 31.6 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j48 | j70 | 63 | 88.9 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j46 | j45 | 63 | 65.1 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j49 | j46 | 63 | 47.8 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j43 | j46 | 63 | 43.3 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j43 | j46 | 63 | 2.6 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j43 | j41 | 63 | 45.9 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j45 | j40 | 63 | 3.1 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j45 | j40 | 63 | 10.7 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j42 | j29 | 63 | 77.6 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j42 | j29 | 63 | 44.2 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j42 | j48 | 63 | 31.3 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j48 | j47 | 63 | 34.9 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j40 | j29 | 63 | 81.2 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 97 | 95 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | 97 | 96 | 63 | 23 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | 98 | 97 | 63 | 38.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | 108 | 98 | 110 | 76 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | 181a | 181b | 63 | 150 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | 125 | 120 | 110 | 6.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | 108 | 125 | 110 | 130.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | 108 | 118 | 63 | 35 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | 108 | 118 | 63 | 150.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | 108 | 118 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | 108 | 118 | 63 | 80 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | 108a | 108b | 63 | 65 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | 40 | 29 | 63 | 20.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | 41 | 40 | 63 | 15 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | 189 | 187 | 75 | 79 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | 178 | 176 | 90 | 30 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | 255 | 256 | 63 | 80 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | 255 | 257 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | 253 | 255 | 63 | 123.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | 253a | 253b | 63 | 30.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | 253 | 254 | 63 | 101.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | 231a | 231b | 63 | 10.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | 231 | 253 | 63 | 598.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | 33a | 33b | 63 | 350.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | 88a | 88b | 63 | 16.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Hathsara | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | 77a | 77b | 63 | 25.6 | 5.5 | 3.3 | 1 | 4.3 | no
2 | 77 | 88 | 63 | 175.4 | 5.5 | 3.3 | 1 | 4.3 | no
3 | 77 | 80 | 63 | 125.6 | 5.5 | 3.3 | 1 | 4.3 | no
4 | 77 | 75 | 63 | 6.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | 75 | 74 | 63 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
6 | 70 | 75 | 63 | 70 | 5.5 | 3.3 | 1 | 4.3 | no
7 | 70 | 55 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
8 | 61a | 61b | 63 | 16.9 | 5.5 | 3.3 | 1 | 4.3 | no
9 | 61 | 70 | 63 | 91 | 5.5 | 3.3 | 1 | 4.3 | no
10 | 61 | 62 | 63 | 35.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | 61 | 62 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
12 | 60 | 62 | 63 | 15 | 5.5 | 3.3 | 1 | 4.3 | no
13 | 64a | 64b | 63 | 10.9 | 5.5 | 3.3 | 1 | 4.3 | no
14 | 60a | 60b | 63 | 30.1 | 5.5 | 3.3 | 1 | 4.3 | no
15 | 15 | 93 | 63 | 250 | 5.5 | 3.3 | 1 | 4.3 | no
16 | 38a | 38b | 63 | 20 | 5.5 | 3.3 | 1 | 4.3 | no
17 | 249a | 249b | 63 | 60 | 5.5 | 3.3 | 1 | 4.3 | no
18 | 60 | 64 | 63 | 87 | 5.5 | 3.3 | 1 | 4.3 | no
19 | 57 | 60 | 63 | 34 | 5.5 | 3.3 | 1 | 4.3 | no
20 | 57 | 58 | 63 | 38 | 5.5 | 3.3 | 1 | 4.3 | no
21 | 49a | 49b | 63 | 50 | 5.5 | 3.3 | 1 | 4.3 | no
22 | 49 | 57 | 63 | 93 | 5.5 | 3.3 | 1 | 4.3 | no
23 | 59 | 49 | 63 | 89.9 | 5.5 | 3.3 | 1 | 4.3 | no
24 | 98 | 59 | 110 | 55 | 5.5 | 3.3 | 1 | 4.3 | no
25 | 98a | 98b | 63 | 25 | 5.5 | 3.3 | 1 | 4.3 | no
26 | 97 | 95 | 63 | 73 | 5.5 | 3.3 | 1 | 4.3 | no
27 | 97a | 97b | 63 | 80.1 | 5.5 | 3.3 | 1 | 4.3 | no
28 | 5 | 7 | 63 | 154 | 5.5 | 3.3 | 1 | 4.3 | no
29 | 5 | 8 | 110 | 30 | 5.5 | 3.3 | 1 | 4.3 | no
30 | 5a | 5b | 63 | 69 | 5.5 | 3.3 | 1 | 4.3 | no
31 | 43a | 43b | 63 | 85.3 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## brahupurhydro
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j7 | j1 | 200 | 1502.2 | 6 | 3 | 1 | 4 | no
2 | j7 | j1 | 200 | 7.8 | 6 | 3 | 1 | 4 | no
3 | j111 | j112 | 63 | 215 | 6 | 3 | 1 | 4 | no
4 | j143 | j53 | 63 | 5 | 6 | 3 | 1 | 4 | no
5 | j93 | 92 | 63 | 7 | 6 | 3 | 1 | 4 | no
6 | j111 | j240 | 63 | 83.3 | 6 | 3 | 1 | 4 | no
7 | j186 | j141 | 63 | 65 | 6 | 3 | 1 | 4 | no
8 | j186 | j179 | 63 | 26.8 | 6 | 3 | 1 | 4 | no
9 | j232 | j179 | 63 | 53 | 6 | 3 | 1 | 4 | no
10 | j179 | j163 | 63 | 76.2 | 6 | 3 | 1 | 4 | no
11 | j179 | j163 | 63 | 5 | 6 | 3 | 1 | 4 | no
12 | j93 | j117 | 63 | 5 | 6 | 3 | 1 | 4 | no
13 | j93 | j163 | 63 | 7 | 6 | 3 | 1 | 4 | no
14 | j50 | j51 | 63 | 208.3 | 6 | 3 | 1 | 4 | no
15 | j5 | j4 | 63 | 94.6 | 6 | 3 | 1 | 4 | no
16 | j8 | j9 | 63 | 6 | 6 | 3 | 1 | 4 | no
17 | j8 | j9 | 63 | 76 | 6 | 3 | 1 | 4 | no
18 | j79 | j7 | 63 | 815.3 | 6 | 3 | 1 | 4 | no
19 | j79 | j35 | 63 | 46.3 | 6 | 3 | 1 | 4 | no
20 | j143 | j163 | 63 | 180 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j41 | j7 | 160 | 625 | 5.5 | 3 | 1 | 4 | no
2 | j167 | j229 | 140 | 231.3 | 5.5 | 3 | 1 | 4 | no
3 | j229 | j216 | 140 | 10 | 5.5 | 3 | 1 | 4 | no
4 | j216 | j41 | 140 | 338 | 5.5 | 3 | 1 | 4 | no
5 | j41 | j50 | 125 | 129.7 | 5.5 | 3 | 1 | 4 | no
6 | j50 | j111 | 63 | 111.8 | 5.5 | 3 | 1 | 4 | no
7 | j47 | j254 | 63 | 112.3 | 5.5 | 3 | 1 | 4 | no
8 | j24 | j254 | 63 | 161 | 5.5 | 3 | 1 | 4 | no
9 | j32 | j65 | 63 | 25 | 5.5 | 3 | 1 | 4 | no
10 | j65 | j54 | 63 | 30 | 5.5 | 3 | 1 | 4 | no
11 | j65 | j151 | 63 | 23.4 | 5.5 | 3 | 1 | 4 | no
12 | j256 | j267 | 63 | 104.3 | 5.5 | 3 | 1 | 4 | no
13 | j267 | j187 | 63 | 53.2 | 5.5 | 3 | 1 | 4 | no
14 | j267 | j315 | 63 | 123.2 | 5.5 | 3 | 1 | 4 | no
15 | j315 | j271 | 63 | 40 | 5.5 | 3 | 1 | 4 | no
16 | j315 | j271 | 63 | 11.1 | 5.5 | 3 | 1 | 4 | no
17 | j315 | j321 | 63 | 186.8 | 5.5 | 3 | 1 | 4 | no
18 | j216 | j265 | 63 | 315.6 | 5.5 | 3 | 1 | 4 | no
19 | j55 | j119 | 63 | 21.1 | 5.5 | 3 | 1 | 4 | no
20 | j88 | j66 | 63 | 30.2 | 5.5 | 3 | 1 | 4 | no
21 | j58 | j88 | 63 | 27.2 | 5.5 | 3 | 1 | 4 | no
22 | j55 | j56 | 63 | 20.5 | 5.5 | 3 | 1 | 4 | no
23 | j88 | j72 | 63 | 24.7 | 5.5 | 3 | 1 | 4 | no
24 | j72 | j84 | 63 | 54.5 | 5.5 | 3 | 1 | 4 | no
25 | j27 | j84 | 63 | 48.5 | 5.5 | 3 | 1 | 4 | no
26 | j27 | j45 | 63 | 46.8 | 5.5 | 3 | 1 | 4 | no
27 | j45 | j64 | 63 | 41.5 | 5.5 | 3 | 1 | 4 | no
28 | j45 | j155 | 63 | 62.6 | 5.5 | 3 | 1 | 4 | no
29 | j45 | j155 | 63 | 34 | 5.5 | 3 | 1 | 4 | no
30 | j155 | j254 | 63 | 26 | 5.5 | 3 | 1 | 4 | no
31 | j254 | j45 | 63 | 71.3 | 5.5 | 3 | 1 | 4 | no
32 | j254 | j151 | 63 | 19 | 5.5 | 3 | 1 | 4 | no
33 | j151 | j72 | 63 | 80.2 | 5.5 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j254 | j207 | 63 | 198.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j254 | j207 | 63 | 38.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j306 | j215 | 63 | 65.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j306 | j324 | 63 | 7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j324 | j206 | 63 | 55 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j206 | j142 | 63 | 106 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j206 | j184 | 63 | 85.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j184 | j120 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j184 | j319 | 63 | 79 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j292 | j300 | 63 | 41 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j309 | j309a | 63 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j322 | j309 | 63 | 91.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j322a | j285 | 63 | 103 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j324 | j233 | 63 | 113.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j233 | j339 | 63 | 65.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j233 | j259 | 63 | 368.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j233 | j259 | 63 | 7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j259 | j102 | 110 | 311.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j246 | j102 | 63 | 413.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j246 | j102 | 63 | 10 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j80 | j339 | 63 | 307.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j259 | j216 | 125 | 211 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j306 | j259 | 63 | 803.2 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j207 | j204 | 63 | 72.3 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j198 | j107 | 63 | 133 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j107 | j132 | 63 | 102.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j132 | j60 | 63 | 23.2 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j107 | j305 | 63 | 76.5 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j279 | j152 | 63 | 37.2 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j355 | j20 | 63 | 157.2 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j86 | j162 | 63 | 98.2 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j162 | j42 | 63 | 82.3 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j42 | j40 | 63 | 78 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j42 | j61 | 63 | 73.2 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j162 | j109 | 63 | 45 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j145 | j146 | 63 | 69.3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j224 | j274 | 63 | 125.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j224 | j274 | 63 | 5 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j274 | j326 | 63 | 148.8 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j274 | j291 | 63 | 248.6 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j291 | j347 | 63 | 15 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j347 | j190 | 63 | 162.3 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j228 | j338 | 63 | 65 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j346 | j330 | 63 | 47.7 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j327 | j323 | 63 | 30.3 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j327 | j323 | 63 | 46.4 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j291 | j327 | 63 | 51 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j327 | j349 | 63 | 33.3 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j327a | j327b | 63 | 35 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j349 | j225 | 63 | 29 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j225 | j223 | 63 | 16 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j225 | j262 | 63 | 21.3 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j225 | j218 | 63 | 46.6 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j220 | j349 | 63 | 56.3 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j122 | j73 | 63 | 75 | 6 | 3 | 1 | 4 | no
2 | j278 | j345 | 63 | 30.1 | 6 | 3 | 1 | 4 | no
3 | j345 | j157 | 63 | 65 | 6 | 3 | 1 | 4 | no
4 | j345 | j194 | 63 | 44.2 | 6 | 3 | 1 | 4 | no
5 | j304 | j283 | 63 | 15 | 6 | 3 | 1 | 4 | no
6 | j350 | j318 | 63 | 34.3 | 6 | 3 | 1 | 4 | no
7 | j296 | j350 | 63 | 30.1 | 6 | 3 | 1 | 4 | no
8 | j356 | j314 | 63 | 30.3 | 6 | 3 | 1 | 4 | no
9 | j314 | j258 | 63 | 15.2 | 6 | 3 | 1 | 4 | no
10 | j314 | j258 | 63 | 45.5 | 6 | 3 | 1 | 4 | no
11 | j202 | j129 | 63 | 31.1 | 6 | 3 | 1 | 4 | no
12 | j314 | j296 | 63 | 41 | 6 | 3 | 1 | 4 | no
13 | j350 | j147 | 63 | 31.1 | 6 | 3 | 1 | 4 | no
14 | j350 | j147 | 63 | 18 | 6 | 3 | 1 | 4 | no
15 | j109 | j255 | 63 | 50 | 6 | 3 | 1 | 4 | no
16 | j255 | j59 | 63 | 54.3 | 6 | 3 | 1 | 4 | no
17 | j123 | j255 | 63 | 51 | 6 | 3 | 1 | 4 | no
18 | j255 | j357 | 63 | 23.5 | 6 | 3 | 1 | 4 | no
19 | j208 | j342 | 63 | 65.3 | 6 | 3 | 1 | 4 | no
20 | j235 | j266 | 63 | 278.3 | 6 | 3 | 1 | 4 | no
21 | j266 | j189 | 63 | 51.3 | 6 | 3 | 1 | 4 | no
22 | j266 | j234 | 63 | 48.1 | 6 | 3 | 1 | 4 | no
23 | j235 | j266 | 63 | 7 | 6 | 3 | 1 | 4 | no
24 | j266 | j189 | 63 | 5 | 6 | 3 | 1 | 4 | no
25 | j321 | j19 | 63 | 753.3 | 6 | 3 | 1 | 4 | no
26 | j19 | j21 | 90 | 60.3 | 6 | 3 | 1 | 4 | no
27 | j19 | j49 | 75 | 120 | 6 | 3 | 1 | 4 | no
28 | j66 | j55 | 63 | 26 | 6 | 3 | 1 | 4 | no
29 | j49 | j66 | 75 | 30 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j270 | j277 | 63 | 30.1 | 5.5 | 3.5 | 1 | 4.5 | no
2 | j220 | j234 | 63 | 41 | 5.5 | 3.5 | 1 | 4.5 | no
3 | j234 | j224 | 63 | 118.3 | 5.5 | 3.5 | 1 | 4.5 | no
4 | j234 | j224 | 63 | 5 | 5.5 | 3.5 | 1 | 4.5 | no
5 | j6 | j159 | 63 | 1113.3 | 5.5 | 3.5 | 1 | 4.5 | no
6 | j159 | j115 | 63 | 489.6 | 5.5 | 3.5 | 1 | 4.5 | no
7 | j115 | j101 | 63 | 123.3 | 5.5 | 3.5 | 1 | 4.5 | no
8 | j115 | j93 | 63 | 150.8 | 5.5 | 3.5 | 1 | 4.5 | no
9 | j93 | j103 | 63 | 130.7 | 5.5 | 3.5 | 1 | 4.5 | no
10 | j93 | j144 | 63 | 37 | 5.5 | 3.5 | 1 | 4.5 | no
11 | j144 | j90 | 63 | 35.3 | 5.5 | 3.5 | 1 | 4.5 | no
12 | j143 | j165 | 63 | 10 | 5.5 | 3.5 | 1 | 4.5 | no
13 | j165 | j158 | 63 | 68 | 5.5 | 3.5 | 1 | 4.5 | no
14 | j254 | j207 | 63 | 51.5 | 5.5 | 3.5 | 1 | 4.5 | no
15 | j212 | j126 | 63 | 394.9 | 5.5 | 3.5 | 1 | 4.5 | no
16 | j126 | j56 | 63 | 170 | 5.5 | 3.5 | 1 | 4.5 | no
17 | j126 | j134 | 63 | 193 | 5.5 | 3.5 | 1 | 4.5 | no
18 | j311 | j134 | 63 | 648.3 | 5.5 | 3.5 | 1 | 4.5 | no
19 | j134 | j211 | 63 | 332.2 | 5.5 | 3.5 | 1 | 4.5 | no
20 | j161 | j161a | 63 | 61.3 | 5.5 | 3.5 | 1 | 4.5 | no
21 | j276 | j306 | 63 | 78 | 5.5 | 3.5 | 1 | 4.5 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Barahupur | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j326 | j264 | 63 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j326 | j287 | 63 | 52 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j287 | j286 | 63 | 29 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j286 | j282 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j182 | j159 | 63 | 69 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j159 | j173 | 63 | 89 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j167 | j158 | 63 | 43 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j321 | j365 | 63 | 200 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j315 | j315a | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j134 | j134a | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j117 | j118 | 63 | 37 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j117 | j121 | 63 | 20 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j121 | j127 | 63 | 28 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j128 | j130 | 63 | 30 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j229 | j197 | 125 | 48 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j264 | j209 | 63 | 29 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j209 | j289 | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j209 | j169 | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j205 | j181 | 63 | 119 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j181 | j202 | 63 | 72 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j181 | j181a | 63 | 198 | 5KG/CM22 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## brahapur jmr and road restorati
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of Pipe Line
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | :brahapur
Block |  | : Mangraura
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Pipe Length (as per Drawing) | Pipe Length (as per Site) | Width | Depth | Quantity | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | j167 | j229 | 140 | 225 | 231.3 | 0.44 | 1.14
2 | j229 | j216 | 140 | 20 | 10 | 0.44 | 1.14
3 | j216 | j41 | 140 |  | 338 | 0.44 | 1.14
4 | j41 | j50 | 125 |  | 129.7 | 0.42 | 1.12 |  | B.T | 129.7 | 0.46 | 59.662 | 129.7 | 0.46 | 59.662 | Done
5 | j50 | j111 | 63 |  | 111.8 | 0.36 | 1.06
6 | j41 | j7 | 160 |  | 625 | 0.46 | 1.16
7 | j7 | j1 | 200 | 1418 | 1502.2 | 0.5 | 1.2
8 | j7 | j1 | 200 |  | 7.8 | 0.5 | 1.2 |  | b.t crossing | 7.8 | 0.5 | 3.9 | 7.8 | 0.5 | 3.9 | Done
9 | j6 | j159 | 63 |  | 1113.3 | 0.36 | 1.06
10 | j159 | j115 | 63 |  | 489.6 | 0.36 | 1.06 |  | B.T | 489.6 | 0.46 | 225.216 | 489.6 | 0.46 | 225.216 | Done
11 | j115 | j101 | 63 |  | 123.3 | 0.36 | 1.06
12 | j115 | j93 | 63 |  | 150.8 | 0.36 | 1.06
13 | j93 | j103 | 63 |  | 130.7 | 0.36 | 1.06
14 | j93 | j144 | 63 |  | 37 | 0.36 | 1.06
15 | j144 | j90 | 63 |  | 35.3 | 0.31 | 1.06
16 | j143 | j165 | 63 |  | 10 | 0.36 | 1.06 |  | B.T | 10 | 0.46 | 4.6 | 10 | 0.46 | 4.6 | Done
17 | j165 | j158 | 63 |  | 68 | 0.36 | 1.06 |  | B.T | 68 | 0.46 | 31.28 | 68 | 0.46 | 31.28 | Done
18 | j111 | j112 | 63 |  | 215 | 0.36 | 1.06
19 | j143 | j163 | 63 |  | 180 | 0.36 | 1.06 |  | B.T | 180 | 0.46 | 82.8 | 180 | 0.46 | 82.8 | Done
20 | j143 | j53 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
21 | j93 | 92 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22 | Done
22 | j111 | j240 | 63 |  | 83.3 | 0.36 | 1.06 |  | brick road | 83.3 | 0.36 | 29.988 | 83.3 | 0.36 | 29.988 | Done
23 | j186 | j141 | 63 |  | 65 | 0.36 | 1.06
24 | j186 | j179 | 63 |  | 26.8 | 0.28 | 1.06
25 | j232 | j179 | 63 | 39 | 53 | 0.32 | 1.06
26 | j179 | j163 | 63 |  | 76.2 | 0.36 | 1.06 |  | B.T | 76.2 | 0.46 | 35.052 | 76.2 | 0.46 | 35.052 | Done
27 | j179 | j163 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
28 | j93 | j117 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
29 | j93 | j163 | 63 |  | 161 | 0.36 | 1.06 |  | b.t | 161 | 0.36 | 57.96 | 161 | 0.36 | 57.96 | Done
30 | j50 | j51 | 63 |  | 208.3 | 0.36 | 1.06
31 | j5 | j4 | 63 |  | 94.6 | 0.36 | 1.06
32 | j8 | j9 | 63 |  | 6 | 0.36 | 1.06 |  | b.t crossing | 6 | 0.36 | 2.16 | 6 | 0.36 | 2.16 | Done
33 | j8 | j9 | 63 |  | 76 | 0.36 | 1.06 |  | brick road | 76 | 0.36 | 27.36 | 76 | 0.36 | 27.36 | Done
34 | j79 A | j7 A | 63 |  | 815.3 | 0.36 | 1.06 |  | B.T | 815.3 | 0.46 | 375.038 | 815.3 | 0.46 | 375.038 | Done
35 | j79 | j35 | 63 |  | 46.3 | 0.34 | 1.06
36 | j47 | j254 | 63 |  | 112.3 | 0.36 | 1.06
37 | j24 | j254 | 63 |  | 161 | 0.36 | 1.06 |  | brick road | 161 | 0.36 | 57.96 | 161 | 0.36 | 57.96 | Done
38 | j32 | j65 | 63 |  | 25 | 0.46 | 1.06 |  | interlocking | 25 | 0.46 | 11.5 | 25 | 0.46 | 11.5 | Done
39 | j65 | j54 | 63 |  | 30 | 0.36 | 1.06
40 | j65 | j151 | 63 |  | 23.4 | 0.29 | 1.06
41 | j256 | j267 | 63 |  | 104.3 | 0.36 | 1.06
42 | j267 | j187 | 63 |  | 53.2 | 0.36 | 1.06
43 | j267 | j315 | 63 |  | 123.2 | 0.36 | 1.06
44 | j315 | j271 | 63 |  | 40 | 0.34 | 1.06
45 | j315 | j271 | 63 |  | 11.1 | 0.36 | 1.06
46 | j315 | j321 | 63 |  | 186.8 | 0.36 | 1.06
47 | j216 | j265 | 63 |  | 315.6 | 0.36 | 1.06
48 | j321 | j19 | 63 |  | 753.3 | 0.36 | 1.06
49 | j19 | j21 | 90 |  | 60.3 | 0.39 | 1.09
50 | j19 | j49 | 75 |  | 120 | 0.46 | 1.07 |  | interlocking | 120 | 0.46 | 55.2 | 120 | 0.46 | 55.2 | Done
51 | j66 | j55 | 63 |  | 26 | 0.36 | 1.06
52 | j49 | j66 | 75 |  | 30 | 0.37 | 1.07
53 | j55 | j119 | 63 |  | 21.1 | 0.33 | 1.06
54 | j88 | j66 | 63 |  | 30.2 | 0.46 | 1.06 |  | interlocking | 30.2 | 0.46 | 13.892 | 30.2 | 0.46 | 13.892 | Done
55 | j58 | j88 | 63 |  | 27.2 | 0.36 | 1.06
56 | j55 | j56 | 63 |  | 20.5 | 0.46 | 1.06 |  | interlocking | 20.5 | 0.46 | 9.43 | 20.5 | 0.46 | 9.43 | Done
57 | j88 | j72 | 63 |  | 24.7 | 0.46 | 1.06 |  | interlocking | 24.7 | 0.46 | 11.362 | 24.7 | 0.46 | 11.362 | Done
58 | j72 | j84 | 63 |  | 54.5 | 0.36 | 1.06
59 | j27 | j84 | 63 |  | 48.5 | 0.36 | 1.06
60 | j27 | j45 | 63 |  | 46.8 | 0.36 | 1.06
61 | j45 | j64 | 63 |  | 41.5 | 0.36 | 1.06
62 | j45 | j155 | 63 |  | 62.6 | 0.36 | 1.06
63 | j45 | j155 | 63 |  | 34 | 0.36 | 1.06 |  | brick road | 34 | 0.36 | 12.24 | 34 | 0.36 | 12.24 | Done
64 | j155 | j254 | 63 |  | 26 | 0.29 | 1.06
65 | j254 | j45 | 63 |  | 71.3 | 0.36 | 1.06 |  | brick road | 71.3 | 0.36 | 25.668 | 71.3 | 0.36 | 25.668 | Done
66 | j254 | j151 | 63 |  | 19 | 0.36 | 1.06 |  | brick road | 19 | 0.36 | 6.84 | 19 | 0.36 | 6.84 | Done
67 | j151 | j72 | 63 |  | 80.2 | 0.46 | 1.06 |  | interlocking | 80.2 | 0.46 | 36.892 | 80.2 | 0.46 | 36.892 | Done
68 | j254 | j207 | 63 |  | 198.3 | 0.36 | 1.06 |  | brick road | 198.3 | 0.36 | 71.388 | 198.3 | 0.36 | 71.388 | Done
69 | j254 | j207 | 63 |  | 38.7 | 0.46 | 1.06 |  | interlocking | 38.7 | 0.46 | 17.802 | 38.7 | 0.46 | 17.802 | Done
70 | j254 | j207 | 63 |  | 51.5 | 0.36 | 1.06
71 | j212 | j126 | 63 |  | 394.9 | 0.36 | 1.06 |  | brick road | 394.9 | 0.46 | 181.654 | 394.9 | 0.46 | 181.654 | Done
72 | j126 | j56 | 63 |  | 170 | 0.36 | 1.06 |  | brick road | 170 | 0.46 | 78.2 | 170 | 0.46 | 78.2 | Done
73 | j126 | j134 | 63 |  | 193 | 0.36 | 1.06 |  | brick road | 193 | 0.46 | 88.78 | 193 | 0.46 | 88.78 | Done
74 | j311 | j134 | 63 |  | 648.3 | 0.36 | 1.06
75 | j134 | j211 | 63 |  | 332.2 | 0.36 | 1.06 |  | brick road | 332.2 | 0.46 | 152.812 | 332.2 | 0.46 | 152.812 | Done
76 | j161 | j161a | 63 |  | 61.3 | 0.36 | 1.06
77 | j276 | j306 | 63 | 106 | 78 | 0.36 | 1.06
78 | j306 | j215 | 63 | 49 | 65.5 | 0.36 | 1.06
79 | j306 | j324 | 63 |  | 7 | 0.46 | 1.06 |  | interlocking | 7 | 0.46 | 3.22 | 7 | 0.46 | 3.22 | Done
80 | j324 | j206 | 63 | 65 | 55 | 0.36 | 1.06
81 | j206 | j142 | 63 | 45 | 106 | 0.36 | 1.06
82 | j206 | j184 | 63 | 88 | 85.1 | 0.36 | 1.06
83 | j184 | j120 | 63 | 26 | 50 | 0.36 | 1.06
84 | j184 | j319 | 63 | 38 | 79 | 0.36 | 1.06
85 | j292 | j300 | 63 |  | 41 | 0.36 | 1.06
86 | j309 | j309a | 63 |  | 51 | 0.46 | 1.06 |  | interlocking | 51 | 0.46 | 23.46 | 51 | 0.46 | 23.46 | Done
87 | j322 | j309 | 63 |  | 91.3 | 0.36 | 1.06
88 | j322a | j285 | 63 |  | 103 | 0.36 | 1.06
89 | j324 | j233 | 63 | 112 | 113.3 | 0.36 | 1.06
90 | j233 | j339 | 63 | 104 | 65.4 | 0.36 | 1.06
91 | j233 | j259 | 63 |  | 368.3 | 0.36 | 1.06
92 | j233 | j259 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52 | Done
93 | j259 | j102 | 110 | 356 | 311.1 | 0.41 | 1.1
94 | j246 | j102 | 63 |  | 413.1 | 0.36 | 1.06
95 | j246 | j102 | 63 |  | 10 | 0.36 | 1.06 |  | culvert
96 | j80 | j339 | 63 |  | 307.7 | 0.36 | 1.06
97 | j259 | j216 | 125 |  | 211 | 0.42 | 1.12
98 | j306 | j259 | 63 |  | 803.2 | 0.36 | 1.06
99 | j207 | j204 | 63 | 79 | 72.3 | 0.36 | 1.06
100 | j198 | j107 | 63 | 121 | 133 | 0.36 | 1.06 |  | brick road | 133 | 0.36 | 47.88 | 133 | 0.36 | 47.88 | Done
101 | j107 | j132 | 63 | 64 | 102.3 | 0.36 | 1.06
102 | j132 | j60 | 63 |  | 23.2 | 0.29 | 1.06
103 | j107 | j305 | 63 |  | 76.5 | 0.36 | 1.06
104 | j279 | j152 | 63 |  | 37.2 | 0.34 | 1.06
105 | j355 | j20 | 63 |  | 157.2 | 0.36 | 1.06
106 | j86 | j162 | 63 | 105 | 98.2 | 0.36 | 1.06
107 | j162 | j42 | 63 |  | 82.3 | 0.36 | 1.06
108 | j42 | j40 | 63 |  | 78 | 0.36 | 1.06
109 | j42 | j61 | 63 |  | 73.2 | 0.36 | 1.06
110 | j162 | j109 | 63 |  | 45 | 0.36 | 1.06
111 | j145 | j146 | 63 |  | 69.3 | 0.36 | 1.06
112 | j224 | j274 | 63 | 126 | 125.1 | 0.36 | 1.06
113 | j224 | j274 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
114 | j274 | j326 | 63 | 167 | 148.8 | 0.36 | 1.06 |  | brick road | 148.8 | 0.36 | 53.568 | 148.8 | 0.36 | 53.568 | Done
115 | j274 | j291 | 63 |  | 248.6 | 0.36 | 1.06
116 | j291 | j347 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4 | Done
117 | j347 | j190 | 63 |  | 162.3 | 0.36 | 1.06
118 | j228 | j338 | 63 |  | 65 | 0.36 | 1.06
119 | j346 | j330 | 63 |  | 47.7 | 0.36 | 1.06
120 | j327 | j323 | 63 |  | 30.3 | 0.36 | 1.06
121 | j327 | j323 | 63 |  | 46.4 | 0.36 | 1.06
122 | j291 | j327 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36 | Done
123 | j327 | j349 | 63 |  | 33.3 | 0.36 | 1.06 |  | brick road | 33.3 | 0.36 | 11.988 | 33.3 | 0.36 | 11.988 | Done
124 | j327a | j327b | 63 |  | 35 | 0.36 | 1.06
125 | j349 | j225 | 63 |  | 29 | 0.36 | 1.06 |  | brick road | 29 | 0.36 | 10.44 | 29 | 0.36 | 10.44 | Done
126 | j225 | j223 | 63 |  | 16 | 0.35 | 1.06
127 | j225 | j262 | 63 |  | 21.3 | 0.36 | 1.06 |  | brick road | 21.3 | 0.36 | 7.668 | 21.3 | 0.36 | 7.668 | Done
128 | j225 | j218 | 63 |  | 46.6 | 0.36 | 1.06 |  | brick road | 46.6 | 0.36 | 16.776 | 46.6 | 0.36 | 16.776 | Done
129 | j220 | j349 | 63 |  | 56.3 | 0.36 | 1.06 |  | brick road | 56.3 | 0.36 | 20.268 | 56.3 | 0.36 | 20.268 | Done
130 | j270 | j277 | 63 |  | 30.1 | 0.36 | 1.06
131 | j220 | j234 | 63 |  | 41 | 0.36 | 1.06
132 | j234 | j224 | 63 |  | 118.3 | 0.36 | 1.06
133 | j234 | j224 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
134 | j122 | j73 | 63 |  | 75 | 0.36 | 1.06
135 | j278 | j345 | 63 |  | 30.1 | 0.36 | 1.06
136 | j345 | j157 | 63 |  | 65 | 0.36 | 1.06 |  | brick road | 65 | 0.36 | 23.4 | 65 | 0.36 | 23.4 | Done
137 | j345 | j194 | 63 |  | 44.2 | 0.36 | 1.06 |  | brick road | 44.2 | 0.36 | 15.912 | 44.2 | 0.36 | 15.912 | Done
138 | j304 | j283 | 63 |  | 15 | 0.36 | 1.06 |  | brick road | 15 | 0.36 | 5.4 | 15 | 0.36 | 5.4 | Done
139 | j350 | j318 | 63 |  | 34.3 | 0.36 | 1.06 |  | brick road | 34.3 | 0.36 | 12.348 | 34.3 | 0.36 | 12.348 | Done
140 | j296 | j350 | 63 |  | 30.1 | 0.36 | 1.06 |  | brick road | 30.1 | 0.36 | 10.836 | 30.1 | 0.36 | 10.836 | Done
141 | j356 | j314 | 63 |  | 30.3 | 0.36 | 1.06 |  | brick road | 30.3 | 0.36 | 10.908 | 30.3 | 0.36 | 10.908 | Done
142 | j314 | j258 | 63 |  | 15.2 | 0.36 | 1.06 |  | brick road | 15.2 | 0.36 | 5.472 | 15.2 | 0.36 | 5.472 | Done
143 | j314 | j258 | 63 |  | 45.5 | 0.36 | 1.06
144 | j202 | j129 | 63 |  | 31.1 | 0.36 | 1.06
145 | j314 | j296 | 63 |  | 41 | 0.36 | 1.06
146 | j350 | j147 | 63 |  | 31.1 | 0.36 | 1.06 |  | brick road | 31.1 | 0.36 | 11.196 | 31.1 | 0.36 | 11.196 | Done
147 | j350 | j147 | 63 |  | 18 | 0.36 | 1.06 |  | brick road | 18 | 0.36 | 6.48 | 18 | 0.36 | 6.48 | Done
148 | j109 | j255 | 63 |  | 50 | 0.36 | 1.06
149 | j255 | j59 | 63 |  | 54.3 | 0.36 | 1.06
150 | j123 | j255 | 63 |  | 51 | 0.36 | 1.06 |  | brick road | 51 | 0.36 | 18.36 | 51 | 0.36 | 18.36 | Done
151 | j255 | j357 | 63 |  | 23.5 | 0.36 | 1.06 |  |  | 23.5 | 0.36 | 8.46 | 23.5 | 0.36 | 8.46 | Done
152 | j208 | j342 | 63 |  | 65.3 | 0.36 | 1.06
153 | j235 | j266 | 63 |  | 278.3 | 0.36 | 1.06
154 | j266 | j189 | 63 |  | 51.3 | 0.36 | 1.06
155 | j266 | j234 | 63 |  | 48.1 | 0.36 | 1.06
156 | j235 | j266 | 63 |  | 7 | 0.36 | 1.06 |  | b.t crossing | 7 | 0.36 | 2.52 | 7 | 0.36 | 2.52 | Done
157 | j266 | j189 | 63 |  | 5 | 0.36 | 1.06 |  | b.t crossing | 5 | 0.36 | 1.8 | 5 | 0.36 | 1.8 | Done
158 | j326 | j264 | 63 |  | 48 | 0.36 | 1.06
159 | j326 | j287 | 63 |  | 52 | 0.36 | 1.06
160 | j287 | j286 | 63 |  | 29 | 0.36 | 1.06
161 | j286 | j282 | 63 |  | 50 | 0.36 | 1.06
162 | j182 | j159 | 63 |  | 69 | 0.36 | 1.06
163 | j159 | j173 | 63 |  | 89 | 0.36 | 1.06
164 | j167 | j158 | 63 |  | 43 | 0.36 | 1.06 |  | brickroad | 43 | 0.36 | 15.48 | 43 | 0.36 | 15.48 | Done
165 | j321 | j365 | 63 |  | 200 | 0.36 | 1.06
166 | j315 | j315a | 63 |  | 50 | 0.36 | 1.06
167 | j134 | j134a | 63 |  | 50 | 0.36 | 1.06
168 | j117 | j118 | 63 |  | 37 | 0.36 | 1.06 |  | brick road | 37 | 0.36 | 13.32 | 37 | 0.36 | 13.32 | Done
169 | j117 | j121 | 63 |  | 20 | 0.36 | 1.06
170 | j121 | j127 | 63 |  | 28 | 0.36 | 1.06
171 | j128 | j130 | 63 |  | 30 | 0.36 | 1.06
172 | j229 | j197 | 125 |  | 48 | 0.42 | 1.12
173 | j264 | j209 | 63 |  | 29 | 0.36 | 1.06
174 | j209 | j289 | 63 |  | 22 | 0.36 | 1.06
175 | j209 | j169 | 63 |  | 22 | 0.36 | 1.06
176 | j205 | j181 | 63 |  | 119 | 0.36 | 1.06
177 | j181 | j202 | 63 |  | 72 | 0.36 | 1.06
178 | j181 | j181a | 63 |  | 198 | 0.36 | 1.06
[5 empty] | 20405.9 | [9 empty] | 2162.296
|  | Representative PMPL - BRCCPL (JV) Pratapgarh |  |  |  |  | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  |  |  | Representative UP Jal Nigam (Rural) Pratapgarh
[5 empty] | 63 | 75 | 90 | 110 | 125 | 140 | 160 | 200
[5 empty] | 16781.5 | 150 | 60.3 | 311.1 | 388.7 | 579.3 | 625 | 1510 | 20405.9