## BHAIDPUR RoadDis. & Restoration
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of JMR - Road Dismantling & Restoration
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : BHAIDPUR
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 1
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | J11 | J27 | 63 | INTERLOCKING | 73.1 | 0.46 | 33.626 | 73.1 | 0.46 | 33.626 | DONE
2 | J11 | J27 | 63 | INTERLOCKING | 3.2 | 0.46 | 1.472 | 3.2 | 0.46 | 1.472 | DONE
3 | J27 | J49 | 63 | INTERLOCKING | 43.2 | 0.46 | 19.872 | 43.2 | 0.46 | 19.872 | DONE
4 | J27 | J36 | 63 | INTERLOCKING | 140.9 | 0.46 | 64.814 | 140.9 | 0.46 | 64.814 | DONE
5 | J34 | J36 | 63 | BRICK ROAD | 1.8 | 0.363 | 0.6534 | 1.8 | 0.363 | 0.6534 | DONE
6 | J36 | J47 | 63 | BRICK ROAD | 60.1 | 0.363 | 21.8163 | 60.1 | 0.363 | 21.8163 | DONE
7 | J47 | J52 | 63 | BRICK ROAD | 33.4 | 0.363 | 12.1242 | 33.4 | 0.363 | 12.1242 | DONE
8 | J52 | J63 | 63 | BRICK ROAD | 7.4 | 0.363 | 2.6862 | 7.4 | 0.363 | 2.6862 | DONE
9 | J52 | J53 | 63 | BRICK ROAD | 2.4 | 0.363 | 0.8712 | 2.4 | 0.363 | 0.8712 | DONE
10 | J47 | J42 | 63 | BRICK ROAD | 100.6 | 0.363 | 36.5178 | 100.6 | 0.363 | 36.5178 | DONE
11 | J42 | J49 | 63 | BRICK ROAD | 58.7 | 0.363 | 21.3081 | 58.7 | 0.363 | 21.3081 | DONE
12 | J69 | J75 | 63 | INTERLOCKING | 47.8 | 0.46 | 21.988 | 47.8 | 0.46 | 21.988 | DONE
13 | J75 | J80 | 63 | BRICK ROAD | 20.7 | 0.363 | 7.5141 | 20.7 | 0.363 | 7.5141 | DONE
14 | J75 | J80 | 63 | INTERLOCKING | 40.1 | 0.46 | 18.446 | 40.1 | 0.46 | 18.446 | DONE
15 | J82 | J84 | 63 | BRICK ROAD | 63.5 | 0.363 | 23.0505 | 63.5 | 0.363 | 23.0505 | DONE
16 | J69 | J71 | 63 | INTERLOCKING | 20.1 | 0.46 | 9.246 | 20.1 | 0.46 | 9.246 | DONE
17 | J71 | J72 | 63 | BRICK ROAD | 13.4 | 0.363 | 4.8642 | 13.4 | 0.363 | 4.8642 | DONE
18 | J71 | J71A | 63 | INTERLOCKING | 146.1 | 0.46 | 67.206 | 146.1 | 0.46 | 67.206 | DONE
19 | J71A | J73 | 63 | BRICK ROAD | 22.2 | 0.363 | 8.0586 | 22.2 | 0.363 | 8.0586 | DONE
20 | J73 | J70 | 63 | BRICK ROAD | 31.2 | 0.363 | 11.3256 | 31.2 | 0.363 | 11.3256 | DONE
21 | J70 | J65 | 63 | BRICK ROAD | 74.8 | 0.363 | 27.1524 | 74.8 | 0.363 | 27.1524 | DONE
22 | J129A | J129 | 75 | C.C. | 157.7 | 0.375 | 59.1375 | 157.7 | 0.375 | 59.1375 | DONE
23 | J132 | J136 | 63 | C.C. | 95.5 | 0.363 | 34.6665 | 95.5 | 0.363 | 34.6665 | DONE
24 | J136 | 142A | 63 | C.C. | 25.7 | 0.363 | 9.3291 | 25.7 | 0.363 | 9.3291 | DONE
25 | J142A | J142 | 63 | C.C. | 74.1 | 0.363 | 26.8983 | 74.1 | 0.363 | 26.8983 | DONE
26 | J142A | J142 | 63 | INTERLOCKING | 75.1 | 0.46 | 34.546 | 75.1 | 0.46 | 34.546 | DONE
27 | J146 | J142 | 63 | INTERLOCKING | 43.7 | 0.46 | 20.102 | 43.7 | 0.46 | 20.102 | DONE
28 | J149 | J151 | 63 | BRICK ROAD | 36.8 | 0.363 | 13.3584 | 36.8 | 0.363 | 13.3584 | DONE
29 | J94 | J129A | 75 | C.C. | 3.8 | 0.375 | 1.425 | 3.8 | 0.375 | 1.425 | DONE
30 | J126 | J120 | 63 | BRICK ROAD | 397.3 | 0.363 | 144.2199 | 397.3 | 0.363 | 144.2199 | DONE
31 | J120 | J121 | 63 | BRICK ROAD | 20.3 | 0.363 | 7.3689 | 20.3 | 0.363 | 7.3689 | DONE
32 | J121 | J122 | 63 | BRICK ROAD | 174.9 | 0.363 | 63.4887 | 174.9 | 0.363 | 63.4887 | DONE
33 | J109 | J100 | 63 | C.C. | 78.4 | 0.363 | 28.4592 | 78.4 | 0.363 | 28.4592 | DONE
34 | J99 | J102A | 63 | C.C. | 115.4 | 0.363 | 41.8902 | 115.4 | 0.363 | 41.8902 | DONE
35 | J102A | J102 | 63 | C.C. | 54.8 | 0.363 | 19.8924 | 54.8 | 0.363 | 19.8924 | DONE
36 | J17 | J21A | 63 | BRICK ROAD | 122.5 | 0.363 | 44.4675 | 122.5 | 0.363 | 44.4675 | DONE
37 | J21B | J22 | 63 | BRICK ROAD | 24.9 | 0.363 | 9.0387 | 24.9 | 0.363 | 9.0387 | DONE
38 | J1 | J8 | 160 | BRICK ROAD | 102.8 | 0.46 | 47.288 | 102.8 | 0.46 | 47.288 | DONE
39 | J8 | J10 | 160 | BRICK ROAD | 143.1 | 0.46 | 65.826 | 143.1 | 0.46 | 65.826 | DONE
40 | J94 | J129A | 75 | C.C. | 164.9 | 0.375 | 61.8375 | 164.9 | 0.375 | 61.8375 | DONE
41 | J92 | J99 | 90 | C.C. | 43.1 | 0.39 | 16.809 | 43.1 | 0.39 | 16.809 | DONE
Total |  |  |  |  | 2959.5 |  | 1164.6614 | 2959.5 |  | 1164.6614
|  | Representative PMPL - BRCCPL (JV) Pratapgarh |  |  |  | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  | Representative UP Jal Nigam (Rural) Pratapgarh

## BHAIDPUR RoadDis. & Restora (2
GOVERNMENT OF UTTAR PRADESH
STATE WATER & SANITATION MISSION ( SWSM )
Joint Measurement Report of JMR - Road Dismantling & Restoration
Name of the Work :- Survey , Design Preparation of DPR , Construction , Commissioning and O&M for 10 Years of Various Rural Water Supply Projects in the state of Uttar Pradesh as Per Request for Proposal for Division " Prayagraj "
Name of the Agency : POWER MECH PROJECTS LIMITED – BHOORATHNOM CONSTRUCTIONS COMPANY PRIVATE LIMITED (JV), Hyderabad.
Name OF Scheme |  | : BHAIDPUR
Block |  | : MANGRAURA
Total Scope |  | :
JMR No. |  | : 2
Date of JMR |  | :
Sr. No. | Start Node | End Node | Dia | Type OF Road | Dismantling Length | Dismantling Width | Dismantling Quantity | Restoration Length | Restoration Width | Restoration Quantity | Restoration Status | Remark
1 | J39 | J39A | 90 | BRICK ROAD | 5.3 | 0.39 | 2.067 | 5.3 | 0.39 | 2.067 | DONE
2 | J39A | J40 | 63 | BRICK ROAD | 67.2 | 0.363 | 24.3936 | 67.2 | 0.363 | 24.3936 | DONE
3 | J39A | J44 | 90 | BRICK ROAD | 3 | 0.39 | 1.17 | 3 | 0.39 | 1.17 | DONE
4 | J57 | J62 | 63 | BRICK ROAD | 3 | 0.363 | 1.089 | 3 | 0.363 | 1.089 | DONE
5 | J57 | J63 | 63 | BRICK ROAD | 19.7 | 0.363 | 7.1511 | 19.7 | 0.363 | 7.1511 | DONE
6 | J91 | J94 | 125 | B.T. ROAD | 3.8 | 0.425 | 1.615 | 3.8 | 0.425 | 1.615 | DONE
7 | J92 | J99 | 90 | B.T. ROAD | 98.2 | 0.39 | 38.298 | 98.2 | 0.39 | 38.298 | DONE
8 | J92 | J99 | 90 | B.T. ROAD | 88.1 | 0.39 | 34.359 | 88.1 | 0.39 | 34.359 | DONE
9 | J10 | J11 | 160 | B.T. ROAD | 3 | 0.46 | 1.38 | 3 | 0.46 | 1.38 | DONE
10 | J12 | J28 | 125 | B.T. ROAD | 3 | 0.425 | 1.275 | 3 | 0.425 | 1.275 | DONE
11 | J12 | J10 | 160 | B.T. ROAD | 4 | 0.46 | 1.84 | 4 | 0.46 | 1.84 | DONE
12 | J70 | J65 | 63 | B.T. ROAD | 3.5 | 0.363 | 1.2705 | 3.5 | 0.363 | 1.2705 | DONE
13 | J138 | J139 | 63 | B.T. ROAD | 6.5 | 0.363 | 2.3595 | 6.5 | 0.363 | 2.3595 | DONE
Total |  |  |  |  | 308.3 |  | 118.2677 | 308.3 |  | 118.2677 |  |  | 1282
|  | Representative PMPL - BRCCPL (JV) Pratapgarh |  |  |  | Representative Medhaj Techno Concept Pvt Ltd (TPI) Pratapgarh |  |  | Representative UP Jal Nigam (Rural) Pratapgarh