## madhura rani (ags)
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j221 | j215 | 160 | 252 | 6 | 3 | 1 | 4 | no
2 | j309 | j273 | 160 | 7 | 6 | 3 | 1 | 4 | no
3 | j309 | j273 | 160 | 495.4 | 6 | 3 | 1 | 4 | no
4 | j273 | j243 | 160 | 3 | 6 | 3 | 1 | 4 | no
5 | j273 | j243 | 160 | 121 | 6 | 3 | 1 | 4 | no
6 | j273 | j243 | 160 | 3 | 6 | 3 | 1 | 4 | no
7 | j315 | j322 | 140 | 63 | 6 | 3 | 1 | 4 | no
8 | j315 | j322 | 140 | 20.1 | 6 | 3 | 1 | 4 | no
9 | j265 | j264 | 140 | 216 | 6 | 3 | 1 | 4 | no
10 | j264 | j252 | 140 | 79 | 6 | 3 | 1 | 4 | no
11 | j264 | j252 | 140 | 10.2 | 6 | 3 | 1 | 4 | no
12 | j341 | j354 | 63 | 101 | 6 | 3 | 1 | 4 | no
13 | j344 | j341 | 63 | 7.3 | 6 | 3 | 1 | 4 | no
14 | j337 | j337a | 63 | 15.5 | 6 | 3 | 1 | 4 | no
15 | j344 | j347 | 63 | 56.2 | 6 | 3 | 1 | 4 | no
16 | j341 | j366 | 63 | 197.1 | 6 | 3 | 1 | 4 | no
17 | j341 | j366 | 63 | 19.3 | 6 | 3 | 1 | 4 | no
18 | J341 | J366 | 63 | 173.2 | 6 | 3 | 1 | 4 | no
19 | J366 | J368 | 63 | 152.7 | 6 | 3 | 1 | 4 | no
20 | J368 | J369 | 63 | 54.8 | 6 | 3 | 1 | 4 | no
21 | J368 | J362 | 63 | 150 | 6 | 3 | 1 | 4 | no
22 | J366 | J355 | 63 | 3.2 | 6 | 3 | 1 | 4 | no
23 | J366 | J355 | 63 | 127.6 | 6 | 3 | 1 | 4 | no
24 | J355 | J360 | 63 | 125.5 | 6 | 3 | 1 | 4 | no
25 | J351 | J350 | 63 | 123 | 6 | 3 | 1 | 4 | no
26 | J322 | J336 | 63 | 240 | 6 | 3 | 1 | 4 | no
27 | J324 | j333 | 63 | 111.7 | 6 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j315 | j337 | 160 | 197.1 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j309 | j315 | 160 | 320 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j309 | j315 | 160 | 9.1 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j309 | j315 | 160 | 400 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j252 | j243 | 160 | 121.4 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j243 | j231 | 160 | 144.4 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j231 | j224 | 160 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j252 | j243 | 160 | 121.4 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j243 | j231 | 160 | 144.4 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j231 | j224 | 160 | 56.1 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j224 | j221 | 160 | 3.5 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j224 | j221 | 160 | 164 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j337 | j337a | 140 | 67.7 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j337a(1) | j337a | 140 | 5.3 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j337a(1) | j344 | 140 | 17.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j344 | j341 | 140 | 24.3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j315 | j322 | 140 | 122.3 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j315 | j322 | 140 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j324 | j325 | 63 | 20.2 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j324 | j322 | 63 | 38.8 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j270 | j289 | 63 | 246 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j289 | j306 | 63 | 291.1 | 5.5 | 3.3 | 1 | 4.3 | no
23 | j306 | j301 | 63 | 245.2 | 5.5 | 3.3 | 1 | 4.3 | no
24 | j306 | j301 | 63 | 3.1 | 5.5 | 3.3 | 1 | 4.3 | no
25 | j301 | j304 | 63 | 40.2 | 5.5 | 3.3 | 1 | 4.3 | no
26 | j304 | j305 | 63 | 61.1 | 5.5 | 3.3 | 1 | 4.3 | no
27 | j304 | j302a | 63 | 115.1 | 5.5 | 3.3 | 1 | 4.3 | no
28 | j304 | j302a | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no
29 | j302a | j302b | 63 | 24.1 | 5.5 | 3.3 | 1 | 4.3 | no
30 | j302a | j302 | 63 | 15.6 | 5.5 | 3.3 | 1 | 4.3 | no
31 | j302 | j303 | 63 | 7.5 | 5.5 | 3.3 | 1 | 4.3 | no
32 | j302 | j303 | 63 | 32.1 | 5.5 | 3.3 | 1 | 4.3 | no
33 | j302 | j303 | 63 | 70.2 | 5.5 | 3.3 | 1 | 4.3 | no
34 | j302 | j299 | 63 | 8 | 5.5 | 3.3 | 1 | 4.3 | no
35 | j302 | j299 | 63 | 20 | 5.5 | 3.3 | 1 | 4.3 | no
36 | j302 | j299 | 63 | 3.2 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j265 | j270 | 110 | 65 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j299 | j300 | 63 | 75.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j299 | j297 | 63 | 40.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j297 | j298 | 63 | 36.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j298a | j298 | 63 | 14 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j298 | j298b | 63 | 22 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j297 | j295 | 63 | 93.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j295 | j293 | 63 | 104.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j293 | j288 | 63 | 55 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j293 | j288 | 63 | 11 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j293 | j290 | 63 | 10.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j290 | j286 | 63 | 15.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j286 | j285 | 63 | 88.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j295 | j294 | 63 | 171 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j265 | j266 | 63 | 340.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j266 | j267 | 63 | 61 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j267a | j267b | 63 | 12.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j266 | j268 | 63 | 29.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j265 | j264 | 63 | 216 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j264 | j262 | 63 | 219.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j262 | j263 | 63 | 35 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j262 | j256 | 63 | 50 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j256 | j255 | 63 | 3.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j256 | j255 | 63 | 6.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j255 | j260 | 63 | 118 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j255 | j249 | 63 | 64.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j249 | j253 | 63 | 17.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j249 | j253 | 63 | 15 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j249 | j244 | 63 | 13 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j244 | j250 | 63 | 116.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j244 | j231 | 63 | 58.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j244 | j231 | 63 | 25 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j244 | j231 | 63 | 94 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j252 | j250 | 63 | 81 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j250 | j244 | 63 | 51 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j250 | j251 | 63 | 49.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j250a | j250b | 63 | 57 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j224 | j225 | 63 | 53.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j225 | j226 | 63 | 146.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j225 | j227 | 63 | 3.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j225 | j227 | 63 | 56.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j221 | j222 | 63 | 67 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j216 | j220 | 63 | 321.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j171 | j170 | 63 | 65.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j171 | j172 | 63 | 78.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j171 | j173 | 63 | 21.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j173 | j177 | 63 | 48.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j173 | j174 | 63 | 5.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j173 | j174 | 63 | 3.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j173 | j174 | 63 | 22.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j174 | j175 | 63 | 55.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j174 | j177 | 63 | 125.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j169 | j146 | 63 | 474 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j182 | j183 | 63 | 158.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j166 | j160 | 63 | 68.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j160 | j161 | 63 | 39 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j160 | j138 | 63 | 474.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j160 | j159 | 63 | 180 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j145 | j152 | 63 | 213 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j140 | j157 | 63 | 116 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j113 | j114 | 63 | 78 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j273 | j274 | 63 | 160 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j274 | j277 | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j274 | j277 | 63 | 206 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j274 | j275 | 63 | 32 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | j275 | j276 | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | j275 | j276 | 63 | 81.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j275 | j278 | 63 | 134.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j278a | j278b | 63 | 18.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j301 | j269 | 63 | 308.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j301 | j269 | 63 | 36.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j301 | j269 | 63 | 111.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j296 | j245 | 63 | 248 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | j245 | j246 | 63 | 8.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | j246 | j247 | 63 | 45.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | j246 | j246a | 63 | 6.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | j246a | j246b | 63 | 29.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | j246a | j246c | 63 | 4.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | j246c | j246d | 63 | 24.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | j246 | j248 | 63 | 140.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | j236 | j243 | 63 | 58 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
10 | j236 | j211 | 63 | 573.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
11 | j236 | j233 | 63 | 469.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
12 | j233 | j234 | 63 | 107 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
13 | j233 | j230 | 63 | 116 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
14 | j230 | j223 | 63 | 176.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | j230 | j240 | 63 | 183.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | j240 | j269 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | j240 | j269 | 63 | 247.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | j306 | j313 | 63 | 3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | j306 | j313 | 63 | 170.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | j306 | j313 | 63 | 12 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | j306 | j313 | 63 | 12 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | j306 | j313 | 63 | 656 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | madhura rani ganj and saraouli | [5 empty] | Date
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation
1 | j296 | j245 | 63 | 248 | 5.5 | 3.3 | 1 | 4.3 | no
2 | j245 | j246 | 63 | 8.5 | 5.5 | 3.3 | 1 | 4.3 | no
3 | j246 | j247 | 63 | 45.1 | 5.5 | 3.3 | 1 | 4.3 | no
4 | j246 | j246a | 63 | 6.3 | 5.5 | 3.3 | 1 | 4.3 | no
5 | j246a | j246b | 63 | 29.2 | 5.5 | 3.3 | 1 | 4.3 | no
6 | j246a | j246c | 63 | 4.3 | 5.5 | 3.3 | 1 | 4.3 | no
7 | j246c | j246d | 63 | 24.7 | 5.5 | 3.3 | 1 | 4.3 | no
8 | j246 | j248 | 63 | 140.3 | 5.5 | 3.3 | 1 | 4.3 | no
9 | j236 | j243 | 63 | 58 | 5.5 | 3.3 | 1 | 4.3 | no
10 | j236 | j211 | 63 | 573.5 | 5.5 | 3.3 | 1 | 4.3 | no
11 | j236 | j233 | 63 | 469.1 | 5.5 | 3.3 | 1 | 4.3 | no
12 | j233 | j234 | 63 | 107 | 5.5 | 3.3 | 1 | 4.3 | no
13 | j233 | j230 | 63 | 116 | 5.5 | 3.3 | 1 | 4.3 | no
14 | j230 | j223 | 63 | 176.6 | 5.5 | 3.3 | 1 | 4.3 | no
15 | j230 | j240 | 63 | 183.1 | 5.5 | 3.3 | 1 | 4.3 | no
16 | j240 | j269 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
17 | j240 | j269 | 63 | 247.4 | 5.5 | 3.3 | 1 | 4.3 | no
18 | j306 | j313 | 63 | 3 | 5.5 | 3.3 | 1 | 4.3 | no
19 | j306 | j313 | 63 | 170.1 | 5.5 | 3.3 | 1 | 4.3 | no
20 | j306 | j313 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
21 | j306 | j313 | 63 | 12 | 5.5 | 3.3 | 1 | 4.3 | no
22 | j306 | j313 | 63 | 656 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## madhra rani (ags)
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j341 | j354 |  |  | 63 | 101 | 101
2 | j344 | j341 |  |  | 63 | 7.3 | 108.3
3 | j337 | j337a |  |  | 63 | 15.5 | 123.8
4 | j344 | j347 |  |  | 63 | 56.2 | 180
5 | j341 | j366 |  |  | 63 | 197.1 | 377.1
6 | j341 | j366 | B.T ROAD |  | 63 | 19.3 | 396.4
7 | J341 | J366 |  |  | 63 | 173.2 | 569.6
8 | J366 | J368 |  |  | 63 | 152.7 | 722.3
9 | J368 | J369 |  |  | 63 | 54.8 | 777.1
10 | J368 | J362 |  |  | 63 | 150 | 927.1
11 | J366 | J355 | B.T ROAD |  | 63 | 3.2 | 930.3
12 | J366 | J355 |  |  | 63 | 127.6 | 1057.9
13 | J355 | J360 |  |  | 63 | 125.5 | 1183.4
14 | J351 | J350 |  |  | 63 | 123 | 1306.4
15 | J322 | J336 |  |  | 63 | 240 | 1546.4
16 | J324 | j333 |  |  | 63 | 111.7 | 1658.1
17 | j324 | j325 |  |  | 63 | 20.2 | 1678.3
18 | j324 | j322 |  |  | 63 | 38.8 | 1717.1
19 | j270 | j289 |  |  | 63 | 246 | 1963.1
20 | j289 | j306 |  |  | 63 | 291.1 | 2254.2
21 | j306 | j301 |  |  | 63 | 245.2 | 2499.4
22 | j306 | j301 | brick road |  | 63 | 3.1 | 2502.5
23 | j301 | j304 | brick road |  | 63 | 40.2 | 2542.7
24 | j304 | j305 |  |  | 63 | 61.1 | 2603.8
25 | j304 | j302a | brick road |  | 63 | 115.1 | 2718.9
26 | j304 | j302a | brick road |  | 63 | 4 | 2722.9
27 | j302a | j302b |  |  | 63 | 24.1 | 2747
28 | j302a | j302 |  |  | 63 | 15.6 | 2762.6
29 | j302 | j303 | brick road |  | 63 | 7.5 | 2770.1
30 | j302 | j303 | brick road |  | 63 | 32.1 | 2802.2
31 | j302 | j303 |  |  | 63 | 70.2 | 2872.4
32 | j302 | j299 | brick road |  | 63 | 8 | 2880.4
33 | j302 | j299 | brick road |  | 63 | 20 | 2900.4
34 | j302 | j299 | brick road |  | 63 | 3.2 | 2903.6
35 | j299 | j300 |  |  | 63 | 75.5 | 2979.1
36 | j299 | j297 |  |  | 63 | 40.5 | 3019.6
37 | j297 | j298 |  |  | 63 | 36.1 | 3055.7
38 | j298a | j298 |  |  | 63 | 14 | 3069.7
39 | j298 | j298b |  |  | 63 | 22 | 3091.7
40 | j297 | j295 |  |  | 63 | 93.2 | 3184.9
41 | j295 | j293 |  |  | 63 | 104.5 | 3289.4
42 | j293 | j288 | brick road |  | 63 | 55 | 3344.4
43 | j293 | j288 |  |  | 63 | 11 | 3355.4
44 | j293 | j290 |  |  | 63 | 10.5 | 3365.9
45 | j290 | j286 |  |  | 63 | 15.5 | 3381.4
46 | j286 | j285 |  |  | 63 | 88.3 | 3469.7
47 | j295 | j294 |  |  | 63 | 171 | 3640.7
48 | j265 | j266 |  |  | 63 | 340.1 | 3980.8
49 | j266 | j267 |  |  | 63 | 61 | 4041.8
50 | j267a | j267b |  |  | 63 | 12.9 | 4054.7
51 | j266 | j268 |  |  | 63 | 29.2 | 4083.9
52 | j265 | j264 |  |  | 63 | 216 | 4299.9
53 | j264 | j262 |  |  | 63 | 219.1 | 4519
54 | j262 | j263 |  |  | 63 | 35 | 4554
55 | j262 | j256 |  |  | 63 | 50 | 4604
56 | j256 | j255 | B.T ROAD |  | 63 | 3.8 | 4607.8
57 | j256 | j255 | brick road |  | 63 | 6.2 | 4614
58 | j255 | j260 |  |  | 63 | 118 | 4732
59 | j255 | j249 | brick road |  | 63 | 64.1 | 4796.1
60 | j249 | j253 | brick road |  | 63 | 17.2 | 4813.3
61 | j249 | j253 |  |  | 63 | 15 | 4828.3
62 | j249 | j244 |  |  | 63 | 13 | 4841.3
63 | j244 | j250 |  |  | 63 | 116.1 | 4957.4
64 | j244 | j231 |  |  | 63 | 58.2 | 5015.6
65 | j244 | j231 | brick road |  | 63 | 25 | 5040.6
66 | j244 | j231 |  |  | 63 | 94 | 5134.6
67 | j252 | j250 |  |  | 63 | 81 | 5215.6
68 | j250 | j244 |  |  | 63 | 51 | 5266.6
69 | j250 | j251 |  |  | 63 | 49.1 | 5315.7
70 | j250a | j250b |  |  | 63 | 57 | 5372.7
71 | j224 | j225 |  |  | 63 | 53.2 | 5425.9
72 | j225 | j226 |  |  | 63 | 146.1 | 5572
73 | j225 | j227 | B.T ROAD |  | 63 | 3.4 | 5575.4
74 | j225 | j227 |  |  | 63 | 56.5 | 5631.9
75 | j221 | j222 |  |  | 63 | 67 | 5698.9
76 | j216 | j220 |  |  | 63 | 321.1 | 6020
77 | j171 | j170 |  |  | 63 | 65.9 | 6085.9
78 | j171 | j172 |  |  | 63 | 78.5 | 6164.4
79 | j171 | j173 | interlocking |  | 63 | 21.5 | 6185.9
80 | j173 | j177 |  |  | 63 | 48.5 | 6234.4
81 | j173 | j174 | interlocking |  | 63 | 5.4 | 6239.8
82 | j173 | j174 | brick road |  | 63 | 3.7 | 6243.5
83 | j173 | j174 |  |  | 63 | 22.4 | 6265.9
84 | j174 | j175 |  |  | 63 | 55.3 | 6321.2
85 | j174 | j177 |  |  | 63 | 125.6 | 6446.8
86 | j169 | j146 |  |  | 63 | 474 | 6920.8
87 | j182 | j183 |  |  | 63 | 158.5 | 7079.3
88 | j166 | j160 |  |  | 63 | 68.1 | 7147.4
89 | j160 | j161 |  |  | 63 | 39 | 7186.4
90 | j160 | j138 |  |  | 63 | 474.2 | 7660.6
91 | j160 | j159 |  |  | 63 | 180 | 7840.6
92 | j145 | j152 |  |  | 63 | 213 | 8053.6
93 | j140 | j157 |  |  | 63 | 116 | 8169.6
94 | j113 | j114 |  |  | 63 | 78 | 8247.6
95 | j273 | j274 |  |  | 63 | 160 | 8407.6
96 | j274 | j277 | B.T ROAD |  | 63 | 3 | 8410.6
97 | j274 | j277 |  |  | 63 | 206 | 8616.6
98 | j274 | j275 |  |  | 63 | 32 | 8648.6
99 | j275 | j276 | B.T ROAD |  | 63 | 3 | 8651.6
100 | j275 | j276 |  |  | 63 | 81.2 | 8732.8
101 | j275 | j278 |  |  | 63 | 134.5 | 8867.3
102 | j278a | j278b |  |  | 63 | 18.8 | 8886.1
103 | j301 | j269 |  |  | 63 | 308.5 | 9194.6
104 | j301 | j269 | interlocking |  | 63 | 36.2 | 9230.8
105 | j301 | j269 |  |  | 63 | 111.1 | 9341.9
106 | j296 | j245 |  |  | 63 | 248 | 9589.9
107 | j245 | j246 |  |  | 63 | 8.5 | 9598.4
108 | j246 | j247 |  |  | 63 | 45.1 | 9643.5
109 | j246 | j246a |  |  | 63 | 6.3 | 9649.8
110 | j246a | j246b |  |  | 63 | 29.2 | 9679
111 | j246a | j246c |  |  | 63 | 4.3 | 9683.3 |  |  |  | 12393.8
112 | j246c | j246d |  |  | 63 | 24.7 | 9708 |  |  |  | 15344.8
113 | j246 | j248 |  |  | 63 | 140.3 | 9848.3
114 | j236 | j243 |  |  | 63 | 58 | 9906.3
115 | j236 | j211 |  |  | 63 | 573.5 | 10479.8
116 | j236 | j233 |  |  | 63 | 469.1 | 10948.9
117 | j233 | j234 |  |  | 63 | 107 | 11055.9
118 | j233 | j230 |  |  | 63 | 116 | 11171.9
119 | j230 | j223 |  |  | 63 | 176.6 | 11348.5
120 | j230 | j240 |  |  | 63 | 183.1 | 11531.6
121 | j240 | j269 | interlocking |  | 63 | 3 | 11534.6
122 | j240 | j269 |  |  | 63 | 247.4 | 11782
123 | j306 | j313 | B.T ROAD |  | 63 | 3 | 11785
124 | j306 | j313 |  |  | 63 | 170.1 | 11955.1
125 | j306 | j313 | culvert |  | 63 | 12 | 11967.1
126 | j306 | j313 | B.T ROAD |  | 63 | 12 | 11979.1
127 | j306 | j313 |  |  | 63 | 656 | 12635.1
128 | j265 | j270 |  |  | 110 | 65 | 12700.1
129 | j337 | j337a |  |  | 140 | 67.7 | 12767.8
130 | j337a(1) | j337a | B.T ROAD |  | 140 | 5.3 | 12773.1
131 | j337a(1) | j344 |  |  | 140 | 17.1 | 12790.2
132 | j344 | j341 |  |  | 140 | 24.3 | 12814.5
133 | j315 | j322 |  |  | 140 | 122.3 | 12936.8
134 | j315 | j322 | B.T ROAD |  | 140 | 4 | 12940.8
135 | j315 | j322 |  |  | 140 | 63 | 13003.8
136 | j315 | j322 |  |  | 140 | 20.1 | 13023.9
137 | j265 | j264 |  |  | 140 | 216 | 13239.9
138 | j264 | j252 |  |  | 140 | 79 | 13318.9
139 | j264 | j252 | B.T ROAD |  | 140 | 10.2 | 13329.1
140 | j315 | j337 |  |  | 160 | 197.1 | 13526.2
141 | j309 | j315 |  |  | 160 | 320 | 13846.2
142 | j309 | j315 | culvert |  | 160 | 9.1 | 13855.3 |  |  |  | 316.7
143 | j309 | j315 |  |  | 160 | 400 | 14255.3
144 | j252 | j243 |  |  | 160 | 121.4 | 14376.7
145 | j243 | j231 |  |  | 160 | 144.4 | 14521.1
146 | j231 | j224 |  |  | 160 | 56.1 | 14577.2
147 | j252 | j243 |  |  | 160 | 121.4 | 14698.6
148 | j243 | j231 |  |  | 160 | 144.4 | 14843
149 | j231 | j224 |  |  | 160 | 56.1 | 14899.1
150 | j224 | j221 | B.T ROAD |  | 160 | 3.5 | 14902.6
151 | j224 | j221 |  |  | 160 | 164 | 15066.6
152 | j221 | j215 |  |  | 160 | 252 | 15318.6
153 | j309 | j273 | B.T ROAD |  | 160 | 7 | 15325.6
154 | j309 | j273 |  |  | 160 | 495.4 | 15821
155 | j273 | j243 | B.T ROAD |  | 160 | 3 | 15824
156 | j273 | j243 |  |  | 160 | 121 | 15945
157 | j273 | j243 | B.T ROAD |  | 160 | 3 | 15948
|  | 63 | 110 | 140 | 160
|  | 12635.1 | 65 | 629 | 2618.9 |  | 15948
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
[5 empty] | 178.3 | 150
316.7

## restoration
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | squarmeter
1 | j341 | j366 | B.T ROAD | 0.36 | 63 | 19.3 | 6.948
2 | J366 | J355 | B.T ROAD | 0.36 | 63 | 3.2 | 1.152
3 | j306 | j301 | brick road | 0.36 | 63 | 3.1 | 1.116
4 | j301 | j304 | brick road | 0.36 | 63 | 40.2 | 14.472
5 | j304 | j302a | brick road | 0.36 | 63 | 115.1 | 41.436
6 | j304 | j302a | brick road | 0.36 | 63 | 4 | 1.44
7 | j302 | j303 | brick road | 0.36 | 63 | 7.5 | 2.7
8 | j302 | j303 | brick road | 0.36 | 63 | 32.1 | 11.556
9 | j302 | j299 | brick road | 0.36 | 63 | 8 | 2.88
10 | j302 | j299 | brick road | 0.36 | 63 | 20 | 7.2
11 | j302 | j299 | brick road | 0.36 | 63 | 3.2 | 1.152
12 | j293 | j288 | brick road | 0.36 | 63 | 55 | 19.8
13 | j256 | j255 | B.T ROAD | 0.36 | 63 | 3.8 | 1.368
14 | j256 | j255 | brick road | 0.36 | 63 | 6.2 | 2.232
15 | j255 | j249 | brick road | 0.36 | 63 | 64.1 | 23.076
16 | j249 | j253 | brick road | 0.36 | 63 | 17.2 | 6.192
17 | j244 | j231 | brick road | 0.36 | 63 | 25 | 9
18 | j225 | j227 | B.T ROAD | 0.36 | 63 | 3.4 | 1.224
19 | j171 | j173 | interlocking | 0.36 | 63 | 21.5 | 7.74
20 | j173 | j174 | interlocking | 0.36 | 63 | 5.4 | 1.944
21 | j173 | j174 | brick road | 0.36 | 63 | 3.7 | 1.332
22 | j274 | j277 | B.T ROAD | 0.36 | 63 | 3 | 1.08
23 | j275 | j276 | B.T ROAD | 0.36 | 63 | 3 | 1.08
24 | j301 | j269 | interlocking | 0.36 | 63 | 36.2 | 13.032
25 | j240 | j269 | interlocking | 0.36 | 63 | 3 | 1.08
26 | j306 | j313 | B.T ROAD | 0.36 | 63 | 3 | 1.08
27 | j306 | j313 | B.T ROAD | 0.36 | 63 | 12 | 4.32
28 | j337a(1) | j337a | B.T ROAD | 0.44 | 140 | 5.3 | 2.332
29 | j315 | j322 | B.T ROAD | 0.44 | 140 | 4 | 1.76
30 | j264 | j252 | B.T ROAD | 0.44 | 140 | 10.2 | 4.488
31 | j224 | j221 | B.T ROAD | 0.46 | 160 | 3.5 | 1.61
32 | j309 | j273 | B.T ROAD | 0.46 | 160 | 7 | 3.22
33 | j273 | j243 | B.T ROAD | 0.46 | 160 | 3 | 1.38
34 | j273 | j243 | B.T ROAD | 0.46 | 160 | 3 | 1.38
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date