## MADHURA RANI GANJ(TANISH-2)
MADHURA RANI GANJ AND SARAOULI(JMR) BLOCK-MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 100.7 | 1.06
2 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 226.5 | 1.06
3 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 251.7 | 1.06
4 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 281.8 | 1.06
5 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 339 | 1.06
6 | j411 | j418 |  |  | 63 | 23.2 | 362.2 | 1.06
7 | j380 | j399 | culvert |  | 63 | 2 | 364.2 | 1.06
8 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 370.9 | 1.06
9 | j447a | j447b |  |  | 63 | 10.2 | 381.1 | 1.06
10 | j129 | j130 | brick road | 0.36 | 63 | 25.1 | 406.2 | 1.06
11 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 411.2 | 1.06
12 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 514.3 | 1.06
13 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 627.5 | 1.06
14 | j134 | j136 | cc | 0.36 | 63 | 54 | 681.5 | 1.06
15 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 706.3 | 1.06
16 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 791.4 | 1.06
17 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 838.5 | 1.06
18 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 916.8 | 1.06
19 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 920.8 | 1.06
20 | j25 | j38 |  |  | 63 | 15.3 | 936.1 | 1.06
21 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 969.2 | 1.06
22 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 1062.7 | 1.06
23 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 1110.3 | 1.06
24 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 1191.1 | 1.06
25 | j27 | j27a |  |  | 63 | 37.2 | 1228.3 | 1.06
26 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1231.3 | 1.06
27 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 1304.4 | 1.06
28 | j55 | j50 |  |  | 90 | 77.6 | 1382 | 1.09
29 | j63 | j74 |  |  | 90 | 101.3 | 1483.3 | 1.09
30 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 1513.5 | 1.1
31 | j2 | j3 |  |  | 110 | 195.6 | 1709.1 | 1.1
32 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 1714.1 | 1.1
33 | j441 | j459 |  |  | 110 | 140.9 | 1855 | 1.1
34 | j448 | j454 |  |  | 140 | 118.6 | 1973.6 | 1.14
35 | j425 | j437 |  |  | 140 | 91.3 | 2064.9 | 1.14
36 | j437 | j441 |  |  | 140 | 110.1 | 2175 | 1.14
37 | j451 | j447 |  |  | 140 | 44.2 | 2219.2 | 1.14
38 | j50 | j49 |  |  | 140 | 189.7 | 2408.9 | 1.14
39 | j45 | j63 |  |  | 140 | 291.1 | 2700 | 1.14
40 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 2726.2 | 1.14
41 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 2774.3 | 1.14
42 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 2980.5 | 1.14
43 | j442 | j448 |  |  | 160 | 167.5 | 3148 | 1.16
44 | j49 | j47 |  |  | 160 | 215 | 3363 | 1.16
45 | j47 | j45 |  |  | 160 | 701.1 | 4064.1 | 1.16
46 | j47 | j45 | culvert |  | 160 | 3 | 4067.1 | 1.16
47 | j45 | j34 |  |  | 160 | 206 | 4273.1 | 1.16
48 | j34 | j30 |  |  | 160 | 90 | 4363.1 | 1.16
49 | j30 | j29 |  |  | 160 | 15 | 4378.1 | 1.16
50 | j29 | j25 |  |  | 160 | 168 | 4546.1 | 1.16
51 | j25 | j24 |  |  | 160 | 54.9 | 4601 | 1.16
52 | j24 | j23 |  |  | 160 | 88.8 | 4689.8 | 1.16
53 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 4697 | 1.16
54 | j23 | j26 |  |  | 160 | 127.2 | 4824.2 | 1.16
55 | j26 | j28 |  |  | 160 | 7.7 | 4831.9 | 1.16
56 | j28 | j46 |  |  | 160 | 195.7 | 5027.6 | 1.16
57 | j46 | j72 |  |  | 160 | 234.1 | 5261.7 | 1.16
58 | j72 | j110 |  |  | 160 | 165.3 | 5427 | 1.16
59 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 5431.6 | 1.16
60 | j113 | j115 |  |  | 160 | 60 | 5491.6 | 1.16
61 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 5829.9 | 1.16
62 | j216 | j215 |  |  | 160 | 263.1 | 6093 | 1.16
63 | j167 | j182 |  |  | 160 | 152.1 | 6245.1 | 1.16
64 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 6515.8 | 1.2
65 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 6635.5 | 1.2
66 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 6858.7 | 1.2
67 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 7107.2 | 1.2
68 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 7464.4 | 1.2
69 | j216 | j170 | b.t road | 0.5 | 200 | 76.8 | 7541.2 | 1.2
70 | j170 | j169 | b.t road | 0.5 | 200 | 68.5 | 7609.7 | 1.2
71 | j169 | j167 | b.t road | 0.5 | 200 | 191.2 | 7800.9 | 1.2
72 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 7805.9 | 1.2
73 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 7831 | 1.2
74 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 7923.7 | 1.2
75 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 8043.2 | 1.2
76 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 8128.3 | 1.2
77 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 8261.8 | 1.2 |  |  | 1253.95
78 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 8474.1 | 1.2 |  |  | 140.01
79 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 8535.1 | 1.2
80 | j27 | j23 | culvert |  | 200 | 4.7 | 8539.8 | 1.2
81 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 8552.1 | 1.2
82 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 8571.3 | 1.2
83 | j493 | j491 | brick road | 0.5 | 200 | 101 | 8672.3 | 1.2
84 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 8701.6 | 1.2
85 | j489 | j485 |  |  | 200 | 45 | 8746.6 | 1.2
86 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 8793 | 1.2
87 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 8858.8 | 1.2
88 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 8934.4 | 1.2 |  | 1313.315
89 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 8991.7 | 1.2
90 | j480 | j477 |  | 0.5 | 200 | 70.6 | 9062.3 | 1.2
91 | j477 | j379 |  | 0.5 | 200 | 98.8 | 9161.1 | 1.2
92 | j379 | j376 |  | 0.5 | 200 | 45.6 | 9206.7 | 1.2
93 | j495 | j487 | b.t road | 0.46 | 160 | 87.8 | 9294.5 | 1.16
94 | j433 | j492 |  |  | 160 | 167.8 | 9462.3 | 1.16
95 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 9489.4 | 1.16
96 | j511 | j514 |  | 0.44 | 140 | 25.1 | 9514.5 | 1.14
97 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 9667.3 | 1.14
98 | j447 | j442 |  |  | 140 | 20 | 9687.3 | 1.14
99 | j447 | j442 | brick road | 0.44 | 140 | 52 | 9739.3 | 1.14
100 | j24 | j12 |  |  | 110 | 122.7 | 9862 | 1.1
101 | j12 | j1 |  |  | 110 | 105.3 | 9967.3 | 1.1
102 | j77 | j92 |  |  | 110 | 77.8 | 10045.1 | 1.1
103 | j77 | j84 |  |  | 110 | 74.8 | 10119.9 | 1.1
104 | j570 | j590 |  |  | 110 | 106.4 | 10226.3 | 1.1
105 | j84 | j86 |  |  | 90 | 79.2 | 10305.5 | 1.09
106 | j489 | j490 |  |  | 63 | 32 | 10337.5 | 1.06
107 | j447a | j447b |  |  | 63 | 31 | 10368.5 | 1.06
108 | j456 | j457 |  |  | 63 | 21.1 | 10389.6 | 1.06
109 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 10486.6 | 1.06
110 | j162 | j165 | b.t road | 0.36 | 63 | 298.7 | 10785.3 | 1.06
111 | j45 | j133 | b.t road | 0.36 | 63 | 133 | 10918.3 | 1.06
112 | j111 | j128 | b.t road | 0.36 | 63 | 238.4 | 11156.7 | 1.06
113 | j128 | j130 | b.t road | 0.36 | 63 | 11.2 | 11167.9 | 1.06
114 | j130 | j137 | b.t road | 0.36 | 63 | 44.5 | 11212.4 | 1.06
115 | j137 | j142 | b.t road | 0.36 | 63 | 45.5 | 11257.9 | 1.06
116 | j142 | j147 | b.t road | 0.36 | 63 | 22.3 | 11280.2 | 1.06
117 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 11286.4 | 1.14
118 | j381 | j382 |  |  | 140 | 29.7 | 11316.1 | 1.14
119 | j382 | j386 |  |  | 140 | 34.3 | 11350.4 | 1.14
120 | j398 | j393 | brick road | 0.44 | 140 | 50.6 | 11401 | 1.14
121 | j401 | j414 | brick road | 0.36 | 63 | 6.5 | 11407.5 | 1.06
122 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 11414.4 | 1.2
123 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 11417.9 | 1.06
124 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 11424.9 | 1.06
125 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 11431.4 | 1.06
126 | j574 | j575 | culvert | 0.36 | 63 | 6.9 | 11438.3 | 1.06
127 | j7 | j7a |  |  | 63 | 302 | 11740.3 | 1.06
|  |  | 63 | 90 | 110 | 140 | 160 | 200
|  |  | 2611.5 | 258.1 | 858.7 | 1496.2 | 3547.3 | 2968.5 | 11740.3
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date
ROAD RESTORATION
TYPE OF ROAD | 63 | 75 | 90 | 110 | 140 | 160 | 200 | AVG WIDTH | Cummilative
brick road | 132.3 | 0 | 0 | 30.2 | 176.9 | 365.4 | 195.9 | 0.416 | 374.6912
b.t road | 829.3 | 0 | 0 | 5 | 212.4 | 99.6 | 2507.9 | 0.461 | 1684.5862
interlocking | 453.5 | 0 | 0 | 0 | 152.8 | 0 | 0 | 0.36 | 218.268
cc | 715.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.466 | 333.423
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date

## hydro testing
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 1
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 2
Block :- |  | Mangraura | [7 empty] | 3
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 4
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 5
1 | j493 | j491 | 200 | 101 | 5.5 | 3.3 | 1 | 4.3 | no | 6
2 | j491 | j489 | 200 | 29.3 | 5.5 | 3.3 | 1 | 4.3 | no | 7
3 | j489 | j485 | 200 | 45 | 5.5 | 3.3 | 1 | 4.3 | no | 8
4 | j485 | j481 | 200 | 46.4 | 5.5 | 3.3 | 1 | 4.3 | no | 9
5 | j487 | j486 | 200 | 65.8 | 5.5 | 3.3 | 1 | 4.3 | no | 10
6 | j486 | j482 | 200 | 75.6 | 5.5 | 3.3 | 1 | 4.3 | no | 11
7 | j481 | j483 | 200 | 57.3 | 5.5 | 3.3 | 1 | 4.3 | no | 12
8 | j480 | j477 | 200 | 70.6 | 5.5 | 3.3 | 1 | 4.3 | no | 13
9 | j477 | j379 | 200 | 98.8 | 5.5 | 3.3 | 1 | 4.3 | no | 14
10 | j379 | j376 | 200 | 45.6 | 5.5 | 3.3 | 1 | 4.3 | no | 15
11 | j495 | j487 | 160 | 87.8 | 5.5 | 3.3 | 1 | 4.3 | no | 16
12 | j433 | j492 | 160 | 167.8 | 5.5 | 3.3 | 1 | 4.3 | no | 17
13 | j433 | j442 | 160 | 27.1 | 5.5 | 3.3 | 1 | 4.3 | no | 18
14 | j511 | j514 | 140 | 25.1 | 5.5 | 3.3 | 1 | 4.3 | no | 19
15 | j511 | j514 | 140 | 152.8 | 5.5 | 3.3 | 1 | 4.3 | no | 20
16 | j447 | j442 | 140 | 20 | 5.5 | 3.3 | 1 | 4.3 | no | 21
17 | j447 | j442 | 140 | 52 | 5.5 | 3.3 | 1 | 4.3 | no | 22
18 | j542 | j491 | 63 | 100.7 | 5.5 | 3.3 | 1 | 4.3 | no | 23
19 | j380 | j399 | 63 | 125.8 | 5.5 | 3.3 | 1 | 4.3 | no | 24
20 | j399 | j403 | 63 | 25.2 | 5.5 | 3.3 | 1 | 4.3 | no | 25
21 | j403 | j411 | 63 | 30.1 | 5.5 | 3.3 | 1 | 4.3 | no | 26
22 | j411 | j418 | 63 | 57.2 | 5.5 | 3.3 | 1 | 4.3 | no | 27
23 | j411 | j418 | 63 | 23.2 | 5.5 | 3.3 | 1 | 4.3 | no | 28
24 | j380 | j399 | 63 | 2 | 5.5 | 3.3 | 1 | 4.3 | no | 29
25 | j380 | j399 | 63 | 6.7 | 5.5 | 3.3 | 1 | 4.3 | no | 30
26 | j447a | j447b | 63 | 10.2 | 5.5 | 3.3 | 1 | 4.3 | no | 31
27 | j129 | j130 | 63 | 25.1 | 5.5 | 3.3 | 1 | 4.3 | no | 32
28 | j34 | j35 | 63 | 5 | 5.5 | 3.3 | 1 | 4.3 | no | 33
29 | j34 | j35 | 63 | 103.1 | 5.5 | 3.3 | 1 | 4.3 | no | 34
30 | j133 | j134 | 63 | 113.2 | 5.5 | 3.3 | 1 | 4.3 | no | 35
31 | j134 | j136 | 63 | 54 | 5.5 | 3.3 | 1 | 4.3 | no | 36
32 | j134 | j135 | 63 | 24.8 | 5.5 | 3.3 | 1 | 4.3 | no | 37
33 | j133 | j138 | 63 | 85.1 | 5.5 | 3.3 | 1 | 4.3 | no | 38
34 | j138 | j160 | 63 | 47.1 | 5.5 | 3.3 | 1 | 4.3 | no | 39
35 | j138 | j139 | 63 | 78.3 | 5.5 | 3.3 | 1 | 4.3 | no | 40
36 | j25 | j38 | 63 | 4 | 5.5 | 3.3 | 1 | 4.3 | no | 41
37 | j25 | j38 | 63 | 15.3 | 5.5 | 3.3 | 1 | 4.3 | no | 42
38 | j25 | j38 | 63 | 33.1 | 5.5 | 3.3 | 1 | 4.3 | no | 43
39 | j25 | j38 | 63 | 93.5 | 5.5 | 3.3 | 1 | 4.3 | no | 44
40 | j39 | j38 | 63 | 47.6 | 5.5 | 3.3 | 1 | 4.3 | no | 45
41 | j38 | j79 | 63 | 80.8 | 5.5 | 3.3 | 1 | 4.3 | no | 46
42 | j401 | j414 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
43 | j587 | j639 | 63 | 3.5 | 5.5 | 3.3 | 1 | 4.3 | no
44 | j504 | j506 | 63 | 7 | 5.5 | 3.3 | 1 | 4.3 | no
45 | j536 | j538 | 63 | 6.5 | 5.5 | 3.3 | 1 | 4.3 | no
46 | j574 | j575 | 63 | 6.9 | 5.5 | 3.3 | 1 | 4.3 | no
47 | j7 | j7a | 63 | 302 | 5.5 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  | 47
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION |  | 48
NAME |  |  |  | NAME |  |  |  | NAME |  | 49
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date |  | 50
51
52
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh | [7 empty] | 53
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh | [7 empty] | 54
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 55
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 56
Block :- |  | Mangraura | [7 empty] | 57
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 58
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 59
1 | j310 | j309 | 200 | 270.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 60
2 | j310 | j283 | 200 | 119.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 61
3 | j283 | j228 | 200 | 223.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 62
4 | j228 | j216 | 200 | 248.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 63
5 | j216 | j170 | 200 | 357.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 64
6 | j216 | j170 | 200 | 76.8 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 65
7 | j170 | j169 | 200 | 68.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 66
8 | j169 | j167 | 200 | 191.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 67
9 | j169 | j167 | 200 | 5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 68
10 | j167 | j166 | 200 | 25.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 69
11 | j166 | j159 | 200 | 92.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 70
12 | j159 | j146 | 200 | 119.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 71
13 | j159 | j141 | 200 | 85.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 72
14 | j141 | j113 | 200 | 133.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 73
15 | j113 | j27 | 200 | 212.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 74
16 | j27 | j23 | 200 | 61 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 75
17 | j27 | j23 | 200 | 4.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 76
18 | j27 | j23 | 200 | 12.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 77
19 | j502 | j493 | 200 | 19.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 78
20 | j310 | j376 | 200 | 6.9 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 79
21 | j381 | j382 | 140 | 6.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 80
22 | j381 | j382 | 140 | 29.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 81
23 | j382 | j386 | 140 | 34.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 82
24 | j398 | j393 | 140 | 50.6 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 83
25 | j489 | j490 | 63 | 32 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 84
26 | j447a | j447b | 63 | 31 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 85
27 | j456 | j457 | 63 | 21.1 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 86
28 | j74 | j75 | 63 | 97 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 87
29 | j162 | j165 | 63 | 298.7 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 88
30 | j45 | j133 | 63 | 133 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 89
31 | j111 | j128 | 63 | 238.4 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 90
32 | j128 | j130 | 63 | 11.2 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 91
33 | j130 | j137 | 63 | 44.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 92
34 | j137 | j142 | 63 | 45.5 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 93
35 | j142 | j147 | 63 | 22.3 | 5KG/CM2 | 3.5 | 1 | 4.5 | NO | 94
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  | 95
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION |  | 96
NAME |  |  |  | NAME |  |  |  | NAME |  | 97
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date |  | 98
99
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh | [7 empty] | 100
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh | [7 empty] | 101
TPI:- |  | Medhaj Techno Concept Pvt. Ltd. | [7 empty] | 102
Contractor:- |  | Power Mech Project Ltd. | [7 empty] | 103
Block :- |  | Mangraura | [7 empty] | 104
GP :- |  | madhura rani ganj | [5 empty] | Date |  | 105
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | 106
1 | j442 | j448 | 160 | 167.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 107
2 | j49 | j47 | 160 | 215 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 108
3 | j47 | j45 | 160 | 701.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 109
4 | j47 | j45 | 160 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 110
5 | j45 | j34 | 160 | 206 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 111
6 | j34 | j30 | 160 | 90 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 112
7 | j30 | j29 | 160 | 15 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 113
8 | j29 | j25 | 160 | 168 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 114
9 | j25 | j24 | 160 | 54.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 115
10 | j24 | j23 | 160 | 88.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 116
11 | j24 | j23 | 160 | 7.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 117
12 | j23 | j26 | 160 | 127.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 118
13 | j26 | j28 | 160 | 7.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 119
14 | j28 | j46 | 160 | 195.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 120
15 | j46 | j72 | 160 | 234.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 121
16 | j72 | j110 | 160 | 165.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 122
17 | j72 | j110 | 160 | 4.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 123
18 | j113 | j115 | 160 | 60 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 124
19 | j115 | j120 | 160 | 338.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 125
20 | j216 | j215 | 160 | 263.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 126
21 | j167 | j182 | 160 | 152.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | 127
22 | j448 | j454 | 140 | 118.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 110 | 140
23 | j425 | j437 | 140 | 91.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 0 | 0 | #REF!
24 | j437 | j441 | 140 | 110.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | j451 | j447 | 140 | 44.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | j50 | j49 | 140 | 189.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | j45 | j63 | 140 | 291.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
28 | j120 | j123 | 140 | 26.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
29 | j123 | j126 | 140 | 48.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
30 | j77 | j72 | 140 | 206.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | j126 | j129 | 110 | 30.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | j2 | j3 | 110 | 195.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | j2 | j3 | 110 | 5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | j441 | j459 | 110 | 140.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | j24 | j12 | 110 | 122.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | j12 | j1 | 110 | 105.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | j77 | j92 | 110 | 77.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | j77 | j84 | 110 | 74.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | j570 | j590 | 110 | 106.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | j55 | j50 | 90 | 77.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | j63 | j74 | 90 | 101.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | j84 | j86 | 90 | 79.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | j27 | j27a | 63 | 37.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | j27 | j27a | 63 | 3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | j30 | j31 | 63 | 73.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date

## road restoration
MADHURA RANI GANJ AND SARAOULI(road restoration)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(MM) | Pipe Length (M) | sqmeter | REMARK
1 | J147 | J148 | BRICK ROAD | 0.36 | 63 | 33.6 | 12.096
2 | J3 | J10 | B.T ROAD | 0.36 | 63 | 45.7 | 16.452
3 | J91 | J91A | B.T ROAD | 0.36 | 63 | 27 | 9.72
4 | J624 | J595 | B.T ROAD | 0.36 | 63 | 3.3 | 1.188
5 | J587 | J639 | B.T ROAD | 0.36 | 63 | 2.5 | 0.9
6 | J616 | J537 | BRICK ROAD | 0.36 | 63 | 5.4 | 1.944
7 | j558 | j542 | BRICK ROAD | 0.36 | 63 | 76.3 | 27.468
8 | j601 | j530 | BRICK ROAD | 0.36 | 63 | 210.7 | 75.852
9 | j514 | j619 | BRICK ROAD | 0.36 | 63 | 323 | 116.28
10 | j414 | j407 | BRICK ROAD | 0.36 | 63 | 3.9 | 1.404
11 | j478 | j479a | BRICK ROAD | 0.36 | 63 | 12.2 | 4.392
12 | j479a | j479 | BRICK ROAD | 0.36 | 63 | 6.5 | 2.34
13 | j594 | j598 | BRICK ROAD | 0.36 | 63 | 3.3 | 1.188
14 | j526 | j530 | interlocking | 0.46 | 63 | 21.7 | 9.982
15 | j530 | j600 | interlocking | 0.46 | 63 | 181 | 83.26
16 | j600 | j601 | BRICK ROAD | 0.36 | 63 | 51.2 | 18.432
17 | j600 | j602 | BRICK ROAD | 0.36 | 63 | 53.2 | 19.152
18 | j602 | j616 | BRICK ROAD | 0.36 | 63 | 21.7 | 7.812
19 | j381 | j391 | B.T ROAD | 0.36 | 63 | 5 | 1.8
20 | j428 | j438 | BRICK ROAD | 0.36 | 63 | 95.5 | 34.38
21 | j438 | j443 | BRICK ROAD | 0.36 | 63 | 50.9 | 18.324
22 | j443 | j444 | BRICK ROAD | 0.36 | 63 | 2.3 | 0.828
23 | j438 | j429 | BRICK ROAD | 0.36 | 63 | 2.7 | 0.972
24 | j427a | j427b | BRICK ROAD | 0.36 | 63 | 37.1 | 13.356
25 | j427 | j428 | BRICK ROAD | 0.36 | 63 | 32.2 | 11.592
26 | j427a | j429 | BRICK ROAD | 0.36 | 63 | 8.1 | 2.916
27 | j429 | j430 | BRICK ROAD | 0.36 | 63 | 23.7 | 8.532
28 | j424 | j426 | BRICK ROAD | 0.36 | 63 | 53.6 | 19.296
29 | j542 | j491 | brick road | 0.36 | 63 | 100.7 | 36.252
30 | j380 | j399 | interlocking | 0.46 | 63 | 125.8 | 57.868
31 | j399 | j403 | interlocking | 0.46 | 63 | 25.2 | 11.592
32 | j403 | j411 | interlocking | 0.46 | 63 | 30.1 | 13.846
33 | j411 | j418 | interlocking | 0.46 | 63 | 57.2 | 26.312
34 | j380 | j399 | b.t road | 0.36 | 63 | 6.7 | 2.412
35 | j129 | j130 | brick road | 0.36 | 63 | 25.1 | 9.036
36 | j34 | j35 | b.t road | 0.36 | 63 | 5 | 1.8
37 | j34 | j35 | cc | 0.36 | 63 | 103.1 | 37.116
38 | j133 | j134 | cc | 0.36 | 63 | 113.2 | 40.752
39 | j134 | j136 | cc | 0.36 | 63 | 54 | 19.44
40 | j134 | j135 | cc | 0.36 | 63 | 24.8 | 8.928
41 | j133 | j138 | interlocking | 0.46 | 63 | 85.1 | 39.146
42 | j138 | j160 | cc | 0.36 | 63 | 47.1 | 16.956
43 | j138 | j139 | cc | 0.36 | 63 | 78.3 | 28.188
44 | j25 | j38 | b.t road | 0.36 | 63 | 4 | 1.44
45 | j25 | j38 | interlocking | 0.46 | 63 | 33.1 | 15.226
46 | j25 | j38 | cc | 0.36 | 63 | 93.5 | 33.66
47 | j39 | j38 | cc | 0.36 | 63 | 47.6 | 17.136
48 | j38 | j79 | cc | 0.36 | 63 | 80.8 | 29.088
49 | j27 | j27a | b.t road | 0.36 | 63 | 3 | 1.08
50 | j30 | j31 | cc | 0.36 | 63 | 73.1 | 26.316
51 | j126 | j129 | brick road | 0.41 | 110 | 30.2 | 12.382
52 | j2 | j3 | b.t road | 0.41 | 110 | 5 | 2.05
53 | j120 | j123 | brick road | 0.44 | 140 | 26.2 | 11.528
54 | j123 | j126 | brick road | 0.44 | 140 | 48.1 | 21.164
55 | j77 | j72 | b.t road | 0.44 | 140 | 206.2 | 90.728
56 | j24 | j23 | b.t road | 0.46 | 160 | 7.2 | 3.312
57 | j72 | j110 | b.t road | 0.46 | 160 | 4.6 | 2.116
58 | j115 | j120 | brick road | 0.46 | 160 | 338.3 | 155.618
59 | j310 | j309 | b.t road | 0.5 | 200 | 270.7 | 135.35
60 | j310 | j283 | b.t road | 0.5 | 200 | 119.7 | 59.85
61 | j283 | j228 | b.t road | 0.5 | 200 | 223.2 | 111.6
62 | j228 | j216 | b.t road | 0.5 | 200 | 248.5 | 124.25
63 | j216 | j170 | b.t road | 0.5 | 200 | 357.2 | 178.6
64 | j216 | j170 | b.t road | 0.5 | 200 | 76.8 | 38.4
65 | j170 | j169 | b.t road | 0.5 | 200 | 68.5 | 34.25
66 | j169 | j167 | b.t road | 0.5 | 200 | 191.2 | 95.6
67 | j169 | j167 | b.t road | 0.5 | 200 | 5 | 2.5
68 | j167 | j166 | b.t road | 0.5 | 200 | 25.1 | 12.55
69 | j166 | j159 | b.t road | 0.5 | 200 | 92.7 | 46.35
70 | j159 | j146 | b.t road | 0.5 | 200 | 119.5 | 59.75
71 | j159 | j141 | b.t road | 0.5 | 200 | 85.1 | 42.55
72 | j141 | j113 | b.t road | 0.5 | 200 | 133.5 | 66.75
73 | j113 | j27 | b.t road | 0.5 | 200 | 212.3 | 106.15
74 | j27 | j23 | b.t road | 0.5 | 200 | 61 | 30.5
75 | j27 | j23 | b.t road | 0.5 | 200 | 12.3 | 6.15
76 | j502 | j493 | brick road | 0.5 | 200 | 19.2 | 9.6
77 | j493 | j491 | brick road | 0.5 | 200 | 101 | 50.5
78 | j491 | j489 | brick road | 0.5 | 200 | 29.3 | 14.65
79 | j485 | j481 | brick road | 0.5 | 200 | 46.4 | 23.2
80 | j487 | j486 | b.t road | 0.5 | 200 | 65.8 | 32.9
81 | j486 | j482 | b.t road | 0.5 | 200 | 75.6 | 37.8
82 | j481 | j483 | b.t road | 0.5 | 200 | 57.3 | 28.65
83 | j495 | j487 | b.t road | 0.46 | 160 | 87.8 | 40.388
84 | j433 | j442 | brick road | 0.46 | 160 | 27.1 | 12.466
85 | j511 | j514 | interlocking | 0.46 | 140 | 152.8 | 70.288
86 | j447 | j442 | brick road | 0.44 | 140 | 52 | 22.88
87 | j74 | j75 | interlocking | 0.46 | 63 | 97 | 44.62
88 | j162 | j165 | b.t road | 0.36 | 63 | 298.7 | 107.532
89 | j45 | j133 | b.t road | 0.36 | 63 | 133 | 47.88
90 | j111 | j128 | b.t road | 0.36 | 63 | 238.4 | 85.824
91 | j128 | j130 | b.t road | 0.36 | 63 | 11.2 | 4.032
92 | j130 | j137 | b.t road | 0.36 | 63 | 44.5 | 16.02
93 | j137 | j142 | b.t road | 0.36 | 63 | 45.5 | 16.38
94 | j142 | j147 | b.t road | 0.36 | 63 | 22.3 | 8.028
95 | j381 | j382 | b.t road | 0.44 | 140 | 6.2 | 2.728
96 | j398 | j393 | brick road | 0.44 | 140 | 50.6 | 22.264
97 | j401 | j414 | brick road | 0.36 | 63 | 6.5 | 2.34
98 | j310 | j376 | b.t road | 0.5 | 200 | 6.9 | 3.45
99 | j587 | j639 | b.t road | 0.36 | 63 | 3.5 | 1.26
100 | j504 | j506 | b.t road | 0.36 | 63 | 7 | 2.52
101 | j536 | j538 | b.t road | 0.36 | 63 | 6.5 | 2.34
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date