## Sheet1 (3)
Power Mech Projects Limited
JJM UP Water, Phase-3, Pratapgarh
Canal Crossings List from MANGRAURA BLOCK
S. No. | Block | Name Of Scheme / GP | Juntion |  | Dia | Road / Canal / Railway | Owner Department | Name of Road / Canal | Length ( M ) | Cutting / Crossing / Shoulder Laying | Remarks
|  |  | From | To
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11
1 | mangraura | attarsand and praspur | 750 | 746 | 250 | Canal | Irrigation |  | 872 | Shoulder laying
2 |  |  | 750 | 729 | 250 | Canal | Irrigation |  | 250 | Shoulder laying
3 |  |  | 729 | 752 | 250 | Canal | Irrigation |  | 329 | Shoulder laying
4 |  |  | 742 | 687 | 250 | Canal | Irrigation |  | 278 | Shoulder laying
5 |  |  | 687 | 699 | 250 | Canal | Irrigation |  | 24 | Shoulder laying
6 |  |  | 699 | 673 | 250 | Canal | Irrigation |  | 199 | Shoulder laying
Note: Map & Pipeline Index Map Attached for Reference
For PMPL - BRCCPL (JV) Authorized Signatory

## Sheet1 (2)
S. No. | Block | Name Of Scheme | Start Node | End Node | Pipe Dia | Road / Canal / Railway | Owner Department | NH, SH, MDR, ODR | Type of Road | Length ( M ) | Cutting / Crossing / Shoulder Laying | Work Status
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | mangraura | malaak | j134 | j157 | 63mm | Road | PWD | Village BT Road | BT | 108 | NOshoulder laying | Pipeline work in progress
2 | mangraura | malaak | j151 | j163 | 63mm | Road | PWD | Village BT Road | BT | 158 | NOshoulder laying | Pipeline work in progress
3 | mangraura | malaak | j163 | j228 | 63mm | Road | PWD | Village BT Road | BT | 243 | NOshoulder laying | Pipeline work in progress
4 | mangraura | malaak | j228 | j196 | 63mm | Road | PWD | Village BT Road | BT | 287 | NOshoulder laying | Pipeline work in progress
5 | mangraura | malaak | j157 | j151 | 63mm | Road | PWD | Village BT Road | BT | 16 | NOshoulder laying | Pipeline work in progress
6 | mangraura | Barasarai | J235 | J236 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 164 | Road Cutting | Pipeline work in progress
7 | mangraura | Barasarai | J238 | J235 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 35 | Road Cutting | Pipeline work in progress
8 | mangraura | Barasarai | J235 | J234 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 57 | Road Cutting | Pipeline work in progress
9 | mangraura | Barasarai | J234 | J220 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 70 | Road Cutting | Pipeline work in progress
10 | mangraura | Barasarai | J234 | J251 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 19 | Road Cutting | Pipeline work in progress
11 | mangraura | Barasarai | j184 | j185 | 63mm | Road | PWD | MDR ROAD164E | BT | 9 | shoulder laying | Pipeline work in progress
12 | mangraura | Barasarai | j185 | j182 | 63mm | Road | PWD | MDR ROAD164E | BT | 141 | shoulder laying | Pipeline work in progress
13 | mangraura | Barasarai | j182 | j180 | 63mm | Road | PWD | MDR ROAD164E | BT | 10 | shoulder laying | Pipeline work in progress
14 | mangraura | Barasarai | j180 | j171 | 63mm | Road | PWD | MDR ROAD164E | BT | 159 | shoulder laying | Pipeline work in progress
15 | mangraura | mangrauara | j132 | j83 | 63 | Road | PWD | MDR ROAD164E | CC road | 130 | CC road | Pipeline work in progress
16 | mangraura | mangrauara | j83 | j194 | 63 | Road | PWD | MDR ROAD164E | CC road | 139 | CC road | Pipeline work in progress
17 | mangraura | mangrauara | j194 | j203 | 63 | Road | PWD | MDR ROAD164E | CC road | 25 | CC road | Pipeline work in progress
18 | mangraura | mangrauara | j203 | j122 | 90 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
19 | mangraura | mangrauara | j200 | j191 | 75 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
20 | mangraura | mangrauara | J132 | J82 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
21 | mangraura | mangrauara | J43 | J47 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
22 | mangraura | mangrauara | J128 | J92 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
23 | mangraura | suryagarh jagannath | j115 | j208 | 90 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
24 | mangraura | suryagarh jagannath | j97 | j98 | 140 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
25 | mangraura | suryagarh jagannath | j65 | j182 | 75 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
26 | mangraura | suryagarh jagannath | j177 | j179 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
27 | mangraura | suryagarh jagannath | j170 | j171 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
28 | mangraura | suryagarh jagannath | j145 | j146 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
29 | mangraura | suryagarh jagannath | j147 | j149 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
30 | mangraura | suryagarh jagannath | j172 | j173 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
31 | mangraura | suryagarh jagannath | j190 | j192 | 75 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
32 | mangraura | ATTARASAND | J228 | J202 | 160 | Road | PWD | VILLAGE ROAD | BT | 44 | NOshoulder laying | Pipeline work in progress
33 | mangraura | ATTARASAND | J202 | J80 | 160 | Road | PWD | VILLAGE ROAD | BT | 101 | NOshoulder laying | Pipeline work in progress
34 | mangraura | ATTARASAND | J80 | J90 | 160 | Road | PWD | VILLAGE ROAD | BT | 48 | NOshoulder laying | Pipeline work in progress
35 | mangraura | ATTARASAND | J90 | J179 | 160 | Road | PWD | VILLAGE ROAD | BT | 35 | NOshoulder laying | Pipeline work in progress
36 | mangraura | ATTARASAND | J90 | J136 | 90 | Road | PWD | VILLAGE ROAD | BT | 169 | NOshoulder laying | Pipeline work in progress
37 | mangraura | ATTARASAND | J136 | J95 | 90 | Road | PWD | VILLAGE ROAD | BT | 76 | NOshoulder laying | Pipeline work in progress
38 | mangraura | ATTARASAND | J95 | J49 | 90 | Road | PWD | VILLAGE ROAD | BT | 286 | NOshoulder laying | Pipeline work in progress
39 | mangraura | ATTARASAND | J49 | J47 | 90 | Road | PWD | VILLAGE ROAD | BT | 98 | NOshoulder laying | Pipeline work in progress
40 | mangraura | ATTARASAND | J751 | J660 | 160 | Road | PWD | MDR ROAD164E | BT | 9 | ROAD CROSSING | Pipeline work in progress
41 | mangraura | MANDHA AND BHOJI | J41 | J56 | 110 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
42 | mangraura | MANDHA AND BHOJI | J26 | J8 | 140 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
43 | mangraura | MANDHA AND BHOJI | J47 | J48 | 63 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
44 | mangraura | MANDHA AND BHOJI | J101 | J108 | 90 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress

## Sheet1
S. No. | Block | Name Of Scheme | Start Node | End Node | Pipe Dia | Road / Canal / Railway | Owner Department | NH, SH, MDR, ODR | Type of Road | Length ( M ) | Cutting / Crossing / Shoulder Laying | Work Status
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | mangraura | malaak | j134 | j157 | 63mm | Road | PWD | Village BT Road | BT | 108 | NOshoulder laying | Pipeline work in progress
2 | mangraura | malaak | j151 | j163 | 63mm | Road | PWD | Village BT Road | BT | 158 | NOshoulder laying | Pipeline work in progress
3 | mangraura | malaak | j163 | j228 | 63mm | Road | PWD | Village BT Road | BT | 243 | NOshoulder laying | Pipeline work in progress
4 | mangraura | malaak | j228 | j196 | 63mm | Road | PWD | Village BT Road | BT | 287 | NOshoulder laying | Pipeline work in progress
5 | mangraura | malaak | j157 | j151 | 63mm | Road | PWD | Village BT Road | BT | 16 | NOshoulder laying | Pipeline work in progress
6 | mangraura | Barasarai | J235 | J236 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 164 | Road Cutting | Pipeline work in progress
7 | mangraura | Barasarai | J238 | J235 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 35 | Road Cutting | Pipeline work in progress
8 | mangraura | Barasarai | J235 | J234 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 57 | Road Cutting | Pipeline work in progress
9 | mangraura | Barasarai | J234 | J220 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 70 | Road Cutting | Pipeline work in progress
10 | mangraura | Barasarai | J234 | J251 | 63mm | CC ROAD |  | VILLAGE CC ROAD | CC ROAD | 19 | Road Cutting | Pipeline work in progress
11 | mangraura | Barasarai | j184 | j185 | 63mm | Road | PWD | MDR ROAD164E | BT | 9 | shoulder laying | Pipeline work in progress
12 | mangraura | Barasarai | j185 | j182 | 63mm | Road | PWD | MDR ROAD164E | BT | 141 | shoulder laying | Pipeline work in progress
13 | mangraura | Barasarai | j182 | j180 | 63mm | Road | PWD | MDR ROAD164E | BT | 10 | shoulder laying | Pipeline work in progress
14 | mangraura | Barasarai | j180 | j171 | 63mm | Road | PWD | MDR ROAD164E | BT | 159 | shoulder laying | Pipeline work in progress
15 | mangraura | mangrauara | j132 | j83 | 63 | Road | PWD | MDR ROAD164E | CC road | 130 | CC road | Pipeline work in progress
16 | mangraura | mangrauara | j83 | j194 | 63 | Road | PWD | MDR ROAD164E | CC road | 139 | CC road | Pipeline work in progress
17 | mangraura | mangrauara | j194 | j203 | 63 | Road | PWD | MDR ROAD164E | CC road | 25 | CC road | Pipeline work in progress
18 | mangraura | mangrauara | j203 | j122 | 90 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
19 | mangraura | mangrauara | j200 | j191 | 75 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
20 | mangraura | mangrauara | J132 | J82 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
21 | mangraura | mangrauara | J43 | J47 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
22 | mangraura | mangrauara | J128 | J92 | 63 | Road | PWD | MDR ROAD164E | BT | 9 | Road Crossing | Pipeline work in progress
23 | mangraura | suryagarh jagannath | j115 | j208 | 90 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
24 | mangraura | suryagarh jagannath | j97 | j98 | 140 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
25 | mangraura | suryagarh jagannath | j65 | j182 | 75 | Railway |  | NCR | railway | 1.67 | railway CROSSING | Pipeline work in progress
26 | mangraura | suryagarh jagannath | j177 | j179 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
27 | mangraura | suryagarh jagannath | j170 | j171 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
28 | mangraura | suryagarh jagannath | j145 | j146 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
29 | mangraura | suryagarh jagannath | j147 | j149 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
30 | mangraura | suryagarh jagannath | j172 | j173 | 63 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
31 | mangraura | suryagarh jagannath | j190 | j192 | 75 | Road | NATIONAL HIGHWAY | AYODHAYA -PRAYAGRAJ | BT | 12 | ROAD CROSSING | Pipeline work in progress
32 | mangraura | ATTARASAND | J228 | J202 | 160 | Road | PWD | VILLAGE ROAD | BT | 44 | NOshoulder laying | Pipeline work in progress
33 | mangraura | ATTARASAND | J202 | J80 | 160 | Road | PWD | VILLAGE ROAD | BT | 101 | NOshoulder laying | Pipeline work in progress
34 | mangraura | ATTARASAND | J80 | J90 | 160 | Road | PWD | VILLAGE ROAD | BT | 48 | NOshoulder laying | Pipeline work in progress
35 | mangraura | ATTARASAND | J90 | J179 | 160 | Road | PWD | VILLAGE ROAD | BT | 35 | NOshoulder laying | Pipeline work in progress
36 | mangraura | ATTARASAND | J90 | J136 | 90 | Road | PWD | VILLAGE ROAD | BT | 169 | NOshoulder laying | Pipeline work in progress
37 | mangraura | ATTARASAND | J136 | J95 | 90 | Road | PWD | VILLAGE ROAD | BT | 76 | NOshoulder laying | Pipeline work in progress
38 | mangraura | ATTARASAND | J95 | J49 | 90 | Road | PWD | VILLAGE ROAD | BT | 286 | NOshoulder laying | Pipeline work in progress
39 | mangraura | ATTARASAND | J49 | J47 | 90 | Road | PWD | VILLAGE ROAD | BT | 98 | NOshoulder laying | Pipeline work in progress
40 | mangraura | ATTARASAND | J751 | J660 | 160 | Road | PWD | MDR ROAD164E | BT | 9 | ROAD CROSSING | Pipeline work in progress
41 | mangraura | MANDHA AND BHOJI | J41 | J56 | 110 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
42 | mangraura | MANDHA AND BHOJI | J26 | J8 | 140 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
43 | mangraura | MANDHA AND BHOJI | J47 | J48 | 63 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress
44 | mangraura | MANDHA AND BHOJI | J101 | J108 | 90 | Road | PWD | NATIONAL HIGHWAY | BT | 7 | ROAD CROSSING | Pipeline work in progress