## AMUVAHI
Mangraura
AMUVAHI
SHREE KRISHNA POWER
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [5 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125MM | 140MM
1 | 2023-12-01 | J1 | J2 | [5 empty] | 150 |  |  | 150
2 | 2023-12-01 | J1 | J2 | [5 empty] | 238 |  |  | 388
3 | 2023-12-02 | J2 | J5 |  |  | 98 | [5 empty] | 486
4 | 2023-12-03 | 2 | J7 |  |  | 111 | [5 empty] | 597
5 | 2023-12-04 | J7 | J12 |  |  | 228 | [5 empty] | 825
6 | 2023-12-04 | J7 | J14 |  |  | 372 | [5 empty] | 1197
7 | 2023-12-05 | j7 | j14 |  |  | 69 | [5 empty] | 1266
8 | 2023-12-05 | j14 | j15 |  |  | 46 | [5 empty] | 1312
9 | 2023-12-05 | j16 | j17 |  |  | 187 | [5 empty] | 1499
10 | 2023-12-06 | j16 | j18 |  |  | 265 | [5 empty] | 1764
11 | 2023-12-06 | j5 | j6 |  |  | 85 | [5 empty] | 1849
12 | 2023-12-06 | j5 | j4 |  |  | 30 | [5 empty] | 1879
13 | 2023-12-06 | j5 | j21 |  |  | 165 | [5 empty] | 2044
14 | 2023-12-08 | j5 | j21 |  |  | 136 | [5 empty] | 2180
15 | 2023-12-08 | j21 | j20 |  |  | 37 | [5 empty] | 2217
16 | 2023-12-08 | j21 | j22 |  |  | 131 | [5 empty] | 2348
17 | 2023-12-09 | j22 | j23 |  |  | 33 | [5 empty] | 2381
18 | 2023-12-09 | 23 | 24 |  |  | 50 | [5 empty] | 2431
19 | 2023-12-09 | 23 | 26 |  |  | 70 | [5 empty] | 2501
20 | 2023-12-09 | 26 | 27 |  |  | 56 | [5 empty] | 2557
21 | 2023-12-09 | 26 | 40 |  |  | 63 | [5 empty] | 2620
22 | 2023-12-09 | 40 | 41 |  |  | 97 | [5 empty] | 2717
23 | 2023-12-10 | 52 | 73 |  |  | 213 | [5 empty] | 2930
24 | 2023-12-10 | 73 | 74 |  |  | 95 | [5 empty] | 3025
25 | 2023-12-11 | 40 | 52 |  |  | 35 | [5 empty] | 3060
26 | 2023-12-11 | 52 | 53 |  |  | 38 | [5 empty] | 3098
27 | 2023-12-11 | 73 | 77 |  |  | 135 | [5 empty] | 3233
28 | 2023-12-11 | 77 | 99 |  |  | 217 | [5 empty] | 3450
29 | 2023-12-11 | 99 | 103 |  |  | 265 | [5 empty] | 3715
30 | 2023-12-12 | 2 | 7 |  |  | 120 | [5 empty] | 3835
31 | 2023-12-12 | 77 | 80 |  |  | 135 | [5 empty] | 3970
32 | 2023-12-12 | 80 | 89 |  |  | 118 | [5 empty] | 4088
33 | 2023-12-13 | 99 | 104 |  |  | 219 | [5 empty] | 4307
34 | 2023-12-14 | 99 | 104 |  |  | 203 | [5 empty] | 4510
35 | 2023-12-14 | 52a | 53 |  |  | 57 | [5 empty] | 4567
36 | 2023-12-15 | 99 | 104 |  |  | 85 | [5 empty] | 4652
37 | 2023-12-15 | 104 | 103 |  |  | 216 | [5 empty] | 4868
38 | 2023-12-16 | 103 | 90 |  |  | 236 | [5 empty] | 5104
39 | 2023-12-17 | 104 | 122 |  |  | 210 | [5 empty] | 5314
40 | 2023-12-17 | 122 | 126 |  |  | 350 | [5 empty] | 5664
41 | 2023-12-18 | 105 | 116 |  |  | 76 | [5 empty] | 5740
42 | 2023-12-18 | 116 | 118 |  |  | 32 | [5 empty] | 5772
43 | 2023-12-18 | 118 | 120 |  |  | 43 | [5 empty] | 5815
44 | 2023-12-18 | 120 | 121 |  |  | 67 | [5 empty] | 5882
45 | 2023-12-18 | 122 | 123 |  |  | 71 | [5 empty] | 5953
46 | 2023-12-18 | 126 | 127 |  |  | 135 | [5 empty] | 6088
47 | 2023-12-19 | 126 | 120 |  |  | 345 | [5 empty] | 6433
48 | 2023-12-21 | 105 | 98 |  |  | 265 | [5 empty] | 6698
49 | 2023-12-21 | 98 | 91 |  |  | 145 | [5 empty] | 6843
50 | 2023-12-22 | 91 | 90 |  |  | 108 | [5 empty] | 6951
51 | 2023-12-22 | 90 | 89 |  |  | 20 | [5 empty] | 6971
52 | 2023-12-22 | 91 | 87 |  |  | 105 | [5 empty] | 7076
53 | 2023-12-22 | 87 | 84 |  |  | 53 | [5 empty] | 7129
54 | 2023-12-23 | 116 | 117 |  |  | 18 | [5 empty] | 7147
55 | 2023-12-23 | 105 | 100 |  |  | 155 | [5 empty] | 7302
56 | 2023-12-23 | 105 | 114 |  |  | 265 | [5 empty] | 7567
57 | 2023-12-23 | 114 | 113 |  |  | 142 | [5 empty] | 7709
58 | 2023-12-24 | 114 | 113 |  |  | 105 | [5 empty] | 7814
59 | 2023-12-24 | 105 | 100 |  |  | 75 | [5 empty] | 7889
60 | 2023-12-24 | 100 | 72 |  |  | 308 | [5 empty] | 8197
61 | 2023-12-25 | 114 | 113 |  |  | 235 | [5 empty] | 8432
62 | 2023-12-25 | 92 | 93 |  |  | 210 | [5 empty] | 8642
63 | 2023-12-25 | 100 | 102 |  |  | 58 | [5 empty] | 8700
64 | 2023-12-26 | 113 | 115 |  |  | 75 | [5 empty] | 8775
65 | 2023-12-26 | 113 | 112 |  |  | 76 | [5 empty] | 8851
66 | 2023-12-26 | 112 | 111 |  |  | 20 | [5 empty] | 8871
67 | 2023-12-26 | 111 | 110 |  |  | 21 | [5 empty] | 8892
68 | 2023-12-27 | 102 | 101 |  |  | 85 | [5 empty] | 8977
69 | 2023-12-27 | 101 | 92 |  |  | 95 | [5 empty] | 9072
70 | 2023-12-28 | 101 | 106 |  |  | 172 | [5 empty] | 9244
71 | 2023-12-28 | 101 | 106 |  |  | 100 | [5 empty] | 9344
72 | 2023-12-28 | 108 | 111 |  |  | 45 | [5 empty] | 9389
73 | 2023-12-30 | 108 | 109 |  |  | 52 | [5 empty] | 9441
74 | 2023-12-30 | 108 | 106 |  |  | 36 | [5 empty] | 9477
75 | 2023-12-30 | 106 | 107 |  |  | 16 | [5 empty] | 9493
76 | 2023-12-30 | 29 | 32 |  |  | 105 | [5 empty] | 9598
77 | 2023-12-30 | 87 | 88 |  |  | 76 | [5 empty] | 9674
78 | 2023-12-30 | 84 | 94 |  |  | 152 | [5 empty] | 9826
79 | 2023-12-30 | 94 | 97 |  |  | 71 | [5 empty] | 9897
80 | 2023-12-30 | 97 | 98 |  |  | 65 | [5 empty] | 9962
81 | 2023-12-31 | 95 | 97 |  |  | 112 | [5 empty] | 10074
82 | 2023-12-31 | 108 | 109 |  |  | 45 | [5 empty] | 10119
83 | 2023-12-31 | 95 | 96 |  |  | 28 | [5 empty] | 10147
84 | 2024-01-02 | 67 | 70 |  |  | 76 | [5 empty] | 10223
85 | 2024-01-02 | 30 | 32 |  |  | 104 | [5 empty] | 10327
86 | 2024-01-03 | 67 | 68 |  |  | 29 | [5 empty] | 10356
87 | 2024-01-04 | 68 | 69 |  |  | 26 | [5 empty] | 10382
88 | 2024-01-04 | 65 | 67 |  |  | 48 | [5 empty] | 10430
89 | 2024-01-04 | 65 | 66 |  |  | 21 | [5 empty] | 10451
90 | 2024-01-04 | 72 | 92 |  |  | 151 | [5 empty] | 10602
91 | 2024-01-05 | 72 | 92 |  |  | 143 | [5 empty] | 10745
92 | 2024-01-05 | 72a | 92b |  |  | 35 | [5 empty] | 10780
93 | 2024-01-06 | 64 | 61 |  |  | 41 | [5 empty] | 10821
94 | 2024-01-06 | 61 | 59 |  |  | 52 | [5 empty] | 10873
95 | 2024-01-06 | 59 | 60 |  |  | 44 | [5 empty] | 10917
96 | 2024-01-06 | 59 | 57 |  |  | 115 | [5 empty] | 11032
97 | 2024-01-06 | 57 | 58 |  |  | 110 | [5 empty] | 11142
98 | 2024-01-07 | 57 | 55 |  |  | 290 | [5 empty] | 11432
99 | 2024-01-07 | 85a | 87b |  |  | 51 | [5 empty] | 11483
100 | 2024-01-08 | 82 | 79 |  |  | 32 | [5 empty] | 11515
101 | 2024-01-08 | 83 | 82 |  |  | 48 | [5 empty] | 11563
102 | 2024-01-08 | 79 | 78 |  |  | 60 | [5 empty] | 11623
103 | 2024-01-10 | 78 | 79 |  |  | 42 | [5 empty] | 11665
104 | 2024-01-10 | 89 | 85 |  |  | 51 | [5 empty] | 11716
105 | 2024-01-10 | 55 | 56 |  |  | 218 | [5 empty] | 11934
106 | 2024-01-11 | 55 | 54 |  |  | 73 | [5 empty] | 12007
107 | 2024-01-11 | 54 | 44 |  |  | 175 | [5 empty] | 12182
[6 empty] | 11794 | 0 | 0 | 388 | 0 | 0 | 12182
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 11794 | 11794 | 8312 | 3482
1.2 | 75 mm HDPE |  | 0 | 0 |  | 0
1.3 | 90 mm HDPE |  | 0 | 0 |  | 0
1.4 | 110mm HDPE |  | 388 | 388 | 388 | 0
1.5 | 125mm HDPE
1.6 | 140mm HDPE
1.7 | 160mm HDPE
1.8 | 180mm HDPE
1.9 | 200mm HDPE
Sub Total = |  |  | 12182 | 12182 | 8700 | 3482
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-KRISHNA POWER |  | MONTH: | DECEMBER | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | AMUVAHI
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 12750 | 11794 | 8312 | 3482 |  | 4474 | [5 empty] | 0 | 1200000251 | -8312
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000332 | 0
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000333 | 0
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 700 | 388 | 388 | 0 | [7 empty] | 0 | 1200000334 | -388
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000252 | 0
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000335 | 0
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | 0
| Total Qty In ( Rmt ) = |  | 13450 | 12182 | 8700 | 3482
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 20 | 18 |  | 18 |  | 4474 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | 3 | 3 |  | 3 | [7 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
| Total Qty In ( Rmt ) = |  | 23
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
| Total Qty In ( Rmt ) = |  | 0
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 5 |  |  |  |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 5 | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | 4 | 2 |  | 2 |  | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 4 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 30 | 20 |  | 20 |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  | 0 | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## Details
POWER MECH PROJECTS.LIMITED | [10 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-KRISHNA POWER |  | MONTH: | JAN | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | AMUVAHI
Sl NO | Description | Units | Consumption Details (Node/Junction) |  |  |  | Total Consumed upto Date | Remarks | Upto date Consumption
[9 empty] | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
B | Specials :-
| Equal Tee | [11 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j7,7,5,22,23,40,26,52,73,74,77,80,89,90,91,75,87,91 |  |  |  | 18 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | j2,25,3 |  |  |  | 3 | [5 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [10 empty] | 0 | 200030300 | 0
C | Branch TEE | [13 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [10 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [10 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [10 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032228 | 0
D | 4 Way Tee | [13 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [10 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030308 | 0
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | j2,2 |  |  |  | 2 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [10 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [10 empty] | 0 | 200034192 | 0
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030276 | 0
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030274 | 0
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | j8,6,41,24,27,50,17,20,10,11,53,4,86,88,96,93,76,19,13,63 |  |  |  | 20 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030282 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO: