## persanda
Mangraura
persanda
shukla construction
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [7 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125MM | 140MM | 160 | 200
1 | 2023-11-27 | j69 | j19 |  | HDPE | 250 | [7 empty] | 250
2 | 2023-11-27 | j19 | j13 |  | HDPE | 267 | [7 empty] | 517
3 | 2023-11-28 | J69 | J72 |  | HDPE | 340 | [7 empty] | 857
4 | 2023-11-28 | J72 | J74 |  | HDPE | 60 | [7 empty] | 917
5 | 2023-11-28 | J69 | J68 |  | HDPE |  |  | 207 | [5 empty] | 1124
6 | 2023-11-30 | j70 | j71 |  | HDPE | 208 | [7 empty] | 1332
7 | 2023-11-30 | j70 | j75 |  | HDPE | 51 | [7 empty] | 1383
8 | 2023-11-30 | j75 | j77 |  | HDPE | 105 | [7 empty] | 1488
9 | [5 empty] | 52 | [7 empty] | 1540
10 | 2023-12-01 | J107 | J109 |  |  |  |  | 187 | [5 empty] | 1727
11 | 2023-12-01 | J109 | J115 |  |  | 100 | [7 empty] | 1827
12 | 2023-12-05 | j33 | j35 | [5 empty] | 152 |  |  |  |  | 1979
13 | 2023-12-07 | j33 | j35 | [5 empty] | 230 |  |  |  |  | 2209
14 | 2023-12-07 | j35 | j37 | [5 empty] | 30 |  |  |  |  | 2239
15 | 2023-12-07 | j37 | j38 |  |  |  | 78 | [6 empty] | 2317
16 | 2023-12-07 | j38 | j39 |  |  | 180 | [7 empty] | 2497
17 | 2023-12-08 | j37 | j43 |  |  |  |  | 21 | [5 empty] | 2518
18 | 2023-12-08 | j43 | j46 |  |  |  |  | 24 | [5 empty] | 2542
19 | 2023-12-08 | j46 | j51 |  |  |  |  | 19 | [5 empty] | 2561
20 | 2023-12-08 | j51 | j52 |  |  |  | 29 | [6 empty] | 2590
21 | 2023-12-08 | j52 | j56 |  |  |  | 26 | [6 empty] | 2616
22 | 2023-12-08 | j56 | j62 |  |  |  | 71 | [6 empty] | 2687
23 | 2023-12-08 | j62 | j66 |  |  | 107 | [7 empty] | 2794
24 | 2023-12-08 | j62 | j64 |  |  | 38 | [7 empty] | 2832
25 | 2023-12-08 | j64 | j65 |  |  | 27 | [7 empty] | 2859
26 | 2023-12-08 | j56 | 57 |  |  |  | 8 | [6 empty] | 2867
27 | 2023-12-08 | j57 | 58 |  |  | 53 | [7 empty] | 2920
28 | 2023-12-08 | j52 | j53 |  |  | 15 | [7 empty] | 2935
29 | 2023-12-08 | j43 | j45 |  |  | 13 | [7 empty] | 2948
30 | 2023-12-08 | j46 | j45 |  |  | 17 | [7 empty] | 2965
31 | 2023-12-09 | j45 | 44 |  |  |  |  | 50 | [5 empty] | 3015
32 | 2023-12-09 | 35 | 36 |  |  | 205 | [7 empty] | 3220
33 | 2023-12-09 | 35 | 44 |  |  | 23 | [7 empty] | 3243
34 | 2023-12-09 | 44 | 47 |  |  | 9 | [7 empty] | 3252
35 | 2023-12-09 | 47 | 48 |  |  | 18 | [7 empty] | 3270
36 | 2023-12-13 | 32 | 30 |  |  | 22 | [7 empty] | 3292
37 | 2023-12-13 | 30 | 31 |  |  | 55 | [7 empty] | 3347
38 | 2023-12-13 | 30 | 29 |  |  | 60 | [7 empty] | 3407
39 | 2023-12-13 | 29 | 23 |  |  | 80 | [7 empty] | 3487
40 | 2023-12-13 | 38 | 39 |  |  | 32 | [7 empty] | 3519
41 | 2023-12-13 | 38 | 40 |  |  | 24 | [7 empty] | 3543
42 | 2024-01-10 | 68 | 82 | [9 empty] | 614 | 4157
43 | 2024-01-10 | 82 | 84 | [9 empty] | 45 | 4202
44 | 2024-01-10 | 67 | 68 | [9 empty] | 19 | 4221
45 | 2024-01-10 | 78 | 14 | [9 empty] | 187 | 4408
46 | 2024-01-11 | 3 | 5 | [7 empty] | 61 |  |  | 4469
47 | 2024-01-11 | 5 | 9 | [7 empty] | 130 |  |  | 4599
48 | 2024-01-11 | 14 | 17 | [9 empty] | 13 | 4612
49 | 2024-01-11 | 17 | 26 | [9 empty] | 39 | 4651
50 | 2024-01-11 | 26 | 67 | [9 empty] | 185 | 4836
51 | 2024-01-11 | 84 | 85 | [8 empty] | 432 |  | 5268
52 | 2024-01-11 | 85 | 87 | [8 empty] | 84 |  | 5352
[6 empty] | 2411 | 212 | 508 | 412 | 0 | 191 | 516 | 1102 | 5352
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date
1.1 | 63 mm HDPE |  | 2411 | 2411 | 2411
1.2 | 75 mm HDPE |  | 212 | 212 | 212
1.3 | 90 mm HDPE |  | 508 | 508 | 508
1.4 | 110mm HDPE |  | 412 | 412 | 300
1.5 | 125mm HDPE |  | 0 | 0 | 0
1.6 | 140mm HDPE |  | 191 | 191 | 0
1.7 | 160mm HDPE |  | 516 | 516 | 0
1.8 | 180mm HDPE |  |  | 0 | 0
1.9 | 200mm HDPE |  | 1102 | 1102 | 0
Sub Total = |  |  | 5352 | 5352

## Puremanikanth
PUREMANIKANTH(JMR) BLOCK-MANGRAURA
S.NO. | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe(mm) | Pipe Length (M) | CUMMULATIVE | Depth(M) | REMARK
1 | J41 | J54 | BRICK ROAD | 0.36 | 63 | 23.6 | 23.6 | 1.063
2 | J41 | J54 | KC |  | 63 | 70.1 | 93.7 | 1.063
3 | J47 | J12 | KC |  | 63 | 71.3 | 165 | 1.063
4 | J47 | J12 | KC |  | 63 | 43.5 | 208.5 | 1.063
5 | J47 | J46 | KC |  | 63 | 17.5 | 226 | 1.063
6 | J46 | J68 | KC |  | 63 | 17.6 | 243.6 | 1.063
7 | J46 | J41 | KC |  | 63 | 37.1 | 280.7 | 1.063
8 | J46 | J41 | BRICK ROAD | 0.36 | 63 | 101.5 | 382.2 | 1.063
9 | J41 | J80 | BRICK ROAD | 0.36 | 63 | 92.4 | 474.6 | 1.063
10 | J53 | J86 | KC |  | 63 | 65.1 | 539.7 | 1.063
11 | J80 | J72 | BRICK ROAD | 0.36 | 63 | 6.2 | 545.9 | 1.063
12 | J80 | J72 | KC |  | 63 | 85.3 | 631.2 | 1.063
13 | J72 | J60 | B.T. ROAD | 0.36 | 63 | 3.2 | 634.4 | 1.063
14 | J72 | J64 | INTERLOCKING | 0.46 | 63 | 5.2 | 639.6 | 1.063
15 | J72 | J64 | KC |  | 63 | 3.5 | 643.1 | 1.063
16 | J72 | J64 | BRICK ROAD | 0.36 | 63 | 6.2 | 649.3 | 1.063
17 | J72 | J64 | KC |  | 63 | 38.7 | 688 | 1.063
18 | J72 | J60 | KC |  | 63 | 57.1 | 745.1 | 1.063
19 | J72 | J62 | KC |  | 63 | 53.3 | 798.4 | 1.063
20 | J62 | J45 | KC |  | 110 | 73.4 | 871.8 | 1.11
21 | J62 | J45 | KC |  | 110 | 52.1 | 923.9 | 1.11
22 | J62 | J45 | KC |  | 110 | 5.1 | 929 | 1.11
23 | J45 | J29 | B.T. ROAD | 0.36 | 63 | 100.1 | 1029.1 | 1.063
24 | J45 | J29 | KC |  | 63 | 12.1 | 1041.2 | 1.063
25 | J29 | J29A | KC |  | 63 | 25.5 | 1066.7 | 1.063
26 | J29A | J29B | KC |  | 63 | 30.5 | 1097.2 | 1.063
27 | J29A | J29C | KC |  | 63 | 39.3 | 1136.5 | 1.063
28 | J29C | J29D | INTERLOCKING | 0.46 | 63 | 5.9 | 1142.4 | 1.063
29 | J29D | J18 | INTERLOCKING | 0.46 | 63 | 14.1 | 1156.5 | 1.063
30 | J29D | J18 | KC |  | 63 | 55.9 | 1212.4 | 1.063
31 | J29D | J29E | INTERLOCKING | 0.46 | 63 | 2.8 | 1215.2 | 1.063
32 | J29D | J29E | KC |  | 63 | 57.2 | 1272.4 | 1.063
33 | J29D | J70 | INTERLOCKING | 0.46 | 63 | 115.8 | 1388.2 | 1.063
34 | J70 | J78 | BRICK ROAD | 0.36 | 63 | 42.1 | 1430.3 | 1.063
35 | J70 | J76 | INTERLOCKING | 0.46 | 63 | 220.1 | 1650.4 | 1.063
36 | J70 | J76 | KC |  | 63 | 9.3 | 1659.7 | 1.063
37 | J70 | J76 | B.T. ROAD | 0.36 | 63 | 3.8 | 1663.5 | 1.063
38 | J76 | J96 | B.T. ROAD | 0.36 | 75 | 99.1 | 1762.6 | 1.075
39 | J76 | J75 | B.T. ROAD | 0.36 | 90 | 178.5 | 1941.1 | 1.09
40 | J76 | J75 | KC |  | 90 | 8.2 | 1949.3 | 1.09
41 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 101.1 | 2050.4 | 1.09
42 | J75 | J63 | KC |  | 90 | 93.3 | 2143.7 | 1.09
43 | J75 | J63 | B.T. ROAD | 0.36 | 90 | 4 | 2147.7 | 1.09
44 | J63 | J43 | KC |  | 110 | 113.1 | 2260.8 | 1.11
45 | J96 | J106 | B.T. ROAD | 0.36 | 63 | 407.1 | 2667.9 | 1.063
46 | J106 | J87 | B.T. ROAD | 0.36 | 63 | 39.4 | 2707.3 | 1.063
47 | J87 | J106 | BRICK ROAD | 0.36 | 63 | 9.7 | 2717 | 1.063
48 | J87 | J138 | BRICK ROAD | 0.36 | 63 | 60.3 | 2777.3 | 1.063
49 | J87 | J138 | KC |  | 63 | 3.6 | 2780.9 | 1.063
50 | J138 | J101 | KC |  | 63 | 21.6 | 2802.5 | 1.063
51 | J138 | J95 | KC |  | 63 | 64.2 | 2866.7 | 1.063
52 | J95 | J111 | C.C. ROAD | 0.36 | 63 | 102 | 2968.7 | 1.063
53 | J95 | J98 | C.C. ROAD | 0.36 | 63 | 34.8 | 3003.5 | 1.063
54 | J98 | J86 | KC |  | 63 | 7.9 | 3011.4 | 1.063
55 | J98 | J86 | BRICK ROAD | 0.36 | 63 | 44.5 | 3055.9 | 1.063
56 | J98 | J87 | C.C. ROAD | 0.36 | 63 | 19.6 | 3075.5 | 1.063
57 | J98 | J87 | BRICK ROAD | 0.36 | 63 | 22.3 | 3097.8 | 1.063
58 | J106 | J97 | B.T. ROAD | 0.36 | 63 | 156.5 | 3254.3 | 1.063
59 | J106 | J97 | BRICK ROAD | 0.36 | 63 | 80.2 | 3334.5 | 1.063
60 | J106 | J97 | KC |  | 63 | 7.2 | 3341.7 | 1.063
61 | J97 | J132 | C.C. ROAD | 0.36 | 63 | 92 | 3433.7 | 1.063
62 | J97 | J132 | B.T. ROAD | 0.36 | 63 | 22.8 | 3456.5 | 1.063
63 | J132 | J143 | B.T. ROAD | 0.36 | 63 | 21.1 | 3477.6 | 1.063
64 | J132 | J143 | C.C. ROAD | 0.36 | 63 | 28.1 | 3505.7 | 1.063
65 | J74A | J74B | BRICK ROAD | 0.36 | 63 | 2.6 | 3508.3 | 1.063 | CROSSING
66 | J74A | J74B | KC |  | 63 | 24.6 | 3532.9 | 1.063
67 | J74A | J8 | BRICK ROAD | 0.36 | 125 | 35.1 | 3568 | 1.125
68 | J74A | J8 | KC |  | 125 | 4.3 | 3572.3 | 1.125
69 | J8 | J28 | KC |  | 63 | 25 | 3597.3 | 1.063
70 | J8 | J6 | KC |  | 125 | 50 | 3647.3 | 1.125
71 | J6 | J28 | KC |  | 63 | 32.6 | 3679.9 | 1.063
72 | J6 | J3A | KC |  | 125 | 20.6 | 3700.5 | 1.125
73 | J3A | J3B | KC |  | 63 | 30 | 3730.5 | 1.063
74 | J3A | J3 | KC |  | 125 | 15.8 | 3746.3 | 1.125
75 | J3 | J4 | KC |  | 63 | 47.3 | 3793.6 | 1.063
| J3 | J62 | KC |  | 110 | 45.6 | 3839.2 | 1.11
76 | J3 | J62 | KC |  | 110 | 3.3 | 3842.5 | 1.11 | CROSSING
77 | J28 | J25 | BRICK ROAD | 0.36 | 63 | 66.3 | 3908.8 | 1.063
78 | J25 | J13 | B.T. ROAD | 0.36 | 63 | 83.8 | 3992.6 | 1.063
79 | J25 | J22 | B.T. ROAD | 0.36 | 63 | 12.3 | 4004.9 | 1.063
80 | J22 | J34 | B.T. ROAD | 0.36 | 63 | 103.9 | 4108.8 | 1.063
81 | J22 | J17 | B.T. ROAD | 0.36 | 63 | 33.5 | 4142.3 | 1.063
82 | J17 | J17A | BRICK ROAD | 0.36 | 63 | 22.3 | 4164.6 | 1.063
83 | J17A | J17B | KC |  | 63 | 24.3 | 4188.9 | 1.063
84 | J17A | J116 | KC |  | 63 | 27.1 | 4216 | 1.063
85 | J17A | J116 | BRICK ROAD | 0.36 | 63 | 7.5 | 4223.5 | 1.063
86 | J17 | J57 | B.T. ROAD | 0.36 | 63 | 55.6 | 4279.1 | 1.063
87 | J57 | J15 | KC |  | 63 | 56.3 | 4335.4 | 1.063
88 | J15 | J9 | KC |  | 63 | 54.1 | 4389.5 | 1.063
89 | J9 | J63 | KC |  | 63 | 169 | 4558.5 | 1.063
90 | J9 | J63 | BRICK ROAD | 0.36 | 63 | 26.1 | 4584.6 | 1.063
91 | J18 | J35 | KC |  | 63 | 122.3 | 4706.9 | 1.063
92 | J96 | J115 | B.T. ROAD | 0.36 | 75 | 135.7 | 4842.6 | 1.075
93 | J115 | J104 | INTERLOCKING | 0.46 | 63 | 158.3 | 5000.9 | 1.063
94 | J115 | J122 | B.T. ROAD | 0.36 | 63 | 96.6 | 5097.5 | 1.063
95 | J122 | J125 | B.T. ROAD | 0.36 | 63 | 4.8 | 5102.3 | 1.063 | CROSSING
96 | J122 | J125 | BRICK ROAD | 0.36 | 63 | 180.1 | 5282.4 | 1.063
97 | J122 | J132 | B.T. ROAD | 0.36 | 63 | 56.1 | 5338.5 | 1.063
98 | J63 | J79 | KC |  | 90 | 390.1 | 5728.6 | 1.09
99 | J63 | J79 | INTERLOCKING | 0.46 | 90 | 4.6 | 5733.2 | 1.09
100 | J79 | J148 | KC |  | 90 | 120.1 | 5853.3 | 1.09
101 | J79 | J148 | KC |  | 90 | 9.3 | 5862.6 | 1.09
102 | J79 | J148 |  |  | 90 | 10.5 | 5873.1 | 1.09 | CULVERT
103 | J79 | J148 | B.T. ROAD | 0.36 | 90 | 5.8 | 5878.9 | 1.09 | CROSSING
104 | J148 | J114 | KC |  | 63 | 124.7 | 6003.6 | 1.063
105 | J114 | J118 | KC |  | 63 | 56.6 | 6060.2 | 1.063
106 | J141 | J140 | KC |  | 63 | 13.1 | 6073.3 | 1.063
107 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 10.1 | 6083.4 | 1.063
108 | J141 | J140 | KC |  | 63 | 23.1 | 6106.5 | 1.063
109 | J141 | J140 | BRICK ROAD | 0.36 | 63 | 17.6 | 6124.1 | 1.063
110 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 4.1 | 6128.2 | 1.063
111 | J140 | J136 | KC |  | 63 | 17.9 | 6146.1 | 1.063
112 | J140 | J136 | BRICK ROAD | 0.36 | 63 | 2.7 | 6148.8 | 1.063 | CROSSING
113 | J140 | J134 | BRICK ROAD | 0.36 | 63 | 20.8 | 6169.6 | 1.063
114 | J134 | J135 | KC |  | 63 | 32.1 | 6201.7 | 1.063
115 | J134 | J135 | BRICK ROAD | 0.36 | 63 | 2.8 | 6204.5 | 1.063 | CROSSING
116 | J134 | J128 | INTERLOCKING | 0.46 | 63 | 213.1 | 6417.6 | 1.063 | PR
117 | J75 | J69 | KC |  | 63 | 150 | 6567.6 | 1.063
118 | J128 | J128A | KC |  | 63 | 7.1 | 6574.7 | 1.063
119 | J128 | J114 | BRICK ROAD | 0.36 | 63 | 5.6 | 6580.3 | 1.063
120 | J128 | J114 | KC |  | 63 | 422.1 | 7002.4 | 1.063
121 | J148 | J153 | KC |  | 63 | 429.7 | 7432.1 | 1.063
122 | J79 | J79A | INTERLOCKING | 0.46 | 63 | 59.2 | 7491.3 | 1.063
123 | J79A | J79B | INTERLOCKING | 0.46 | 63 | 2.8 | 7494.1 | 1.063 | CROSSING
124 | J79A | J79B | KC |  | 63 | 14.1 | 7508.2 | 1.063
125 | J79B | J79C | KC |  | 63 | 11.2 | 7519.4 | 1.063
126 | J79B | J79D | KC |  | 63 | 28.5 | 7547.9 | 1.063
127 | J79A | J49 | INTERLOCKING | 0.46 | 63 | 134.4 | 7682.3 | 1.063
128 | J49 | J23 | BRICK ROAD | 0.36 | 63 | 53.1 | 7735.4 | 1.063
129 | J49 | J24 | BRICK ROAD | 0.36 | 63 | 46.1 | 7781.5 | 1.063
130 | J49 | J24 | KC |  | 63 | 31.2 | 7812.7 | 1.063
131 | J24A | J24B | KC |  | 63 | 24.8 | 7837.5 | 1.063
132 | J49 | J30 | INTERLOCKING | 0.46 | 63 | 16.1 | 7853.6 | 1.063
133 | J30 | J55 | BRICK ROAD | 0.36 | 63 | 40 | 7893.6 | 1.063
134 | J55 | J40 | KC |  | 63 | 69 | 7962.6 | 1.063
135 | J55 | J61 | KC |  | 63 | 29.8 | 7992.4 | 1.063
136 | J30 | J42 | INTERLOCKING | 0.46 | 63 | 25.6 | 8018 | 1.063
137 | J42 | J61 | BRICK ROAD | 0.36 | 63 | 41.4 | 8059.4 | 1.063
138 | J42 | J39 | INTERLOCKING | 0.46 | 63 | 43.3 | 8102.7 | 1.063
139 | J39 | J19 | KC |  | 63 | 35.5 | 8138.2 | 1.063
140 | J39 | J50 | INTERLOCKING | 0.46 | 63 | 19.1 | 8157.3 | 1.063
141 | J39 | J50 | KC |  | 63 | 4.1 | 8161.4 | 1.063
142 | J50 | J36 | KC |  | 63 | 3.8 | 8165.2 | 1.063
143 | J50 | J36 | INTERLOCKING | 0.46 | 75 | 31.9 | 8197.1 | 1.075
144 | J36 | J73 | INTERLOCKING | 0.46 | 90 | 10.1 | 8207.2 | 1.09
145 | J36 | J73 | BRICK ROAD | 0.36 | 90 | 8.4 | 8215.6 | 1.09
146 | J68 | J46 | KC |  | 63 | 121.5 | 8337.1 | 1.063
147 | J36 | J73 | KC |  | 90 | 18 | 8355.1 | 1.09
148 | J36 | J73 | KC | 0.36 | 90 | 24.9 | 8380 | 1.09
149 | J36 | J73 | KC |  | 90 | 15.3 | 8395.3 | 1.09
150 | J36 | J73 | KC | 0.36 | 90 | 7.1 | 8402.4 | 1.09
151 | J73 | J56A | B.T. ROAD | 0.36 | 140 | 3.3 | 8405.7 | 1.14 | CROSSING
152 | J73 | J56A | KC |  | 140 | 73.8 | 8479.5 | 1.14
153 | J56A | J56B | KC |  | 63 | 24.1 | 8503.6 | 1.063
154 | J56A | J56C | KC |  | 140 | 5.5 | 8509.1 | 1.14
155 | J56C | J56D | KC |  | 63 | 7.6 | 8516.7 | 1.063
156 | J56C | J56D | BRICK ROAD | 0.36 | 63 | 20.1 | 8536.8 | 1.063
157 | J56D | J56 | BRICK ROAD | 0.36 | 125 | 24.2 | 8561 | 1.125
158 | J56 | J56C | KC |  | 140 | 19.8 | 8580.8 | 1.14
159 | J56 | J5 | BRICK ROAD | 0.36 | 140 | 38.1 | 8618.9 | 1.14
160 | J5 | J10 | BRICK ROAD | 0.36 | 63 | 18 | 8636.9 | 1.063
161 | J5 | J10 | KC |  | 63 | 13.1 | 8650 | 1.063
162 | J5 | J5A | BRICK ROAD | 0.36 | 140 | 24.6 | 8674.6 | 1.14
163 | J5A | J5B | BRICK ROAD | 0.36 | 63 | 2.1 | 8676.7 | 1.063 | CROSSING
164 | J5A | J5B | KC |  | 63 | 13.2 | 8689.9 | 1.063
165 | J5A | J2 | BRICK ROAD | 0.36 | 140 | 10 | 8699.9 | 1.14
166 | J5A | J2 | KC |  | 140 | 25.3 | 8725.2 | 1.14
167 | J2 | J1 | KC |  | 63 | 12 | 8737.2 | 1.063
168 | J2 | J2A | KC |  | 140 | 19.5 | 8756.7 | 1.14
169 | J2 | J2A | KC |  | 140 | 7.5 | 8764.2 | 1.14
170 | J56D | J74 | BRICK ROAD | 0.36 | 125 | 13.8 | 8778 | 1.125
171 | J74 | J82 | BRICK ROAD | 0.36 | 63 | 1.5 | 8779.5 | 1.063
172 | J74 | J82 | KC |  | 63 | 60.1 | 8839.6 | 1.063
173 | J74 | J74A | BRICK ROAD | 0.36 | 125 | 9.8 | 8849.4 | 1.125
174 | J52 | J41 | KC |  | 63 | 141.3 | 8990.7 | 1.063
175 | J58 | J18 | KC |  | 63 | 102.3 | 9093 | 1.063
176 | J58 | J54 | B.T. ROAD | 0.36 | 63 | 151.2 | 9244.2 | 1.063
177 | J75 | J15 | KC |  | 63 | 68.1 | 9312.3 | 1.063
178 | J73 | J57 | B.T. ROAD | 0.36 | 63 | 52 | 9364.3 | 1.063
| 7394.7 | 266.7 | 1009.3 | 292.6 | 173.6 | 227.4 | 9364.3
| 9797 | 267 | 1010 | 293 | 174 | 228 | 11769 |  |  | 55.9
| 63 | 75 | 90 | 110 | 125 | 140
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  | 55
DESIGNATION |  |  |  | DESIGNATION |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  | SIGN.with date