## hathsara
Mangraura
hathsara
MAHADEV reddy
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [5 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125MM | 140MM
1 | 2023-12-22 | 102 | 76 |  |  | 225 | [5 empty] | 225
2 | 2023-12-23 | j76 | j227 |  |  | 525 | [5 empty] | 750
3 | 2023-12-24 | j76 | j227 |  |  | 182 | [5 empty] | 932
4 | 2023-12-24 | 227 | 234 |  |  | 316 | [5 empty] | 1248
5 | 2023-12-25 | 242 | 236 |  |  | 58 | [5 empty] | 1306
6 | 2023-12-25 | 236 | 234 |  |  | 52 | [5 empty] | 1358
7 | 2023-12-25 | 250 | 251 |  |  | 404 | [5 empty] | 1762
8 | 2023-12-26 | 250 | 249 |  |  | 218 | [5 empty] | 1980
9 | 2023-12-27 | 236 | 242 |  |  | 58 | [5 empty] | 2038
10 | 2023-12-27 | 242 | 241 |  |  | 121 | [5 empty] | 2159
11 | 2023-12-27 | 242 | 247 |  |  | 81 | [5 empty] | 2240
12 | 2023-12-27 | 247 | 249 |  |  | 40 | [5 empty] | 2280
13 | 2023-12-28 | 160 | 161 |  |  | 106 | [5 empty] | 2386
14 | 2023-12-28 | 161 | 159 |  |  | 67 | [5 empty] | 2453
15 | 2023-12-28 | 162 | 158 |  |  | 65 | [5 empty] | 2518
16 | 2023-12-28 | 162 | 164 |  |  | 193 | [5 empty] | 2711
17 | 2023-12-29 | 160 | 149 |  |  | 176 | [5 empty] | 2887
18 | 2023-12-29 | 149 | 135 |  |  | 48 | [5 empty] | 2935
19 | 2023-12-29 | 135 | 126 |  |  | 106 | [5 empty] | 3041
20 | 2023-12-29 | 126 | 110 |  |  | 110 | [5 empty] | 3151
21 | 2023-12-30 | 126 | 110 |  |  | 115 | [5 empty] | 3266
22 | 2023-12-30 | 10 | 102 |  |  | 55 | [5 empty] | 3321
23 | 2023-12-31 | 110 | 102 |  |  | 106 | [5 empty] | 3427
24 | 2024-01-01 | 4 | 76 |  |  |  | 355 |  |  |  |  | 3782
25 | 2024-01-01 | 8 | 34 | [5 empty] | 90 |  |  | 3872
26 | 2024-01-02 | 4 | 30 |  |  | 181 | [5 empty] | 4053
27 | 2024-01-02 | 15 | 16 |  |  | 58 | [5 empty] | 4111
28 | 2024-01-02 | 16 | 30 |  |  | 86 | [5 empty] | 4197
29 | 2024-01-02 | 16 | 13 |  |  | 100 | [5 empty] | 4297
30 | 2024-01-04 | 1 | 2 | [6 empty] | 120 |  | 4417
31 | 2024-01-04 | 3 | 1 | [5 empty] | 160 |  |  | 4577
32 | 2024-01-04 | 3 | 4 |  |  |  |  | 120 |  |  |  | 4697
33 | 2024-01-05 | 2 | 5 |  |  |  |  | 280 |  |  |  | 4977
34 | 2024-01-05 | 8 | 28 |  |  | 100 | [5 empty] | 5077
35 | 2024-01-07 | 8 | 28 |  |  | 43 | [5 empty] | 5120
36 | 2024-01-07 | 28 | 20 |  |  | 100 | [5 empty] | 5220
37 | 2024-01-08 | 28 | 28a |  |  | 50 | [5 empty] | 5270
38 | 2024-01-08 | 28 | 20 |  |  | 145 | [5 empty] | 5415
39 | 2024-01-08 | 20 | 21 |  |  | 96 | [5 empty] | 5511
40 | 2024-01-08 | 21 | 22 |  |  | 16 | [5 empty] | 5527
41 | 2024-01-08 | 21 | 19 |  |  | 35 | [5 empty] | 5562
42 | 2024-01-08 | 22 | 27 |  |  |  | 34 |  |  |  |  | 5596
43 | 2024-01-08 | 27 | 30 |  |  |  | 38 |  |  |  |  | 5634
44 | 2024-01-09 | 3 | 11 |  |  | 150 | [5 empty] | 5784
45 | 2024-01-09 | 11 | 13 |  |  | 30 | [5 empty] | 5814
46 | 2024-01-09 | 11 | 14 |  |  | 50 | [5 empty] | 5864
47 | 2024-01-09 | 17 | 14 |  |  | 16 | [5 empty] | 5880
48 | 2024-01-09 | 17 | 18 |  |  | 44 | [5 empty] | 5924
49 | 2024-01-09 | 17 | 19 |  |  | 15 | [5 empty] | 5939
50 | 2024-01-10 | 30 | 103 |  |  | 130 | [5 empty] | 6069
51 | 2024-01-11 | 136 | 166 |  |  | 200 | [5 empty] | 6269
52 | 2024-01-13 | 166 | 169 |  |  | 570 | [5 empty] | 6839
53 | 2024-01-14 | 166 | 169 |  |  | 250 | [5 empty] | 7089
54 | 2024-01-14 | 169 | 168 |  |  | 90 | [5 empty] | 7179
55 | 2024-01-14 | 168 | 100 |  |  | 200 | [5 empty] | 7379
56 | 2024-01-14 | 168 | 174 |  |  | 60 | [5 empty] | 7439
57 | 2024-01-17 | 103 | 112 |  |  | 40 | [5 empty] | 7479
58 | 2024-01-17 | 112 | 136 |  |  | 265 | [5 empty] | 7744
59 | 2024-01-17 | 136 | 134 |  |  | 12 | [5 empty] | 7756
60 | 2024-01-17 | 136 | 137 |  |  | 22 | [5 empty] | 7778
61 | 2024-01-18 | 103 | 115 |  |  | 265 | [5 empty] | 8043
62 | 2024-01-18 | 103 | 56 |  |  | 100 | [5 empty] | 8143
63 | 2024-01-19 | 56 | 100 |  |  | 290 | [5 empty] | 8433
64 | 2024-01-19 | 103 | 56 |  |  | 210 | [5 empty] | 8643
65 | 2024-01-20 | 156 | 100 |  |  | 125 | [5 empty] | 8768
66 | 2024-01-20 | 115 | 128 |  |  | 100 | [5 empty] | 8868
67 | 2024-01-20 | 115 | 109 |  |  | 90 | [5 empty] | 8958
68 | 2024-01-20 | 109 | 101 |  |  | 30 | [5 empty] | 8988
69 | 2024-01-20 | 109 | 110 |  |  | 80 | [5 empty] | 9068
70 | 2024-01-21 | 168 | 174 |  |  | 180 | [5 empty] | 9248
71 | 2024-01-21 | 168 | 168a |  |  | 40 | [5 empty] | 9288
72 | 2024-01-21 | 174 | 177 |  |  | 70 | [5 empty] | 9358
73 | 2024-01-21 | 177 | 181 |  |  | 70 | [5 empty] | 9428
74 | 2024-01-21 | 174 | 171 |  |  | 10 | [5 empty] | 9438
75 | 2024-01-22 | 174 | 171 |  |  | 57 | [5 empty] | 9495
76 | 2024-01-22 | 171 | 170 |  |  | 110 | [5 empty] | 9605
77 | 2024-01-22 | 170 | 125 |  |  | 10 | [5 empty] | 9615
78 | 2024-01-23 | 176 | 125 |  |  | 30 | [5 empty] | 9645
79 | 2024-01-23 | 181 | 184 |  |  | 150 | [5 empty] | 9795
80 | 2024-01-24 | 181 | 184 |  |  | 100 | [5 empty] | 9895
81 | 2024-01-24 | 125 | 120 |  |  |  |  | 100 |  |  |  | 9995
82 | 2024-01-24 | 114 | 125 | [5 empty] | 70 |  |  | 10065
83 | 2024-01-24 | 125 | 120 | [5 empty] | 80 |  |  | 10145
[6 empty] | 8698 | 427 | 500 | 400 | 120 | 0 | 10145
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 8698 | 8698 | - | 8698
1.2 | 75 mm HDPE |  | 427 | 427 | - | 427
1.3 | 90 mm HDPE |  | 500 | 500 | - | 500
1.4 | 110mm HDPE |  | 400 | 400 | - | 400
1.5 | 125mm HDPE |  | 120 | 120 | - | 120
1.6 | 140mm HDPE
1.7 | 160mm HDPE
1.8 | 180mm HDPE
1.9 | 200mm HDPE
Sub Total = |  |  | 10145 | 10145 |  | 10145
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-madhav reddy |  | MONTH: | JAN | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | HASTHARA
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty | Gp1 | Gp2 | Total
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 12455 | 8698 | - | 8698 |  | 4474 | [5 empty] | 0 | 1200000251 | #VALUE!
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt | 450 | 427 | - | 427 | [7 empty] | 0 | 1200000332 | #VALUE!
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt | 500 | 500 | - | 500 | [7 empty] | 0 | 1200000333 | #VALUE!
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt | 1050 | 400 | - | 400 | [7 empty] | 0 | 1200000334 | #VALUE!
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 125 | 120 | - | 120 | [7 empty] | 0 | 1200000252 | #VALUE!
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | [11 empty] | 0 | 1200000335 | 0
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | 0
| Total Qty In ( Rmt ) = |  | 14580 | 10145 |  | 10145
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 25 | 23 |  | 23 |  | 4474 | [5 empty] | 0 | 200030286 | 0 | 10 | 5 | 15
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0 |  |  | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 10 | 1 |  | 1 | [7 empty] | 0 | 200030288 | 0 |  |  | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | 9 | 1 |  | 1 | [7 empty] | 0 | 200030289 | 0 |  |  | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | 1 |  |  |  |  | 4474 | [5 empty] | 0 | 200032212 | 0 |  |  | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0 |  |  | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030293 | 0 |  |  | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0 |  |  | 0
| Total Qty In ( Rmt ) = |  | 45
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
| Total Qty In ( Rmt ) = |  | 0
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | 4 |  |  |  |  | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | 2 | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | 4 |  |  |  |  | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | 2 | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | 4 | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | 2 |  |  |  |  | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 40 | 24 |  | 24 |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  | 0 | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## Details
POWER MECH PROJECTS.LIMITED | [10 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-MADHAV REDDY |  | MONTH: | JAN | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | HASTHARA
Sl NO | Description | Units | Consumption Details (Node/Junction) |  |  |  | Total Consumed upto Date | Remarks | Upto date Consumption
[9 empty] | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
B | Specials :-
| Equal Tee | [11 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j227,102,242,236,250,251,247,160,159,158,164,135,126,110,10,4,16,3,2,166,135,137,112, |  |  |  | 23 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j176 |  |  |  | 1 | [5 empty] | 0 | 200030288 | #REF!
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | j3 |  |  |  | 1 | [5 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [10 empty] | 0 | 200030300 | 0
C | Branch TEE | [13 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [10 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [10 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [10 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032228 | 0
D | 4 Way Tee | [13 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [10 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030308 | 0
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [10 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [10 empty] | 0 | 200034192 | 0
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030276 | 0
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030274 | 0
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | j85,88,80,82,78,74,73,68,64,47,45,52,256,260,226,263,262,232,179,12,7,24,26,33 |  |  |  | 24 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030282 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO: