## MADURANI GANJ
Mangraura
MANDHURANIGANJ
ags pvt limited
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125MM | 140MM | 160
1 | 2023-12-04 | J294 | J306 |  |  | 285 | [6 empty] | 285
2 | 2023-12-05 | j293 | j290 |  |  | 32 | [6 empty] | 317
3 | 2023-12-05 | j290 | j286 |  |  | 36 | [6 empty] | 353
4 | 2023-12-05 | j286 | j287 |  |  | 29 | [6 empty] | 382
5 | 2023-12-06 | j294 | j295 |  |  | 108 | [6 empty] | 490
6 | 2023-12-06 | j295 | j293 |  |  | 144 | [6 empty] | 634
7 | 2023-12-06 | j293 | j287 |  |  | 32 | [6 empty] | 666
8 | 2023-12-06 | j287 | j296 |  |  | 29 | [6 empty] | 695
9 | 2023-12-07 | j302 | j303 |  |  | 113 | [6 empty] | 808
10 | 2023-12-08 | j297 | 298 |  |  | 50 | [6 empty] | 858
11 | 2023-12-08 | j299 | 300 |  |  | 33 | [6 empty] | 891
12 | 2023-12-09 | j255 | j259 |  |  | 23 | [6 empty] | 914
13 | 2023-12-09 | 259 | j260 |  |  | 50 | [6 empty] | 964
14 | 2023-12-10 | j255 | 259 |  |  | 34 | [6 empty] | 998
15 | 2023-12-10 | 266 | 268 |  |  | 22 | [6 empty] | 1020
16 | 2023-12-10 | 266 | 267 |  |  | 34 | [6 empty] | 1054
17 | 2023-12-10 | 289 | 285 |  |  | 50 | [6 empty] | 1104
18 | 2023-12-10 | 285 | 270 |  |  | 60 | [6 empty] | 1164
19 | 2023-12-10 | 299 | 297 |  |  | 38 | [6 empty] | 1202
20 | 2023-12-10 | 297 | 295 |  |  | 72 | [6 empty] | 1274
21 | 2023-12-11 | 255 | 249 |  |  | 66 | [6 empty] | 1340
22 | 2023-12-11 | 249 | 253 |  |  | 30 | [6 empty] | 1370
23 | 2023-12-11 | 249 | 244 |  |  | 11 | [6 empty] | 1381
24 | 2023-12-11 | 244 | 232 |  |  | 40 | [6 empty] | 1421
25 | 2023-12-11 | 240 | 250 |  |  | 96 | [6 empty] | 1517
26 | 2023-12-12 | 255 | 249 |  |  | 66 | [6 empty] | 1583
27 | 2023-12-12 | 249 | 253 |  |  | 30 | [6 empty] | 1613
28 | 2023-12-12 | 249 | 244 |  |  | 11 | [6 empty] | 1624
29 | 2023-12-12 | 244 | 232 |  |  | 40 | [6 empty] | 1664
30 | 2023-12-13 | 236 | 239 |  |  | 206 | [6 empty] | 1870
31 | 2023-12-13 | 245 | 246 |  |  | 13 | [6 empty] | 1883
32 | 2023-12-13 | 246 | 248 |  |  | 126 | [6 empty] | 2009
33 | 2023-12-13 | 246 | 247 |  |  | 22 | [6 empty] | 2031
34 | 2023-12-14 | 344 | 347 |  |  | 48 | [6 empty] | 2079
35 | 2023-12-14 | 341 | 354 |  |  | 72 | [6 empty] | 2151
36 | 2023-12-14 | 355 | 350 |  |  | 74 | [6 empty] | 2225
37 | 2023-12-14 | 350 | 346 |  |  | 41 | [6 empty] | 2266
38 | 2023-12-15 | 324 | 325 |  |  | 16 | [6 empty] | 2282
39 | 2023-12-15 | 324 | 333 |  |  | 141 | [6 empty] | 2423
40 | 2023-12-16 | 170 | 171 |  |  | 86 | [6 empty] | 2509
41 | 2023-12-16 | 171 | 172 |  |  | 33 | [6 empty] | 2542
42 | 2023-12-16 | 171 | 173 |  |  | 27 | [6 empty] | 2569
43 | 2023-12-16 | 173 | 174 |  |  | 21 | [6 empty] | 2590
44 | 2023-12-16 | 174 | 175 |  |  | 15 | [6 empty] | 2605
45 | 2023-12-16 | 173 | 177 |  |  | 74 | [6 empty] | 2679
46 | 2023-12-16 | 176 | 177 |  |  | 24 | [6 empty] | 2703
47 | 2023-12-17 | 174 | 177 |  |  | 60 | [6 empty] | 2763
48 | 2023-12-18 | 265 | 266 |  |  | 150 | [6 empty] | 2913
49 | 2023-12-19 | 265 | 266 |  |  | 155 | [6 empty] | 3068
50 | 2023-12-20 | 264 | 261 |  |  | 64 | [6 empty] | 3132
51 | 2023-12-20 | 261 | 262 |  |  | 141 | [6 empty] | 3273
52 | 2023-12-20 | 262 | 256 |  |  | 46 | [6 empty] | 3319
53 | 2023-12-20 | 216 | 217 |  |  | 157 | [6 empty] | 3476
54 | 2023-12-20 | 217 | 219 |  |  | 50 | [6 empty] | 3526
55 | 2023-12-21 | 217 | 219 |  |  | 88 | [6 empty] | 3614
56 | 2023-12-21 | 219 | 220 |  |  | 40 | [6 empty] | 3654
57 | 2023-12-22 | 273 | 274 |  |  | 148 | [6 empty] | 3802
58 | 2023-12-22 | 274 | 277 |  |  | 187 | [6 empty] | 3989
59 | 2023-12-22 | 274 | 275 |  |  | 38 | [6 empty] | 4027
60 | 2023-12-22 | 275 | 278 |  |  | 158 | [6 empty] | 4185
61 | 2023-12-23 | 281 | 291 |  |  | 140 | [6 empty] | 4325
62 | 2023-12-23 | 291 | 296 |  |  | 68 | [6 empty] | 4393
63 | 2023-12-23 | 296 | 301 |  |  | 65 | [6 empty] | 4458
64 | 2023-12-23 | 301 | 306 |  |  | 234 | [6 empty] | 4692
65 | 2023-12-24 | 306 | 307 |  |  | 100 | [6 empty] | 4792
66 | 2023-12-24 | 308 | 311 |  |  | 607 | [6 empty] | 5399
67 | 2023-12-26 | 311 | 314 |  |  | 97 | [6 empty] | 5496
68 | 2023-12-26 | 302 | 304 |  |  | 68 | [6 empty] | 5564
69 | 2023-12-27 | 362 | 368 |  |  | 138 | [6 empty] | 5702
70 | 2023-12-27 | 368 | 367 |  |  | 60 | [6 empty] | 5762
71 | 2023-12-28 | 367 | 366 |  |  | 82 | [6 empty] | 5844
72 | 2023-12-28 | 366 | 356 |  |  | 119 | [6 empty] | 5963
73 | 2023-12-28 | 355 | 360 |  |  | 121 | [6 empty] | 6084
74 | 2024-01-06 | 269 | 245 |  |  | 206 | [6 empty] | 6290
75 | 2024-01-06 | 245 | 236 |  |  | 226 | [6 empty] | 6516
76 | 2024-01-06 | 245 | 236 |  |  | 58 | [6 empty] | 6574
77 | 2024-01-06 | 236 | 211 |  |  | 176 | [6 empty] | 6750
78 | 2024-01-08 | 166 | 160 |  |  | 66 | [6 empty] | 6816
79 | 2024-01-08 | 160 | 161 |  |  | 31 | [6 empty] | 6847
80 | 2024-01-08 | 160 | 138 |  |  | 434 | [6 empty] | 7281
81 | 2024-01-09 | 159 | 160 |  |  | 142 | [6 empty] | 7423
82 | 2024-01-10 | 182 | 183 |  |  | 140 | [6 empty] | 7563
83 | 2024-01-10 | 146 | 169 |  |  | 454 | [6 empty] | 8017
84 | 2024-01-11 | 236 | 311 |  |  | 100 | [6 empty] | 8117
85 | 2024-01-11 | 236 | 239 |  |  | 85 | [6 empty] | 8202
86 | 2024-01-12 | 233 | 239 |  |  | 225 | [6 empty] | 8427
87 | 2024-01-12 | 233 | 234 |  |  | 90 | [6 empty] | 8517
88 | 2024-01-12 | 233 | 230 |  |  | 107 | [6 empty] | 8624
89 | 2024-01-12 | 230 | 240 |  |  | 150 | [6 empty] | 8774
90 | 2024-01-12 | 236 | 211 |  |  | 98 | [6 empty] | 8872
91 | 2024-01-13 | 223 | 230 |  |  | 67 | [6 empty] | 8939
92 | 2024-01-13 | 239 | 240 |  |  | 15 | [6 empty] | 8954
93 | 2024-01-13 | 113 | 114 |  |  | 75 | [6 empty] | 9029
94 | 2024-01-15 | 368 | 369 |  |  | 46 | [6 empty] | 9075
95 | 2024-01-15 | 366 | 361 |  |  | 105 | [6 empty] | 9180
96 | 2024-01-16 | 304 | 304a |  |  | 52 | [6 empty] | 9232
97 | 2024-01-19 | 302 | 229 |  |  | 28 | [6 empty] | 9260
98 | 2024-01-19 | 299 | 300 |  |  | 20 | [6 empty] | 9280
99 | 2024-01-19 | 297 | 298 |  |  | 15 | [6 empty] | 9295
100 | 2024-01-19 | 298a | 297 |  |  | 12 | [6 empty] | 9307
101 | 2024-01-21 | 273 | 309 | [8 empty] | 482 | 9789
102 | 2024-01-22 | 243 | 273 | [8 empty] | 119 | 9908
103 | 2024-01-22 | 266 | 267 |  |  | 15 | [6 empty] | 9923
104 | 2024-01-22 | 266 | 266A |  |  | 10 | [6 empty] | 9933
105 | 2024-01-23 | 243 | 252 | [8 empty] | 109 | 10042
106 | 2024-01-23 | 252 | 264 | [7 empty] | 77 |  | 10119
107 | 2024-01-23 | 264 | 265 | [7 empty] | 217 |  | 10336
[6 empty] | 9332 | 0 | 0 | 0 | 0 | 294 | 710 | 10336
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed )
1.1 | 63 mm HDPE |  | 9332 | 9332 | 5267 | 4065
1.2 | 75 mm HDPE |  | 0 | 0 | -
1.3 | 90 mm HDPE |  | 0 | 0 | -
1.4 | 110mm HDPE |  | 0 | 0 | -
1.5 | 125mm HDPE |  | 0 | 0 | -
1.6 | 140mm HDPE |  | 294 | 294 | 0 | 294
1.7 | 160mm HDPE |  | 710 | 710 | 0 | 710
1.8 | 180mm HDPE |  |  | 0 | -
1.9 | 200mm HDPE |  |  | 0 | -
Sub Total = |  |  | 10336 | 10336 |  | 5069
Sub-Contractor Site Engineer (Sr.Eng/ DY.M-SMX ) (Dy.M-PMX ) AGM Project Incharge
#REF!
#REF!

## Recon Sheet
POWER MECH PROJECTS.LIMITED | [11 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-AGS CONSTRUCTION |  | MONTH: | JAN | Block: | mangraura
| ABC Limited |  | BILL NO: |  | GP: | MADHURA RANI GANJ
Sl NO | Description | Units |  |  |  |  | Balance Qty | SAP Entry | Remarks | Upto date Consumption
|  |  | Total Issued Qty | Cumulative Consumption | Upto Pre Consumed Qty | This Bill Consumed Qty |  |  |  | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
A | HDPE Pipe :- | [8 empty] | BLOCK | BLOCK | BLOCK | BLOCK
1 | HDPE PIPE-63MM,PN-6,CLASS:PE-100,IS:4984 | Rmt | 9757 | 9332 | 5267 | 4065 |  | 4474 | [5 empty] | 0 | 1200000251 | -5267 | ḍḍ
2 | HDPE PIPE-75MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000332 | 0
3 | HDPE PIPE-90MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000333 | 0
4 | HDPE PIPE-110MM,PN-6,CLASS:PE-100 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000334 | 0
5 | HDPE PIPE-125MM,PN-6,CLASS:PE-100,IS4984 | Rmt |  |  |  | 0 | [7 empty] | 0 | 1200000252 | 0
6 | HDPE PIPE-140MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 720 | 294 | 0 | 294 | [7 empty] | 0 | 1200000253 | 0
7 | HDPE PIPE-160MM,PN-6,CLASS:PE-100 | Rmt | 2280 | 710 | 0 | 710 | [7 empty] | 0 | 1200000335 | 0
8 | HDPE PIPE-200MM,PN-6,CLASS:PE-100,IS4984 | Rmt | 600 |  |  | 0 | [7 empty] | 0 | 1200000255 | 0
9 | DI PIPE-Ø200MM , K7,IS:8329 | Rmt | [11 empty] | 0 | 900007097 | 0
10 | HDPE PIPE-250MM,PN-6,CLASS:PE-100,IS4984 | Rmt | [11 empty] | 0 | 1200000256 | 0
| Total Qty In ( Rmt ) = |  | 13357 | 10336 |  | 5069
B | Specials :-
| Equal Tee | [12 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | 40 | 18 |  | 18 |  | 4474 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | 2 | 1 |  | 1 | [7 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [11 empty] | 0 | 200030300 | 0
| Total Qty In ( Rmt ) = |  | 42
C | Branch TEE | [14 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | 2 | 2 |  | 2 | [7 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [11 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | 10 | 2 |  | 2 | [7 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [11 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [11 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [11 empty] | 0 | 200032228 | 0
| Total Qty In ( Rmt ) = |  | 12
D | 4 Way Tee | [14 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [11 empty] | 0 | 200030308 | 0
Total Qty In ( No's ) =
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [11 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [11 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [11 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | 3 | 1 |  | 1 | [7 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [11 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [11 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [11 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200034192 | 0
Total Qty In ( No's ) =
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [11 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030276 | 0
Total Qty In ( No's ) =
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [11 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030274 | 0
Total Qty In ( No's ) =
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | 2 |  |  |  |  | 4474 | [5 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [5 empty] | 4474 | [5 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [11 empty] | 0 | 200030282 | 0
Total Qty In ( No's ) =
1 | FHTC
1 | GI PIPE-15MM | Rmt | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000409 | 0
2 | MDPE PIPE-20MM | Rmt | [7 empty] | 0 | 0 |  |  | 0 | 1200000408 | 0
3 | BRASS TAP | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000231 | 0
4 | PP CLAMP SADLLE-63MM | Nos | [7 empty] | 0 |  |  |  | 0 | 1200000410 | 0
5 | PP CLAMP SADDLE-75MM | Nos | [11 empty] | 0 | 1200000425 | 0
6 | PP CLAMP SADLLE-90MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000411 | 0
7 | PP CLAMP SADDLE-140MM | Nos | [11 empty] | 0 | 900008156 | 0
8 | PP CLAMP SADDLE-160MM | Nos | [11 empty] | 0 | 900008157 | 0
9 | PP CLAMP SADDLE-200MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 900008159 | 0
10 | PP CLAMP SADDLE 125MM WITH M8 FASTNERS | Nos | [11 empty] | 0 | 900008617 | 0
11 | PP CLAMP SADLLE-110MM | Nos | [11 empty] | 0 | 900007416 | 0
12 | G.I ELBOW 15 MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000419 | 0
13 | GI SOCKET-15MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000416 | 0
14 | WALL MOUNT SADDLE GI PIPE-15MM | Nos | [5 empty] | 4474 | [5 empty] | 0 | 1200000418 | 0
15 | 15MM GI NIPPLE - 0.3MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000450 | 0
16 | 15MM GI NIPPLE - 0.5MTR LENGTH | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000451 | 0
17 | 20MM MDPE COMPRESSION ELBOW | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000448 | 0
18 | SS FLOW CONTROL VAlVE | Nos | [5 empty] | 4474 |  | 0 | 0 |  |  | 0 | 1200000417 | 0
19 | MDPE FEMLE THREADED ASSEMBLY-20MM | Nos | [7 empty] | 0 | 0 |  |  | 0 | 1200000414 | 0
20 | MDPE ELBOW-20MM | Nos | [11 empty] | 0 | 1200000415 | 0
21 | TEFLAN TAPE | Nos |  |  |  | 0 | 0 | [6 empty] | 0 | 200001364 | 0
22 | [6 empty] | 0 | [6 empty] | 0 | #N/A | 0
Total Qty In ( No's ) =
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO:

## Details
POWER MECH PROJECTS.LIMITED | [10 empty] | FHTC
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
| Contractor Name-AGS CONSTRUCTION |  | MONTH: | JAN | Block: | MANGRAURA
| ABC Limited |  | BILL NO: |  | GP: | MADHURA RANI GANJ
Sl NO | Description | Units | Consumption Details (Node/Junction) |  |  |  | Total Consumed upto Date | Remarks | Upto date Consumption
[9 empty] | GP | GP | GP | GP | Total Consumption upto This Bill |  | Entry Qty
B | Specials :-
| Equal Tee | [11 empty] | 0 |  | 0
1 | HDPE-63X63X63MM,PN-6,R-TEE,CLASS:PE-100 | Nos | j294,295,289,285,286,290,293,287,297,299,302,304,301,291,266,255,352 |  |  |  | 18 | [5 empty] | 0 | 200030286 | 0
2 | HDPE-75X75X75MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030287 | 0
3 | HDPE-90X90X90MM,PN-6,R-TEE,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030288 | 0
4 | HDPE-110X110X110MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030289 | 0
5 | HDPE 125mm X 125mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032212 | 0
6 | HDPE-140X140X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030291 | 0
7 | HDPE-160X160X160MM,PN-6,R-TEE,CL:PE-100 | Nos | j243 |  |  |  | 1 | [5 empty] | 0 | 200030293 | 0
8 | HDPE 200X200X200 MM, PN-6, R-TEE, CLASS: | Nos | [10 empty] | 0 | 200030300 | 0
C | Branch TEE | [13 empty] | 0
1 | HDPE BRANCH TEE 63MM X 63MM X 50MM | Nos | [10 empty] | 0 | 200032593 | 0
2 | HDPE 75MM X 75MM X 50MM PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032575 | 0
3 | HDPE 75mm X 75mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032202 | 0
4 | HDPE 90mm X 90mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032233 | 0
5 | HDPE 90mm X 90mm X 63mm, PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032203 | 0
6 | HDPE 90mm X 90mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032204 | 0
7 | HDPE 110mm X 110mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032234 | 0
8 | HDPE 110mm X 110mm X 63mm PN6 TEE PE100 | Nos | j270,344 |  |  |  | 2 | [5 empty] | 0 | 200032205 | 0
9 | HDPE 110mm X 110mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032206 | 0
10 | HDPE 110mm X 110mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032207 | 0
11 | HDPE 125mm X 125mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032235 | 0
12 | HDPE 125mm X 125mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032208 | 0
13 | HDPE 125mm X 125mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032209 | 0
14 | HDPE 125mm X 125mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032210 | 0
15 | HDPE 125mm X 125mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032211 | 0
16 | HDPE Branch TEE 140mm X 140mm X 50mm | Nos | [10 empty] | 0 | 200032236 | 0
17 | HDPE 140mm X 140mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032213 | 0
18 | HDPE 140mm X 140mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032214 | 0
19 | HDPE 140mm X 140mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032215 | 0
20 | HDPE Branch TEE 140mm X 140mm X 125mm | Nos | [10 empty] | 0 | 200032216 | 0
21 | HDPE-140X90X140MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030290 | 0
22 | HDPE 160mm X 160mm X 50mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032237 | 0
23 | HDPE 160mm X 160mm X 63mm PN6 TEE PE100 | Nos | j273,231 |  |  |  | 2 | [5 empty] | 0 | 200032217 | 0
24 | HDPE 160mm X 160mm X 75mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032218 | 0
25 | HDPE 160mm X 160mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032219 | 0
26 | HDPE-160X110X160MM,PN-6,R-TEE,CL:PE-100 | Nos | [10 empty] | 0 | 200030292 | 0
27 | HDPE 160mm X 160mm X 125mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032220 | 0
28 | HDPE 200mm X 200mm X 63mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032222 | 0
29 | HDPE 200X75X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030297 | 0
30 | HDPE 200X90X200 MM, PN-6, R-TEE, CLASS:P | Nos | [10 empty] | 0 | 200030298 | 0
31 | HDPE 200mm X 200mm X 110mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032223 | 0
32 | HDPE 200mm X 200mm X 160mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032225 | 0
33 | HDPE 250mm X 250mm X 90mm PN6 TEE PE100 | Nos | [10 empty] | 0 | 200032228 | 0
D | 4 Way Tee | [13 empty] | 0
1 | HDPE 63MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030301 | 0
2 | HDPE 75MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030302 | 0
3 | HDPE 90MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030303 | 0
4 | HDPE 110MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030304 | 0
5 | HDPE125MM,PN6,4WAY CROSS FITTING,CLPE100 | Nos | [10 empty] | 0 | 200032584 | 0
6 | HDPE 140MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030305 | 0
7 | HDPE 160MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030306 | 0
8 | HDPE200MM ,PN6 ,CROSS TEE ,CLASS:PE100 | Nos | [10 empty] | 0 | 200030308 | 0
E | Reducers
1 | HDPE-75MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030309 | 0
2 | HDPE-90MM,PN6, 63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030311 | 0
3 | HDPE-90MM,PN6, 75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030310 | 0
4 | HDPE-110MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030314 | 0
5 | HDPE-110MM,PN6,75MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030312 | 0
6 | HDPE-110MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030313 | 0
7 | HDPE-125MM,PN6, 63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032241 | 0
8 | HDPE-125MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032239 | 0
9 | HDPE-125MM,PN6, 90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032240 | 0
10 | HDPE-125MM,PN6, 110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032242 | 0
11 | HDPE-140MM,PN6,63MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030320 | 0
12 | HDPE-140MM,PN6, 75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032243 | 0
13 | HDPE-140MM,PN6,90MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030317 | 0
14 | HDPE-140MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030315 | 0
15 | HDPE-140MM,PN6,125MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030316 | 0
16 | HDPE-160MM,PN6,63MM Reducer PE100 | Nos | [10 empty] | 0 | 200032247 | 0
17 | HDPE-160MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032246 | 0
18 | HDPE-160MM,PN6,90MM Reducer PE100 | Nos | [10 empty] | 0 | 200032245 | 0
19 | HDPE-160MM,PN6,110MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030319 | 0
20 | HDPE-160MM,PN6, 125MM Reducer PE100 | Nos | [10 empty] | 0 | 200032244 | 0
21 | HDPE-160MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | j252 |  |  |  | 1 | [5 empty] | 0 | 200030318 | 0
22 | HDPE-200MM,PN6,75MM Reducer PE100 | Nos | [10 empty] | 0 | 200032249 | 0
23 | HDPE-200MM,PN6,90MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030326 | 0
24 | HDPE-200MM,PN6,110MM Reducer PE100 | Nos | [10 empty] | 0 | 200032248 | 0
25 | HDPE-200MM,PN6,140MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030325 | 0
26 | HDPE-200MM,PN6,160MM,ENLARGER,CL:PE100 | Nos | [10 empty] | 0 | 200030328 | 0
27 | HDPE-200MM,PN6,63MM,ENLARGER,CLASS:PE100 | Nos | [10 empty] | 0 | 200030327 | 0
28 | HDPE Reducer 200mm X 125mm | Nos | [10 empty] | 0 | 200034192 | 0
F | Bends 45 Degree
1 | HDPE BEND-63MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032193 | 0
2 | HDPE BEND-90MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032195 | 0
3 | HDPE BEND-110MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032196 | 0
4 | HDPE BEND-75MM,PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032194 | 0
5 | HDPE BEND-125MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030270 | 0
6 | HDPE BEND-125MM, PN6 45DEG PE100 | Nos | [10 empty] | 0 | 200032197 | 0
7 | HDPE BEND-140MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030275 | 0
8 | HDPE BEND-160MM,PN-6,45DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030276 | 0
G | Bends 90Degree
1 | HDPE BEND-63MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030266 | 0
2 | HDPE BEND-75MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030267 | 0
3 | HDPE BEND-90MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030268 | 0
4 | HDPE BEND-110MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030269 | 0
5 | HDPE BEND-140MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030271 | 0
6 | HDPE BEND-160MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030272 | 0
7 | HDPE BEND-200MM,PN-6,90DEG,CLASS:PE-100 | Nos | [10 empty] | 0 | 200030274 | 0
H | End Caps
1 | HDPE-63MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030277 | 0
2 | HDPE-75MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030278 | 0
3 | HDPE-90MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030279 | 0
4 | HDPE-110MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030280 | 0
5 | HDPE-140MM,PN6,END CAP,CLASS:PE100 | Nos | [10 empty] | 0 | 200030282 | 0
Sub Contractor Site Engineer Block incharge AGM DM PMX Project Incharge
ENTRY NO: