## SARSIDIH
Mangraura
sarsidih
16189
khayathi enterprises
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) |  |  |  |  | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 90mm | 110mm | 125 | 140mm
1 | 2023-06-05 | J8 | J9 | k.c | hdpe | 200 |  |  |  |  | 200
2 | 2023-06-05 | J8 | J9 | k.c | hdpe | 100 |  |  |  |  | 300
3 | 2023-06-06 | J8 | J25 | k.c | hdpe | 200 |  |  |  |  | 500
4 | 2023-06-06 | j8 | j4 | k.c | hdpe | 120 |  |  |  |  | 620
5 | 2023-06-06 | j4 | j5 | k.c | hdpe | 80 |  |  |  |  | 700
6 | 2023-06-07 | j4 | j5 | k.c | hdpe | 34 |  |  |  |  | 734
7 | 2023-06-07 | j4 | j1 | k.c | hdpe | 126 |  |  |  |  | 860
8 | 2023-06-08 | j4 | j1 | k.c | hdpe | 53 |  |  |  |  | 913
9 | 2023-06-09 | j25 | j29 | k.c | hdpe | 63 |  |  |  |  | 976
10 | 2023-06-11 | j25 | j29 | k.c | hdpe | 154 |  |  |  |  | 1130
11 | 2023-06-11 | j29 | j31 | k.c | hdpe | 119 |  |  |  |  | 1249
12 | 2023-06-11 | j31 | j32 | k.c | hdpe | 20 |  |  |  |  | 1269
13 | 2023-06-11 | j32 | j36 | k.c | hdpe | 36 |  |  |  |  | 1305
14 | 2023-06-11 | j50 | j48 | k.c | hdpe | 114 |  |  |  |  | 1419
15 | 2023-06-12 | j51 | j55 | k.c | hdpe |  |  | 100 |  |  | 1519
16 | 2023-06-12 | j55 | j67 | k.c | hdpe |  |  | 150 |  |  | 1669
17 | 2023-06-13 | j55 | j67 | k.c | hdpe |  |  | 135 |  |  | 1804
18 | 2023-06-13 | j67 | j77 | k.c | hdpe |  |  | 65 |  |  | 1869
19 | 2023-06-14 | j67 | j77 | k.c | hdpe |  |  | 100 |  |  | 1969
20 | 2023-06-14 | j67 | j75 | k.c | hdpe |  | 50 |  |  |  | 2019
21 | 2023-06-15 | J77 | J106 | k.c | hdpe |  |  | 62 |  |  | 2081
22 | 2023-06-15 | J67 | J75 | k.c | hdpe |  | 69 |  |  |  | 2150
23 | 2023-06-16 | j77 | j106 | k.c | hdpe |  |  | 100 |  |  | 2250
24 | 2023-06-16 | j77 | j78 | k.c | hdpe | 20 |  |  |  |  | 2270
25 | 2023-06-17 | j77 | j106 | k.c | hdpe |  |  | 200 |  |  | 2470
26 | 2023-06-18 | j77 | j106 | k.c | hdpe |  |  | 260 |  |  | 2730
27 | 2023-06-19 | j77 | j106 | k.c | hdpe |  |  | 30 |  |  | 2760
28 | 2023-06-19 | j106 | j107 | k.c | hdpe | 295 |  |  |  |  | 3055
29 | 2023-06-20 | j77 | j78 | k.c | hdpe | 80 |  |  |  |  | 3135
30 | 2023-06-20 | j78 | j80 | k.c | hdpe | 30 |  |  |  |  | 3165
31 | 2023-06-20 | j80 | j105 | k.c | hdpe | 155 |  |  |  |  | 3320
32 | 2023-06-21 | j80 | j105 | k.c | hdpe | 161 |  |  |  |  | 3481
33 | 2023-06-21 | j80 | j76 | k.c | hdpe | 62 |  |  |  |  | 3543
34 | 2023-06-21 | j76 | j75 | k.c | hdpe |  | 80 |  |  |  | 3623
35 | 2023-06-22 | j67 | j75 | k.c | hdpe |  | 120 |  |  |  | 3743
36 | 2023-06-22 | j75 | j59 | k.c | hdpe |  | 80 |  |  |  | 3823
37 | 2023-06-23 | j59 | j57 | k.c | hdpe |  | 76 |  |  |  | 3899
38 | 2023-06-23 | j59 | j60 | k.c | hdpe | 6 |  |  |  |  | 3905
39 | 2023-06-23 | j57 | j58 | k.c | hdpe | 46 |  |  |  |  | 3951
40 | 2023-06-23 | j57 | j54 | k.c | hdpe |  | 74 |  |  |  | 4025
41 | 2023-06-25 | J105 | J116 | k.c | hdpe | 158 |  |  |  |  | 4183
42 | 2023-06-25 | J80 | J105 | k.c | hdpe | 30 |  |  |  |  | 4213
43 | 2023-06-25 | J105 | J103 | k.c | hdpe | 11 |  |  |  |  | 4224
44 | 2023-06-25 | J57 | J54 | k.c | hdpe |  | 26 |  |  |  | 4250
45 | 2023-09-21 | j106 | j108 | k.c | hdpe |  | 96 |  |  |  | 4346
46 | 2023-09-21 | j108 | j114 | k.c | hdpe |  | 27 |  |  |  | 4373
47 | 2023-09-21 | j114 | j128 | k.c | hdpe |  | 75 |  |  |  | 4448
48 | 2023-09-21 | j128 | j130 | k.c | hdpe |  | 10 |  |  |  | 4458
49 | 2023-09-21 | j130 | j133 | k.c | hdpe |  | 58 |  |  |  | 4516
50 | 2023-09-22 | j133 | j135 | k.c | hdpe | 11 |  |  |  |  | 4527
51 | 2023-09-22 | j135 | j148 | k.c | hdpe | 51 |  |  |  |  | 4578
52 | 2023-09-22 | j148 | j153 | k.c | hdpe | 56 |  |  |  |  | 4634
53 | 2023-09-22 | j153 | j156 | k.c | hdpe | 16 |  |  |  |  | 4650
54 | 2023-09-22 | j156 | j166 | k.c | hdpe | 19 |  |  |  |  | 4669
55 | 2023-09-22 | j166 | j172 | k.c | hdpe | 52 |  |  |  |  | 4721
56 | 2023-09-22 | j172 | j173 | k.c | hdpe | 57 |  |  |  |  | 4778
57 | 2023-09-22 | j172 | j179 | k.c | hdpe | 76 |  |  |  |  | 4854
58 | 2023-09-22 | j179 | j180 | k.c | hdpe | 66 |  |  |  |  | 4920
59 | 2023-09-22 | j180 | j181 | k.c | hdpe | 28 |  |  |  |  | 4948
60 | 2023-09-22 | j181 | j171 | k.c | hdpe | 70 |  |  |  |  | 5018
61 | 2023-09-23 | j171 | j151 | k.c | hdpe | 267 |  |  |  |  | 5285
62 | 2023-09-23 | j171 | j169 | k.c | hdpe | 122 |  |  |  |  | 5407
63 | 2023-09-23 | j169 | j183 | k.c | hdpe | 217 |  |  |  |  | 5624
64 | 2023-09-24 | j156 | j157 | k.c | hdpe | 84 |  |  |  |  | 5708 |  |  |  |  | `
65 | 2023-09-24 | j179 | j177 | k.c | hdpe | 20 |  |  |  |  | 5728
66 | 2023-09-24 | j177 | j175 | k.c | hdpe | 45 |  |  |  |  | 5773
67 | 2023-09-24 | j175 | j174 | k.c | hdpe | 23 |  |  |  |  | 5796
68 | 2023-09-24 | j174 | j176 | k.c | hdpe | 34 |  |  |  |  | 5830
69 | 2023-09-24 | j109 | j110 | k.c | hdpe | 66 |  |  |  |  | 5896
70 | 2023-09-24 | j110 | j112 | k.c | hdpe | 24 |  |  |  |  | 5920
71 | 2023-09-24 | j110 | j111 | k.c | hdpe | 10 |  |  |  |  | 5930
72 | 2023-09-24 | j173 | j166 | k.c | hdpe | 74 |  |  |  |  | 6004
73 | 2023-09-24 | j176 | j180 | k.c | hdpe | 55 |  |  |  |  | 6059
74 | 2023-09-24 | j108 | j109 | k.c | hdpe |  | 22 |  |  |  | 6081
75 | 2023-09-24 | j109 | j113 | k.c | hdpe |  | 17 |  |  |  | 6098
76 | 2023-09-24 | j113 | j118 | k.c | hdpe |  | 36 |  |  |  | 6134
77 | 2023-09-25 | j118 | j122 | k.c | hdpe |  | 38 |  |  |  | 6172
78 | 2023-09-25 | j122 | j125 | k.c | hdpe | 55 |  |  |  |  | 6227
79 | 2023-09-25 | j122 | j137 | k.c | hdpe | 104 |  |  |  |  | 6331
80 | 2023-09-25 | j137 | j146 | k.c | hdpe | 392 |  |  |  |  | 6723
81 | 2023-09-25 | j146 | j145 | k.c | hdpe | 15 |  |  |  |  | 6738
82 | 2023-09-25 | j145 | j147 | k.c | hdpe | 113 |  |  |  |  | 6851
83 | 2023-09-25 | j137 | j138 | k.c | hdpe | 17 |  |  |  |  | 6868
84 | 2023-09-25 | j138 | j144 | k.c | hdpe | 122 |  |  |  |  | 6990
85 | 2023-09-25 | j144 | j149 | k.c | hdpe | 83 |  |  |  |  | 7073
86 | 2023-09-25 | j149 | j150 | k.c | hdpe | 70 |  |  |  |  | 7143
87 | 2023-09-25 | j149 | j158 | k.c | hdpe | 92 |  |  |  |  | 7235
88 | 2023-09-25 | j158 | j168 | k.c | hdpe | 42 |  |  |  |  | 7277
89 | 2023-09-26 | j169 | j168 | k.c | hdpe | 29 |  |  |  |  | 7306
90 | 2023-09-26 | j168 | j164 | k.c | hdpe | 34 |  |  |  |  | 7340
91 | 2023-09-26 | j164 | j163 | k.c | hdpe | 24 |  |  |  |  | 7364
92 | 2023-09-26 | j163 | j162 | k.c | hdpe | 97 |  |  |  |  | 7461
93 | 2023-09-27 | j168 | j170 | k.c | hdpe | 35 |  |  |  |  | 7496
94 | 2023-09-27 | j170 | j167 | k.c | hdpe | 61 |  |  |  |  | 7557
95 | 2023-09-27 | j167 | j155 | k.c | hdpe | 57 |  |  |  |  | 7614
96 | 2023-09-27 | j155 | j148 | k.c | hdpe | 90 |  |  |  |  | 7704
97 | 2023-09-27 | 174 | 170 | k.c | hdpe | 40 |  |  |  |  | 7744
98 | 2023-09-30 | J140 | J141 | k.c | hdpe | 108 |  |  |  |  | 7852
99 | 2023-09-30 | J140 | J126 | k.c | hdpe | 105 |  |  |  |  | 7957
100 | 2023-09-30 | J126 | J116 | k.c | hdpe | 39 |  |  |  |  | 7996
101 | 2023-09-30 | J116 | J105 | k.c | hdpe | 300 |  |  |  |  | 8296
102 | 2023-10-06 | J76 | J81 | k.c | hdpe | 116 |  |  |  |  | 8412
103 | 2023-10-06 | J81 | J83 | k.c | hdpe | 14 |  |  |  |  | 8426
104 | 2023-10-06 | J83 | J86 | k.c | hdpe | 43 |  |  |  |  | 8469
105 | 2023-10-06 | J86 | J87 | k.c | hdpe | 22 |  |  |  |  | 8491
106 | 2023-10-07 | J75 | J73 | k.c | hdpe | 109 |  |  |  |  | 8600
107 | 2023-10-07 | J73 | J74 | k.c | hdpe | 125 |  |  |  |  | 8725
108 | 2023-10-07 | J81 | J82 | k.c | hdpe | 35 |  |  |  |  | 8760
109 | 2023-10-07 | J87 | J89 | k.c | hdpe | 74 |  |  |  |  | 8834
110 | 2023-10-07 | J89 | J92 | k.c | hdpe | 24 |  |  |  |  | 8858
111 | 2023-10-07 | J92 | J93 | k.c | hdpe | 59 |  |  |  |  | 8917
112 | 2023-10-09 | J54 | J45 | k.c | hdpe |  | 300 |  |  |  | 9217
113 | 2023-10-10 | J45 | J41 | k.c | hdpe |  | 10 |  |  |  | 9227
114 | 2023-10-10 | J54 | J45 | k.c | hdpe |  | 70 |  |  |  | 9297
115 | 2023-10-10 | J45 | J46 | k.c | hdpe | 10 |  |  |  |  | 9307
116 | 2023-10-10 | J46 | J48 | k.c | hdpe | 70 |  |  |  |  | 9377
117 | 2023-10-12 | J12 | J21 | k.c | hdpe | 59 |  |  |  |  | 9436
118 | 2023-10-12 | J21 | J39 | k.c | hdpe | 71 |  |  |  |  | 9507
119 | 2023-10-13 | j1 | j2 | k.c | hdpe |  |  |  |  | 129 | 9636
120 | 2023-10-13 | j2 | j6 | k.c | hdpe |  |  |  |  | 17 | 9653
121 | 2023-10-13 | j67 | j7 | k.c | hdpe |  |  |  |  | 48 | 9701
122 | 2023-10-13 | j7 | j12 | k.c | hdpe |  |  |  |  | 39 | 9740
123 | 2023-10-14 | j12 | j41 | k.c | hdpe |  |  |  |  | 150 | 9890
124 | 2023-10-15 | j44 | j47 | k.c | hdpe |  |  |  | 100 |  | 9990
125 | 2023-10-15 | j47 | j50 | k.c | hdpe |  |  |  | 200 |  | 10190
126 | 2023-10-15 | j50 | j51 | k.c | hdpe |  |  |  | 149 |  | 10339 |  |  |  |  | -2898
127 | 2023-10-16 | j32 | j36 | k.c | hdpe | 36 |  |  |  |  | 10375
128 | 2023-10-17 | j36 | j37 | k.c | hdpe | 34 |  |  |  |  | 10409
129 | 2023-10-18 | j12 | j41 | k.c | hdpe |  |  |  |  | 64 | 10473
130 | 2023-10-18 | j41 | j45 | k.c | hdpe |  | 31 |  |  |  | 10504
131 | 2023-10-19 | j41 | j42 | k.c | hdpe |  |  |  | 36 |  | 10540
132 | 2023-10-25 | j133 | j134 | k.c | hdpe | 161 |  |  |  |  | 10701
133 | 2023-10-25 | j134 | j144 | k.c | hdpe | 155 |  |  |  |  | 10856
[6 empty] | 63 | 90 | 110 | 125 | 140
[6 empty] | 7357 | 1365 | 1202 | 485 | 447 | 10856
[6 empty] | 12324 | 1649 | 1167 | 590 | 459 | 16189

## WQ Vs Execution
POWERMECH PROJECTS LIMITED
UP JAL NIGAM RWSS PROJECT
PRAYAGRAJ DIV - PRATAPGARH DIST.
WO Qty's Vs Execution Qty's
#REF! | [26 empty] | #REF!
S.No | Description of Work | Attarsand & Parsupur P-3 (Mangraura) |  |  |  |  | Saray Jammuvaril (Mangraura) |  |  |  |  | Sarsidih (Mangraura) | [9 empty] | Total |  |  |  |  | Remarks
|  | 6000032180 |  |  |  |  | 6000032180 |  |  |  |  | 6000032180 | [9 empty] | 6000032180
1 | HDPE Pipes - Excavation , laying , Jointing, Backfilling | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill
1.1 | 63 mm HDPE | 5880 | 3115 | 3115 | 3115 | 0 | 4654 | 3008.2 | 3008.2 | 3008.2 | 0 | 12324 | 7357 | 7357 | 5588 | 1769 | [5 empty] | 22858 | 13480.2 | 13480.2 |  | 1769 |  | 2765 | 1645.8 | 4967 | 1061.4
1.2 | 75 mm HDPE | 4144 | 2768.2 | 2768.2 | 2768.2 | 0 | 3234 | 1928.3 | 1928.3 | 1928.3 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 7378 | 4696.5 | 4696.5 | 4696.5 | 0 |  | 1375.8 | 1305.7 | 0 | 0
1.3 | 90 mm HDPE | 2528 | 2276 | 2276 | 2276 | 0 | 1867 | 483.6 | 483.6 | 483.6 | 0 | 1649 | 1365 | 1365 | 954 | 411 | [5 empty] | 6044 | 4124.6 | 4124.6 | 3713.6 | 411 |  | 252 | 1383.4 | 284 | 246.6
1.4 | 110mm HDPE | 3580 | 3275.5 | 3275.5 | 3275.5 | 0 | 2197 | 1740.1 | 1740.1 | 1740.1 | 0 | 1167 | 1202 | 1202 | 934.4 | 267.6 | [5 empty] | 6944 | 6217.6 | 6217.6 | 5950 | 267.6 |  | 304.5 | 456.9 | -35 | 160.56
1.5 | 125mm HDPE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 485 | 485 | 0 | 485 | [5 empty] | 590 | 485 | 485 | 0 | 485 |  | 0 | 0 | 105
1.6 | 140mm HDPE |  |  | 0 | 0 | 0 | 3213 | 2465.7 | 2465.7 | 2465.7 | 0 | 459 | 447 | 447 | 0 | 447 | [5 empty] | 3672 | 2912.7 | 2912.7 | 2465.7 | 447 |  | 0 | 747.3 | 12
1.7 | 160mm HDPE |  |  | 0 | 0 | 0 | 872 | 886.7 | 872 | 872 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 872 | 886.7 | 872 | 872 | 0 |  | 0 | -14.7 | 0
1.8 | 200mm HDPE |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
1.8 | 250 DI_K7 | 2994 | 740 | 740 | 740 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0 | [5 empty] | 2994 | 740 | 740 | 740 | 0 |  | 2254 | 0 | 0
Sub Total Total |  | 19126 | 12174.7 | 12174.7 | 12174.7 | 0 | 16037 | 10512.6 | 10497.9 | 10497.9 | 0 | 16189 | 10856 | 10856 | 7476.4 | 3379.6 | 0 | 0 | 0 | 0 | 0 | 51352 | 33543.3 | 33528.6 | 18437.8 | 3379.6
1 | Gap Closing works - 5% | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill
1.1 | 63 mm HDPE | 5880 | 3083.9 | 3083.9 | 3083.9 | 0 | 4654 | 3008.2 | 3008.2 | 3008.2 | 0 | 12324 | [9 empty] | 22858 | 6092.1 | 6092.1 | 6092.1 | 0 |  | 2796.1 | 1645.8 |  | 0
1.2 | 75 mm HDPE | 4144 | 2760.9 | 2760.9 | 2760.9 | 0 | 3234 | 1928.3 | 1928.3 | 1928.3 | 0 | 0 | [9 empty] | 7378 | 4689.2 | 4689.2 | 4689.2 | 0 |  | 1383.1 | 1305.7 |  | 0
1.3 | 90 mm HDPE | 2528 | 2109 | 2109 | 2109 | 0 | 1867 | 483.6 | 483.6 | 483.6 | 0 | 1649 | [9 empty] | 6044 | 2592.6 | 2592.6 | 2592.6 | 0 |  | 419 | 1383.4 |  | 0
1.4 | 110mm HDPE | 3580 | 3010.6 | 3010.6 | 3010.6 | 0 | 2197 | 1740.1 | 1740.1 | 1740.1 | 0 | 1167 | [9 empty] | 6944 | 4750.7 | 4750.7 | 4750.7 | 0 |  | 569.4 | 456.9 |  | 0
1.5 | 125mm HDPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | [9 empty] | 590 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
1.6 | 140mm HDPE |  | 0 | 0 | 0 | 0 | 3213 | 2465.7 | 2465.7 | 2465.7 | 0 | 459 | [9 empty] | 3672 | 2465.7 | 2465.7 | 2465.7 | 0 |  | 0 | 747.3 |  | 0
1.7 | 160mm HDPE |  | 0 | 0 | 0 | 0 | 872 | 886.7 | 872 | 872 | 0 | 0 | [9 empty] | 872 | 886.7 | 872 | 872 | 0 |  | 0 | -14.7 |  | 0
1.8 | 200mm HDPE |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0
1.8 | 250 DI_K7 | 2994 | 740 | 740 | 740 | 0 | 0 |  | 0 |  |  | 0 | [9 empty] | 2994 | 740 | 740 | 740 | 0 |  | 2254 | 0 |  | 0
Sub Total Total |  | 19126 | 11704.4 | 11704.4 | 11704.4 | 0 | 16037 | 10512.6 | 10497.9 | 10497.9 | 0 | 16189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51352 | 22217 | 22202.3 | 22202.3 | 0
1 | Hydro Testing - 15%
1.1 | 63 mm HDPE | 5880 | 3083.9 | 3083.9 | 3083.9 | 0 | 4654 | 3007.8 | 3007.8 | 3007.8 | 0 | 12324 | [9 empty] | 22858 | 6091.7 | 6091.7 | 6091.7 | 0
1.2 | 75 mm HDPE | 4144 | 2760.9 | 2760.9 | 2760.9 | 0 | 3234 | 1943 | 1943 | 1943 | 0 | 0 | [9 empty] | 7378 | 4703.9 | 4703.9 | 4703.9 | 0
1.3 | 90 mm HDPE | 2528 | 2109 | 2109 | 2109 | 0 | 1867 | 483.6 | 483.6 | 483.6 | 0 | 1649 | [9 empty] | 6044 | 2592.6 | 2592.6 | 2592.6 | 0
1.4 | 110mm HDPE | 3580 | 3010.6 | 3010.6 | 3010.6 | 0 | 2197 | 1770.1 | 1770.1 | 1770.1 | 0 | 1167 | [9 empty] | 6944 | 4780.7 | 4780.7 | 4780.7 | 0
1.5 | 125mm HDPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | [9 empty] | 590 | 0 | 0 | 0 | 0
1.6 | 140mm HDPE | 0 | 0 | 0 | 0 | 0 | 3213 | 2466.7 | 2466.7 | 2466.7 | 0 | 459 | [9 empty] | 3672 | 2466.7 | 2466.7 | 2466.7 | 0
1.7 | 160mm HDPE | 0 | 0 | 0 | 0 | 0 | 872 | 886.7 | 872 | 872 | 0 | 0 | [9 empty] | 872 | 886.7 | 872 | 872 | 0
1.8 | 200mm HDPE | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0
1.8 | 250 DI_K7 | 2994 | 740 | 740 | 740 | 0 | [15 empty] | 2994 | 740 | 740 | 740 | 0
Sub Total Total |  | 19126 | 11704.4 | 11704.4 | 11704.4 | 0 | 16037 | 10557.9 | 10543.2 | 10543.2 | 0 | 16189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51352 | 22262.3 | 22247.6 | 22247.6 | 0
2 | Dismatling & Restoration of Roads
2.1 | For B.O.E Surface | 931.32 | 110.43 | 110.43 | 110.43 | 0 | 1000 |  |  |  |  | 1791.019 | [9 empty] | 3722.339 | 110.43 | 110.43 | 110.43 | 0 |  | 820.89 | 1000 | 1791.019
2.2 | For Bituminous Surface | 696.38 | 6.63 | 6.63 | 6.63 | 0 | 1000 |  |  |  |  | 614.106 | [9 empty] | 2310.486 | 6.63 | 6.63 | 6.63 | 0 |  | 689.75 | 1000 | 614.106
2.3 | For Interlocking Surface |  | 55.43 | 0 | 0 | 0 | 50 | [14 empty] | 50 | 55.43 | 0 | 0 | 0 |  | -55.43 | 50 | 0
2.4 | For CC Road | 34.15 |  | 0 | 0 | 0 | [15 empty] | 34.15 | 0 | 0 | 0 | 0 |  | 34.15 | 0 | 0
4 | Fixing of FHTCS excluding Supply. |  |  | 0 |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
a) | On Fixing | 463 | #REF! | #REF! |  | #REF! | 300 | 52 | 52 | 52 | 0 | 310 | [9 empty] | 763 | #REF! | #REF! | 52 | #REF!
b) | On Testing |  |  | 0 |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
c) | On Commissioning |  |  | 0 |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
5 | Stand post Fixing with required accessories excluding Supply | 1 | #REF! | #REF! |  | #REF! | 1 |  |  |  |  | 1 | [9 empty] | 2 | #REF! | #REF! | 0 | #REF!
6 | Nala/Culvert Crossing ( width -3.5 m) upto Dia 300 | 1 |  | 0 |  | 0 | 1 |  |  |  |  | 2 | [9 empty] | 2 | 0 | 0 | 0 | 0
Prepared By Site Engineer (Sr Eng/ AM-SMX ) ( DM-PMX ) AGM Project Incharge

## HT_Attarsand Pars (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Hydro Testing Report for Atarsand & Parasupur (P-3) (Block Mangura)
#REF!
SL. NO. | Testing Date | Material of Pipe | Dia of the Pipe | Start Node | End Node | Length | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Remarks
1 | 2023-02-11 | HDPE | 110 | J-164 | J-430 | 642 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
2 | 2023-02-11 | HDPE | 110 | J-430 | J-567 | 216 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
3 | 2023-02-11 | HDPE | 110 | J-567 | J-544 | 107 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
4 | 2023-02-11 | HDPE | 110 | J-544 | J-484 | 43 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
5 | 2023-02-11 | HDPE | 110 | J-484 | J-489 | 14 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
6 | 2023-02-11 | HDPE | 110 | J-489 | J-638 | 48 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
7 | 2023-02-11 | HDPE | 110 | J-638 | J-589 | 42 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
8 | 2023-02-11 | HDPE | 110 | J-583 | J-287 | 271 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
9 | 2023-02-11 | HDPE | 110 | J-287 | J-311 | 20 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
10 | 2023-02-11 | HDPE | 110 | J-311 | J-372 | 10 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
11 | 2023-02-11 | HDPE | 63 | J-567 | J-358 | 168 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
12 | 2023-02-11 | HDPE | 63 | J-358 | J-479 | 13 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
13 | 2023-02-11 | HDPE | 63 | J-544 | J-201 | 130 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
14 | 2023-02-11 | HDPE | 75 | J-358 | J-201 | 106 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
15 | 2023-02-11 | HDPE | 75 | J-201 | J-166 | 73 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
16 | 2023-02-11 | HDPE | 75 | J-166 | J-131 | 93 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
17 | 2023-02-11 | HDPE | 75 | J-131 | J-311 | 283 | 5.5 | 3:10 PM | 6:10 PM | 3 Hrs
18 | 2023-06-22 | HDPE | 90 | J650 | J633 | 8.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3
19 | 2023-06-22 | HDPE | 90 | J633 | J711 | 126.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
20 | 2023-06-22 | HDPE | 90 | J711 | J457 | 78.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3
21 | 2023-06-22 | HDPE | 75 | J395 | J270 | 87.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
22 | 2023-06-22 | HDPE | 63 | J270 | J286 | 83.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3
23 | 2023-06-22 | HDPE | 90 | J711 | J719 | 26.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
24 | 2023-06-22 | HDPE | 90 | J719 | J652 | 59.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3
25 | 2023-06-22 | HDPE | 90 | J652 | J612 | 22.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
26 | 2023-06-22 | HDPE | 90 | J612 | J526 | 16.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3
27 | 2023-06-22 | HDPE | 90 | J526 | J538 | 13.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3
28 | 2023-06-22 | HDPE | 90 | J538 | J546 | 72.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3
29 | 2023-06-22 | HDPE | 90 | J546 | J614 | 89.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3
30 | 2023-06-22 | HDPE | 63 | J300 | J652 | 22.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3
31 | 2023-06-22 | HDPE | 63 | J159 | J423 | 150.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
32 | 2023-06-22 | HDPE | 63 | J509 | J596 | 57.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3
33 | 2023-06-22 | HDPE | 63 | J596 | J405 | 75.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3
34 | 2023-06-22 | HDPE | 63 | J696 | J507 | 21.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3
35 | 2023-06-22 | HDPE | 63 | J501 | J151 | 49.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3
36 | 2023-06-22 | HDPE | 63 | J563 | J491 | 35.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3
37 | 2023-06-22 | HDPE | 63 | J427 | J73 | 139.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3
38 | 2023-06-22 | HDPE | 63 | J216 | J264 | 38.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
39 | 2023-06-22 | HDPE | 63 | J264 | J420 | 23.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3
40 | 2023-06-22 | HDPE | 75 | J171 | J277 | 54.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3
41 | 2023-06-22 | HDPE | 75 | J735 | J696 | 57.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3
42 | 2023-06-22 | HDPE | 75 | J194 | J211 | 78.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3
43 | 2023-06-22 | HDPE | 75 | J211 | J128 | 39.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3
44 | 2023-06-22 | HDPE | 75 | J128 | J121 | 34.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3
45 | 2023-06-22 | HDPE | 75 | J121 | J106 | 32.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3
46 | 2023-06-22 | DI | 250 | J750 | J746 | 740 | 5.5KG/CM2 | 3.3 | 1 | 4.3
47 | 2023-06-22 | HDPE | 63 | J638 | J266 | 41.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
48 | 2023-06-22 | HDPE | 110 | J589 | J638 | 79.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
49 | 2023-06-22 | HDPE | 110 | J638 | J489 | 50.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5
50 | 2023-06-24 | HDPE | 75 | J489 | J597 | 58.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
51 | 2023-06-24 | HDPE | 63 | J597 | J605 | 13.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5
52 | 2023-06-24 | HDPE | 75 | J597 | J543 | 43.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5
53 | 2023-06-24 | HDPE | 63 | J543 | J606 | 142.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
54 | 2023-06-24 | HDPE | 75 | J543 | J547 | 127.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5
55 | 2023-06-24 | HDPE | 63 | J588 | J547 | 133 | 5.5KG/CM2 | 3.5 | 1 | 4.5
56 | 2023-06-24 | HDPE | 90 | J564 | J588 | 97.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5
57 | 2023-06-24 | HDPE | 75 | J547 | J564 | 53.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
58 | 2023-06-24 | HDPE | 75 | J588 | J432 | 162.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5
59 | 2023-06-24 | HDPE | 90 | J564 | J614 | 578.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
60 | 2023-06-24 | HDPE | 110 | J614 | J418 | 232.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5
61 | 2023-06-24 | HDPE | 110 | J418 | J372 | 72.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5
62 | 2023-06-24 | HDPE | 110 | J372 | J311 | 11.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
63 | 2023-06-24 | HDPE | 110 | J311 | J287 | 21.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
64 | 2023-06-24 | HDPE | 75 | J311 | J131 | 295.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
65 | 2023-06-24 | HDPE | 110 | J287 | J589 | 272.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5
66 | 2023-06-24 | HDPE | 90 | J693 | J603 | 10.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
67 | 2023-06-24 | HDPE | 90 | J603 | J313 | 182.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5
68 | 2023-06-24 | HDPE | 90 | J313 | J341 | 18.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
69 | 2023-06-24 | HDPE | 90 | J424 | J194 | 68.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5
70 | 2023-06-24 | HDPE | 63 | J194 | J680 | 30.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
71 | 2023-06-24 | HDPE | 110 | J194 | J395 | 98.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
72 | 2023-06-24 | HDPE | 110 | J395 | J457 | 14.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
73 | 2023-06-24 | HDPE | 90 | J457 | J496 | 98.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5
74 | 2023-06-24 | HDPE | 90 | J496 | J557 | 16.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5
75 | 2023-06-24 | HDPE | 90 | J557 | J508 | 38.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5
76 | 2023-06-24 | HDPE | 90 | J508 | J325 | 58.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5
77 | 2023-06-24 | HDPE | 90 | J325 | J699 | 57.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5
78 | 2023-06-24 | HDPE | 63 | J508 | J650 | 70.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5
79 | 2023-06-24 | HDPE | 90 | J650 | J453 | 72.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
80 | 2023-06-24 | HDPE | 90 | J672 | J529 | 65.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5
81 | 2023-06-24 | HDPE | 90 | J453 | J529 | 6.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5
82 | 2023-06-24 | HDPE | 75 | J529 |  | 292.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5
83 | 2023-06-24 | HDPE | 110 | J714 | J718 | 195.1 | 6KG/CM2 | 3.2 | 1 | 4.2
84 | 2023-06-24 | HDPE | 90 | J718 | J218 | 36.4 | 6KG/CM2 | 3.2 | 1 | 4.2
85 | 2023-06-24 | HDPE | 63 | J218 | J448 | 26.6 | 6KG/CM2 | 3.2 | 1 | 4.2
86 | 2023-06-24 | HDPE | 90 | J218 | J394 | 46.3 | 6KG/CM2 | 3.2 | 1 | 4.2
87 | 2023-06-24 | HDPE | 90 | J462 | J394 | 46.6 | 6KG/CM2 | 3.2 | 1 | 4.2
88 | 2023-06-24 | HDPE | 63 | J462 | J376 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2
89 | 2023-06-24 | HDPE | 63 | J524 | J382 | 120.4 | 6KG/CM2 | 3.2 | 1 | 4.2
90 | 2023-06-24 | HDPE | 110 | J382 | J469 | 212.2 | 6KG/CM2 | 3.2 | 1 | 4.2
91 | 2023-06-24 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2
92 | 2023-06-24 | HDPE | 63 | J338 | J410 | 94.7 | 6KG/CM2 | 3.2 | 1 | 4.2
93 | 2023-06-24 | HDPE | 63 | J338 | J171 | 24.6 | 6KG/CM2 | 3.2 | 1 | 4.2
94 | 2023-06-24 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2
95 | 2023-06-24 | HDPE | 75 | J469 | J463 | 75.1 | 6KG/CM2 | 3.2 | 1 | 4.2
96 | 2023-06-24 | HDPE | 75 | J463 | J467 | 46.2 | 6KG/CM2 | 3.2 | 1 | 4.2
97 | 2023-06-24 | HDPE | 75 | J467 | J478 | 49.7 | 6KG/CM2 | 3.2 | 1 | 4.2
98 | 2023-06-24 | HDPE | 75 | J478 | J383 | 14.8 | 6KG/CM2 | 3.2 | 1 | 4.2
99 | 2023-06-24 | HDPE | 75 | J383 | J382 | 81.3 | 6KG/CM2 | 3.2 | 1 | 4.2
100 | 2023-06-24 | HDPE | 75 | J383 | J243 | 47.5 | 6KG/CM2 | 3.2 | 1 | 4.2
101 | 2023-06-24 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2
102 | 2023-06-24 | HDPE | 63 | J201 | J544 | 137.3 | 6KG/CM2 | 3.2 | 1 | 4.2
103 | 2023-06-24 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2
104 | 2023-06-24 | HDPE | 75 | J166 | J201 | 73.9 | 6KG/CM2 | 3.2 | 1 | 4.2
105 | 2023-06-24 | HDPE | 75 | J166 | J131 | 93.3 | 6KG/CM2 | 3.2 | 1 | 4.2
106 | 2023-06-24 | HDPE | 63 | J131 | J589 | 103.6 | 6KG/CM2 | 3.2 | 1 | 4.2
107 | 2023-06-24 | HDPE | 63 | J462 | J374 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2
108 | 2023-06-24 | HDPE | 63 | J479 | J462 | 17.4 | 6KG/CM2 | 3.2 | 1 | 4.2
109 | 2023-06-24 | HDPE | 110 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2
110 | 2023-06-24 | HDPE | 63 | J358 | J439 | 13.4 | 6KG/CM2 | 3.2 | 1 | 4.2
111 | 2023-06-24 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2
112 | 2023-06-25 | HDPE | 63 | J547 | J588 | 10.3 | 6KG/CM2 | 3.2 | 1 | 4.2
113 | 2023-06-25 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2
114 | 2023-06-25 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2
115 | 2023-06-25 | HDPE | 90 | J696 | J646 | 97.5 | 6KG/CM2 | 3.2 | 1 | 4.2
116 | 2023-06-25 | HDPE | 110 | J576 | J707 | 168.1 | 6KG/CM2 | 3.2 | 1 | 4.2
117 | 2023-06-25 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2
118 | 2023-06-25 | HDPE | 63 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2
119 | 2023-06-25 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2
120 | 2023-06-25 | HDPE | 63 | J194 | J680 | 30.1 | 6KG/CM2 | 3.2 | 1 | 4.2
18
Total Length | [5 empty] | 11704.4
HT Abstract
[5 empty] | Dia | Length
[5 empty] | 63 | 3083.9
[5 empty] | 75 | 2760.9
[5 empty] | 90 | 2109
[5 empty] | 110 | 3010.6
[5 empty] | 125 | 0
[5 empty] | 140 | 0
[5 empty] | 160 | 0
[5 empty] | 200 | 0
[5 empty] | 250 | 740
[5 empty] | Total | 11704.4
Prepared By Site Engineer ( Sr.Eng/AM-SMX ) (Dy.M-PMX ) AGM Project Incharge

## FHTC_Saray Jamu (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Saray Jammuvaril (Mangura) FHTC Measurement Sheet
SR.NO | START NODE | END NODE | HDPE | MDPE PIPE | NAME | AADHAR NUMBER | PHONE NUMBER
1 | J163 | J103 | 63 | 5 | JAMUNA | 940253791176 | 8052246339
2 | J163 | J103 | 63 | 5 | UMA PRAKASH | 651669258347 | 7379497850
3 | J163 | J103 | 63 | 5 | RAM JAWAN | 958969999566 | 7800605950
4 | J163 | J103 | 63 | 7 | SURIBI | 919974595478 | 8354919254
5 | J163 | J134 | 63 | 7 | MADURI | 812635107926 | 9621559650
6 | J163 | J134 | 63 | 5 | RAM VALI | 740066163470 | 9670206036
7 | J163 | J134 | 63 | 7 | BAGHU YADAV | 511374774276 | 9670206036
8 | J159 | J201 | 63 | 5 | SON KUMAR | 916490465213 | 8511731720
9 | J159 | J201 | 63 | 6 | SAM TIWARI | 753683774896 | 9918703950
10 | J159 | J201 | 63 | 5 | GAYATHRI DEVI | 347121308211 | 9594195325
11 | J159 | J201 | 63 | 5 | TANDARA BERA SHIIMHA | 957458789465
12 | J159 | J201 | 63 | 5 | AFLAL | 573187004221
13 | J159 | J201 | 63 | 5 | FANLAL | 293638410994
14 | J275 | J269 | 63 | 5 | SIVAKANTH | 712145381832
15 | J275 | J269 | 63 | 5 | SIVA KUMARI | 644805671515 | 7607026007
16 | J275 | J269 | 63 | 5 | DEVAMATI | 593139922449 | 8601732896
17 | J276 | J263 | 63 | 8 | SUMITRA | 686418465551 | 9336369931
18 | J19 | J27 | 110 | 7 | SHALI DEVI | 216854312481
19 | J19 | J27 | 110 | 9 | EFANA KUMARPHAL | 209737519600
20 | J19 | J27 | 110 | 5 | DHARAM | 364034285803
21 | J19 | J27 | 110 | 6 | UBA DEVI | 387472011259
22 | J275 | J269 | 63 | 7 | SANGEETHA | 959480286558
23 | J40 | J16 | 63 | 5 | BHRUJ LAL | 736506891862
24 | J40 | J16 | 63 | 6 | RAM MILAN | 596852998499
25 | J80 | J76 | 63 | 7 | NATH NADTH | 521089037651
26 | J80 | J76 | 63 | 8 | AFTHINA | 522756481453
27 | J80 | J76 | 63 | 5 | MITHRA DEV YADAV | 378036851544
28 | J80 | J76 | 63 | 6 | RAM BAS VARMA | 293658226109 | 9105362179
29 | J84 | J16 | 63 | 6 | LAL MATHI | 718390198364
30 | J76 | J93 | 63 | 6 | RIKI SITA | 577905564520 | 8097764299
31 | J45 | J16 | 75 | 5 | SAMUNA PRASAD | 940253791176 | 8052246339
32 | J45 | J16 | 75 | 8 | OM PRAKESH | 651669258347 | 7379497850
33 | J45 | J16 | 75 | 5 | RAM JATHAN | 958969999566 | 7800605950
34 | J45 | J16 | 75 | 5 | SUSHIL | 919974595472 | 8354919254
35 | J45 | J16 | 75 | 7 | MADHURI | 812635107926 | 9621559650
36 | J45 | J16 | 75 | 5 | RAGHU NATH | 882907194434 | 9601065957
37 | J45 | J20 | 75 | 6 | VEERENDRA PRATAP | 383870701511 | 9918848531
38 | J45 | J20 | 75 | 4 | PRABHU RAM LALA | 513397242000 | 7526074878
39 | J45 | J20 | 75 | 8 | BAL RAM | 348780942346 | 9918848531
40 | J46 | J40 | 90 | 5 | PULAM DEVI | 261029437158
41 | J46 | J40 | 90 | 5 | KANTH LALA | 964375061210 | 7398167717
42 | J46 | J40 | 90 | 6 | RANI DENI | 244300127431 | 8874991073
43 | J14 | J34 | 90 | 8 | SALAN LAL | 954408909312 | 9721174391
44 | J14 | J34 | 90 | 7 | KEVAL DEVATH | 679778061734 | 7390031641
45 | J14 | J34 | 90 | 5 | GIRIJ TIWARI | 940053859769 | 9651025325
46 | J19 | J10 | 110 | 9 | RAM SHANKAR | 746712739410 | 9450401256
47 | J19 | J10 | 110 | 5 | MAMI TIWARI | 608632754926 | 9335501265
48 | J45 | J20 | 75 | 4 | ROSHANI TIWARI | 322727353442
49 | J19 | J27 | 110 | 7 | MAJUDATHI | 361800062225
50 | J19 | J27 | 110 | 5 | SAWMI NATH | 969393125842 | 9665077340
51 | J19 | J27 | 110 | 9 | SUGIL TIWARI | 334651125119 | 8953148385
52 | J19 | J27 | 110 | 5 | BHABITHA | 254701796741 | 7338650632
| TOTAL= |  | 52 | 311 |  | 52
FHTC ABSTRACT
|  |  |  | 63 | 26
|  |  |  | 75 | 10
|  |  |  | 90 | 6
|  |  |  | 110 | 10
|  |  | TOTAL= |  | 52
Prepared By Site Engineer ( Sr.Eng/AM-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Attarsand & Parsupur P-3 (hidden)
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Atarsand & Parasupur (P-3) (Block Mangura) Laying Qty's
Name of the Contractor : Kyathi Enterprises
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 140mm | 160mm | 200mm | DI 250mm
1 |  | J714 | J718 |  | HDPE | 195.1 | [7 empty] | 195.1 | LHS |  | P Saravanan
2 |  | J218 | J448 |  | HDPE | 26.6 | [7 empty] | 221.7 | LHS |  | P Saravanan
3 |  | J462 | J374 |  | HDPE | 83.6 | [7 empty] | 305.3 | LHS |  | P Saravanan
4 |  | J479 | 462 |  | HDPE | 17.4 | [7 empty] | 322.7 | RHS | 3.4 | P Saravanan
5 |  | J524 | J382 |  | HDPE | 120.4 | [7 empty] | 443.1 | RHS | 3.4 | P Saravanan
6 |  | J382 | J469 |  | HDPE | 212.2 | [7 empty] | 655.3 | RHS | 3.4 | P Saravanan
7 |  | J338 | J410 |  | HDPE | 94.7 | [7 empty] | 750 | RHS | 3.4 | P Saravanan
8 |  | J338 | J171 |  | HDPE | 24.6 | [7 empty] | 774.6 | LHS |  | P Saravanan |  | Gap Balance
9 |  | J171 | J167 |  | HDPE | 111.3 | [7 empty] | 885.9 | RHS |  | P Saravanan |  | Gap Balance
10 |  | J567 | J358 |  | HDPE | 170.3 | [7 empty] | 1056.2 | RHS |  | P Saravanan |  | Gap Balance
11 |  | J358 | J439 |  | HDPE | 13.4 | [7 empty] | 1069.6 | LHS | 2 | P Saravanan |  | Gap Balance
12 |  | J201 | J544 |  | HDPE | 137.3 | [7 empty] | 1206.9 | LHS | 2 | P Saravanan
13 |  | J484 | JJ166 |  | HDPE | 169.4 | [7 empty] | 1376.3 | RHS | 1.8 | P Saravanan
14 |  | J131 | J589 |  | HDPE | 103.6 | [7 empty] | 1479.9 | Center | 0 | P Saravanan
15 |  | J638 | J266 | BRICK ROAD | HDPE | 41.1 | [7 empty] | 1521 | Center | 0 | P Saravanan
16 |  | J597 | J605 |  | HDPE | 13.9 | [7 empty] | 1534.9 | LHS | 1.8 | P Saravanan
17 |  | J543 | J606 |  | HDPE | 142.1 | [7 empty] | 1677 | LHS | 1.8 | P Saravanan
18 |  | J547 | J588 |  | HDPE | 10.3 | [7 empty] | 1687.3 | LHS | 1.8 | P Saravanan
19 |  | J588 | J547 |  | HDPE | 133 | [7 empty] | 1820.3 | LHS | 0.9 | P Saravanan
20 |  | j614 | j418 | B.T CROSSING | HDPE | 3.5 | [7 empty] | 1823.8 | LHS | 0.9 | P Saravanan
21 |  | j614 | j418 |  | HDPE | 229.2 | [7 empty] | 2053 | LHS | 0.9 | P Saravanan
22 |  | j194 | j680 |  | HDPE | 30.1 | [7 empty] | 2083.1 | Center |  | P Saravanan
23 |  | J159 | J423 |  | HDPE | 150.2 | [7 empty] | 2233.3 | Center |  | P Saravanan
24 |  | J509 | J596 |  | HDPE | 57.4 | [7 empty] | 2290.7 | LHS | 1.8 | P Saravanan
25 |  | J596 | J405 |  | HDPE | 75.6 | [7 empty] | 2366.3 | LHS | 1.8 | P Saravanan
26 |  | J508 | J650 |  | HDPE | 70.2 | [7 empty] | 2436.5 | LHS | 1.8 | P Saravanan
27 |  | J270 | J286 |  | HDPE | 83.6 | [7 empty] | 2520.1 | Center | 0 | P Saravanan
28 |  | J300 | J652 |  | HDPE | 22.3 | [7 empty] | 2542.4 | Center | 0 | P Saravanan
29 |  | J696 | J507 |  | HDPE | 21.5 | [7 empty] | 2563.9 | Center | 0 | P Saravanan
30 |  | J501 | J151 |  | HDPE | 48.1 | [7 empty] | 2612 | RHS | 1.65 | P Saravanan
31 |  | JJ548 | J511 |  | HDPE | 56.3 | [7 empty] | 2668.3 | RHS | 1.65 | P Saravanan
32 |  | J563 | J491 | BRICK ROAD | HDPE | 35.4 | [7 empty] | 2703.7 | RHS | 1.65 | P Saravanan
33 |  | J427 | J73 |  | HDPE | 139.1 | [7 empty] | 2842.8 | RHS | 1.65 | P Saravanan
34 |  | J216 | j264 |  | HDPE | 38.2 | [7 empty] | 2881 | RHS | 1.65 | P Saravanan
35 |  | j264 | j420 |  | HDPE | 234 | [7 empty] | 3115 | RHS | 1.65 | P Saravanan
36 |  | J469 | J338 |  | HDPE |  | 44.5 | [6 empty] | 3159.5 | RHS | 1.65 | P Saravanan
37 |  | J171 | J277 |  | HDPE |  | 54.2 | [6 empty] | 3213.7 | RHS | 1.65 | P Saravanan
38 |  | J338 | J463 |  | HDPE |  | 75.1 | [6 empty] | 3288.8 | RHS | 1.65 | P Saravanan
39 |  | J463 | J467 |  | HDPE |  | 46.2 | [6 empty] | 3335 | RHS | 1.65 | Shashiranjan
40 |  | J467 | J478 |  | HDPE |  | 49.7 | [6 empty] | 3384.7 | RHS | 1.65 | Shashiranjan
41 |  | J478 | J383 |  | HDPE |  | 14.8 | [6 empty] | 3399.5 | RHS | 1.65 | Shashiranjan
42 |  | J383 | J382 |  | HDPE |  | 81.3 | [6 empty] | 3480.8 | RHS | 1.65 | Shashiranjan
43 |  | j383 | j243 |  | HDPE |  | 47.5 | [6 empty] | 3528.3 | RHS | 1.65 | Shashiranjan
44 |  | j358 | j201 |  | HDPE |  | 108.7 | [6 empty] | 3637 | RHS | 1.65 | Shashiranjan
45 |  | j166 | j201 |  | HDPE |  | 73.9 | [6 empty] | 3710.9 | LHS | 1 | Shashiranjan
46 |  | j166 | j131 |  | HDPE |  | 93.3 | [6 empty] | 3804.2 | RHS | 1.65 | Shashiranjan
47 |  | j489 | j597 |  | HDPE |  | 58.2 | [6 empty] | 3862.4 | RHS | 1.65 | Shashiranjan
48 |  | j597 | j543 |  | HDPE |  | 43.8 | [6 empty] | 3906.2 | RHS | 1.65 | Shashiranjan
49 |  | j543 | j547 |  | HDPE |  | 121.6 | [6 empty] | 4027.8 | RHS | 1.65 | Shashiranjan
50 |  | j564 | j588 |  | HDPE |  | 97.9 | [6 empty] | 4125.7 | RHS | 1.65 | Shashiranjan
51 |  | j547 | j564 |  | HDPE |  | 53.2 | [6 empty] | 4178.9 | RHS | 1.65 | Shashiranjan
52 |  | j588 | j432 |  | HDPE |  | 162.8 | [6 empty] | 4341.7 | CENTER |  | Shashiranjan
53 |  | j311 | j131 |  | HDPE |  | 295.2 | [6 empty] | 4636.9 | RHS | 1.65 | Shashiranjan | jn711 90equaltee
54 |  | j529 | J530 | BRICK ROAD | HDPE |  | 160 | [6 empty] | 4796.9 | LHS | 1.65 | Shashiranjan | jn712 90equal tee
55 |  | j529 | J530 | B.T CROSSING | HDPE |  | 3.5 | [6 empty] | 4800.4 | LHS | 1.65 | Shashiranjan | jn712 90*75 reducer
56 |  | j529 | J530 |  | HDPE |  | 129.3 | [6 empty] | 4929.7 | LHS | 1.65 | Shashiranjan
57 |  | j395 | j270 |  | HDPE |  | 87.2 | [6 empty] | 5016.9 | LHS | 1.65 | Shashiranjan
58 |  | j650 | j737 | B.T CROSSING | HDPE |  | 3.5 | [6 empty] | 5020.4 | LHS | 1.65 | Shashiranjan
59 |  | j650 | j737 |  | HDPE |  | 141 | [6 empty] | 5161.4 | LHS | 1.65 | Shashiranjan | jn652 90*90*63
60 |  | j737 | j696 |  | HDPE |  | 57.1 | [6 empty] | 5218.5 | LHS | 1.65 | Shashiranjan
61 |  | j194 | j211 |  | HDPE |  | 78.9 | [6 empty] | 5297.4 | LHS | 1.65 | Shashiranjan
62 |  | j211 | j128 |  | HDPE |  | 39.8 | [6 empty] | 5337.2 | LHS | 1.65 | Shashiranjan
63 |  | j128 | j121 |  | HDPE |  | 34.3 | [6 empty] | 5371.5 | LHS | 1.65 | Shashiranjan
64 |  | j121 | j106 |  | HDPE |  | 32.6 | [6 empty] | 5404.1 | LHS | 1.65 | Shashiranjan
65 |  | j106 | j177 |  | HDPE |  | 68.5 | [6 empty] | 5472.6 | LHS | 1.65 | Shashiranjan
66 |  | j397 | j434 |  | HDPE |  | 27.8 | [6 empty] | 5500.4 | LHS | 1.65 | Shashiranjan
67 |  | j397 | j229 |  | HDPE |  | 51.6 | [6 empty] | 5552 | LHS | 1.65 | Shashiranjan
68 |  | j229 | j216 |  | HDPE |  | 102.9 | [6 empty] | 5654.9 | LHS | 1.65 | Shashiranjan
69 |  | j229 | j216 |  | HDPE |  | 2.1 | [6 empty] | 5657 | LHS | 1.65 | Shashiranjan
70 |  | J618 | J632 |  | HDPE |  | 44.3 | [6 empty] | 5701.3 | RHS | 1.65 | Shashiranjan
71 |  | J501 | J618 |  | HDPE |  | 129.9 | [6 empty] | 5831.2 | RHS | 1.65 | Shashiranjan
72 |  | J433 | J434 |  | HDPE |  | 33.9 | [6 empty] | 5865.1 | RHS | 1.65 | Shashiranjan | j201-75*75*63
73 |  | J632 | J618 |  | HDPE |  | 18.1 | [6 empty] | 5883.2 | RHS | 1.65 | Shashiranjan
74 |  | j718 | j218 |  | HDPE |  |  | 36.4 | [5 empty] | 5919.6 | RHS | 1.65 | Shashiranjan
75 |  | j218 | J219 |  | HDPE |  |  | 46.3 | [5 empty] | 5965.9 | RHS | 1.65 | Shashiranjan | j484-110*110*63
76 |  | j564 | j614 |  | HDPE |  |  | 578.2 | [5 empty] | 6544.1 | RHS | 1.65 | Shashiranjan
77 |  | j693 | j603 |  | HDPE |  |  | 10.1 | [5 empty] | 6554.2 | RHS | 1.65 | Shashiranjan
78 |  | j603 | j313 |  | HDPE |  |  | 182.8 | [5 empty] | 6737 | RHS | 1.65 | Shashiranjan | j-131-75*75*63
79 |  | j424 | j194 |  | HDPE |  |  | 68.4 | [5 empty] | 6805.4 | RHS | 1.65 | Shashiranjan
80 |  | j454 | j496 |  | HDPE |  |  | 98.5 | [5 empty] | 6903.9 | RHS | 1.65 | Shashiranjan | j735-75*75*75
81 |  | j495 | j557 |  | HDPE |  |  | 16.3 | [5 empty] | 6920.2 | RHS | 1.65 | Shashiranjan
82 |  | j557 | j508 |  | HDPE |  |  | 38.4 | [5 empty] | 6958.6 | RHS | 1.65 | Shashiranjan
83 |  | j508 | j325 |  | HDPE |  |  | 57.3 | [5 empty] | 7015.9 | LHS | 1.65 | Shashiranjan
84 |  | j650 | j453 |  | HDPE |  |  | 70.1 | [5 empty] | 7086 | LHS | 1.65 | Shashiranjan
85 |  | j672 | j529 |  | HDPE |  |  | 65.4 | [5 empty] | 7151.4 | CENTER |  | Shashiranjan
86 |  | j453 | j529 |  | HDPE |  |  | 6 | [5 empty] | 7157.4 | LHS | 1.65 | Shashiranjan
87 |  | j650 | j633 |  | HDPE |  |  | 8.3 | [5 empty] | 7165.7 | RHS | 1.65 | Shashiranjan
88 |  | j633 | j711 |  | HDPE |  |  | 126.2 | [5 empty] | 7291.9 | CENTER |  | Shashiranjan
89 |  | j711 | j457 | B.T CROSSING | HDPE |  |  | 3.5 | [5 empty] | 7295.4 | CENTER |  | Shashiranjan
90 |  | j711 | j457 |  | HDPE |  |  | 74.6 | [5 empty] | 7370 |  |  | Shashiranjan
91 |  | j711 | j719 |  | HDPE |  |  | 22.7 | [5 empty] | 7392.7 |  |  | Shashiranjan
92 |  | j711 | j719 | B.T CROSSING | HDPE |  |  | 3.5 | [5 empty] | 7396.2 |  |  | Shashiranjan
93 |  | j719 | j652 |  | HDPE |  |  | 59.1 | [5 empty] | 7455.3 |  |  | Shashiranjan
94 |  | j652 | j612 |  | HDPE |  |  | 29.2 | [5 empty] | 7484.5 |  |  | Shashiranjan
95 |  | j612 | j526 |  | HDPE |  |  | 16.8 | [5 empty] | 7501.3 |  |  | Shashiranjan
96 |  | j526 | j538 |  | HDPE |  |  | 13.6 | [5 empty] | 7514.9 |  |  | Shashiranjan
97 |  | j538 | j546 |  | HDPE |  |  | 72.9 | [5 empty] | 7587.8
98 |  | j546 | j614 |  | HDPE |  |  | 89.8 | [5 empty] | 7677.6
99 |  | j400 | j159 |  | HDPE |  |  | 65.1 | [5 empty] | 7742.7
100 |  | j662 | j509 |  | HDPE |  |  | 74.3 | [5 empty] | 7817
101 |  | j696 | j649 |  | HDPE |  |  | 97.5 | [5 empty] | 7914.5
102 |  | j361 | j397 |  | HDPE |  |  | 69.1 | [5 empty] | 7983.6
103 |  | j462 | j394 |  | HDPE |  |  | 46.6 | [5 empty] | 8030.2
104 |  | j313 | j341 |  | HDPE |  |  | 18.2 | [5 empty] | 8048.4
105 |  | j508 | j325 | BRICK ROAD | HDPE |  |  | 58.1 | [5 empty] | 8106.5
106 |  | j243 | j567 |  | HDPE |  |  |  | 1046.1 |  |  |  |  | 9152.6
107 |  | j567 | j544 |  | HDPE |  |  |  | 113.5 |  |  |  |  | 9266.1
108 |  | j544 | j484 |  | HDPE |  |  |  | 43.8 |  |  |  |  | 9309.9
109 |  | j484 | j489 |  | HDPE |  |  |  | 14.1 |  |  |  |  | 9324
110 |  | j589 | j638 |  | HDPE |  |  |  | 79.2 |  |  |  |  | 9403.2
111 |  | j638 | j489 |  | HDPE |  |  |  | 50.3 |  |  |  |  | 9453.5
112 |  | j418 | j372 |  | HDPE |  |  |  | 72.5 |  |  |  |  | 9526
113 |  | j372 | j311 |  | HDPE |  |  |  | 11.1 |  |  |  |  | 9537.1
114 |  | j287 | j589 |  | HDPE |  |  |  | 272.6 |  |  |  |  | 9809.7
115 |  | j194 | j395 |  | HDPE |  |  |  | 98.2 |  |  |  |  | 9907.9
116 |  | j395 | j457 |  | HDPE |  |  |  | 14.1 |  |  |  |  | 9922
117 |  | j567 | j707 |  | HDPE |  |  |  | 168.1 |  |  |  |  | 10090.1
118 |  | j707 | j400 |  | HDPE |  |  |  | 38.2 |  |  |  |  | 10128.3
119 |  | j400 | j620 |  | HDPE |  |  |  | 26.4 |  |  |  |  | 10154.7
120 |  | j662 | j688 |  | HDPE |  |  |  | 587.1 |  |  |  |  | 10741.8
121 |  | j688 | j750 |  | HDPE |  |  |  | 97.3 |  |  |  |  | 10839.1
122 |  | j649 | j640 |  | HDPE |  |  |  | 20.4 |  |  |  |  | 10859.5
123 |  | j640 | j507 |  | HDPE |  |  |  | 89.3 |  |  |  |  | 10948.8
124 |  | j507 | j501 |  | HDPE |  |  |  | 90.7 |  |  |  |  | 11039.5
125 |  | j501 | j548 |  | HDPE |  |  |  | 154.1 |  |  |  |  | 11193.6
126 |  | j548 | J549 |  | HDPE |  |  |  | 32 |  |  |  |  | 11225.6
127 |  | j563 | j427 | INTERLOCKING | HDPE |  |  |  | 72.9 |  |  |  |  | 11298.5
128 |  | j427 | j418 | INTERLOCKING | HDPE |  |  |  | 62.3 |  |  |  |  | 11360.8
129 |  | j311 | j287 |  | HDPE |  |  |  | 21.2 |  |  |  |  | 11382
130 |  | j750 | j746 |  | HDPE | [7 empty] | 440 | 11822
131 |  | j750 | J749 |  | HDPE | [7 empty] | 300 | 12122
132 |  | j2 | j7 |  | HDPE |  |  | 52.7 | [5 empty] | 12174.7
133 | [13 empty] | 12174.7
Work Done Qty In ( Rmt ) : | [5 empty] | 3115 | 2768.2 | 2276 | 3275.5 | 0 | 0 | 0 | 740 | [6 empty] | 12174.7
With Held Quantity ( In RMT ) | [19 empty] | 0
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 3115 | 2768.2 | 2276 | 3275.5 | 0 | 0 | 0 | 740 | [6 empty] | 12174.7
Prepared By Site Engineer ( Sr. Eng/AM-SMX ) ( AM-PMX ) Project Incharge

## Saray Jammuvaril (hidden)
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Saray Jammuvaril (Mangura) Pipe Laying & Gap Closing Measurement Sheet
Name of the Contractor : Kyathi Enterprises
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [8 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | 200mm | DI 250mm
1 |  | j18 | j9 |  | HDPE | 660.6 | [8 empty] | 660.6
2 |  | j17 | j39 |  | HDPE | 201.4 | [8 empty] | 862
3 |  | j45 | j25 |  | HDPE | 49 | [8 empty] | 911
4 |  | j20 | j31 |  | HDPE | 40 | [8 empty] | 951
5 |  | j1 | j6 |  | HDPE | 61 | [8 empty] | 1012
6 |  | j163 | j103 |  | HDPE | 184.3 | [8 empty] | 1196.3
7 |  | j163 | j134 |  | HDPE | 78.5 | [8 empty] | 1274.8
8 |  | j134 | j142 |  | HDPE | 142 | [8 empty] | 1416.8 |  |  |  |  | Gap Balance
9 |  | j51 | j201 |  | HDPE | 235.3 | [8 empty] | 1652.1 |  |  |  |  | Gap Balance
10 |  | j101 | j258 |  | HDPE | 358.2 | [8 empty] | 2010.3 |  |  |  |  | Gap Balance
11 |  | J258 | J280 |  | HDPE | 221.9 | [8 empty] | 2232.2 |  |  |  |  | Gap Balance
12 |  | J275 | J269 |  | HDPE | 48 | [8 empty] | 2280.2
13 |  | J276 | J263 |  | HDPE | 91 | [8 empty] | 2371.2
14 |  | J44 | J76 |  | HDPE | 200 | [8 empty] | 2571.2
15 |  | J76 | J93 |  | HDPE | 40 | [8 empty] | 2611.2
16 |  | J76 | J84 |  | HDPE | 167 | [8 empty] | 2778.2
17 |  | J91 | J106 |  | HDPE | 230 | [8 empty] | 3008.2
18 |  | J20 | J1 |  | HDPE |  | 205.5 | [7 empty] | 3213.7
19 |  | J20 | J1 | B.T | HDPE |  | 3.5 | [7 empty] | 3217.2
20 |  | J33 | J42 |  | HDPE |  | 177.9 | [7 empty] | 3395.1
21 |  | J42 | J27 |  | HDPE |  | 89.8 | [7 empty] | 3484.9
22 |  | J92 | J33 |  | HDPE |  | 220.3 | [7 empty] | 3705.2
23 |  | j109 | j98 |  | HDPE |  | 134 | [7 empty] | 3839.2
24 |  | j98 | j116 |  | HDPE |  | 270 | [7 empty] | 4109.2
25 |  | j45 | j116 |  | HDPE |  | 123 | [7 empty] | 4232.2
26 |  | j45 | j20 |  | HDPE |  | 190 | [7 empty] | 4422.2
27 |  | j46 | j34 |  | HDPE |  | 105.6 | [7 empty] | 4527.8
28 |  | j26 | j54 |  | HDPE |  | 117 | [7 empty] | 4644.8
29 |  | j92 | j51 |  | HDPE |  | 291.7 | [7 empty] | 4936.5
30 |  | j18 | j17 |  | HDPE |  |  | 71.1 | [6 empty] | 5007.6
31 |  | j109 | j107 |  | HDPE |  |  | 257.2 | [6 empty] | 5264.8
32 |  | j8 | j46 |  | HDPE |  |  | 93.2 | [6 empty] | 5358
33 |  | J33 | J27 |  | HDPE |  |  | 62.1 | [6 empty] | 5420.1
34 |  | j17 | j19 |  | HDPE |  |  |  | 377.9 | [5 empty] | 5798
35 |  | j17 | j19 | BRICK ROAD | HDPE |  |  |  | 4.5 | [5 empty] | 5802.5
36 |  | j19 | j10 |  | HDPE |  |  |  | 43 | [5 empty] | 5845.5
37 |  | j19 | j10 | B.T | HDPE |  |  |  | 5 | [5 empty] | 5850.5
38 |  | j10 | j109 |  | HDPE |  |  |  | 463.7 | [5 empty] | 6314.2
39 |  | j10 | j109 | B.T | HDPE |  |  |  | 3.5 | [5 empty] | 6317.7
40 |  | j1 | j10 |  | HDPE |  |  |  | 315 | [5 empty] | 6632.7
41 |  | j19 | j21 |  | HDPE |  |  |  | 51.3 | [5 empty] | 6684
42 |  | J27 | J21 |  | HDPE |  |  |  | 226.2 | [5 empty] | 6910.2
43 |  | J38 | J40 |  | HDPE |  |  |  | 100 | [5 empty] | 7010.2
44 |  | J40 | J74 |  | HDPE |  |  |  | 150 | [5 empty] | 7160.2
45 |  | j4 | j281 |  | HDPE | [5 empty] | 117.8 |  |  |  | 7278
46 |  | j281 | j8 |  | HDPE | [5 empty] | 26.3 |  |  |  | 7304.3
47 |  | j70 | j92 |  | HDPE | [5 empty] | 580.2 |  |  |  | 7884.5
48 |  | j57 | j101 |  | HDPE | [5 empty] | 582.9 |  |  |  | 8467.4
49 |  | j101 | j2 |  | HDPE | [5 empty] | 380.6 |  |  |  | 8848
50 |  | J9 | j13 |  | HDPE | [5 empty] | 106.9 |  |  |  | 8954.9
51 |  | J260 | J261 |  | HDPE | [5 empty] | 180 |  |  |  | 9134.9
52 |  | J260 | J258 |  | HDPE | [5 empty] | 15 |  |  |  | 9149.9
53 |  | J172 | J212 |  | HDPE | [5 empty] | 156 |  |  |  | 9305.9
54 |  | J173 | J212 |  | HDPE | [5 empty] | 120 |  |  |  | 9425.9
55 |  | J58 | J43 |  | HDPE | [5 empty] | 200 |  |  |  | 9625.9
56 |  | j8 | j9 |  | HDPE | [6 empty] | 141.3 |  |  | 9767.2
57 |  | j9 | j70 |  | HDPE | [6 empty] | 322.4 |  |  | 10089.6
58 |  | j90 | j89 |  | HDPE | [6 empty] | 12 |  |  | 10101.6
59 |  | J150 | J259 |  | HDPE | [6 empty] | 62 |  |  | 10163.6
60 |  | J259 | J248 |  | HDPE | [6 empty] | 18 |  |  | 10181.6
61 |  | J248 | J264 |  | HDPE | [6 empty] | 202 |  |  | 10383.6
62 |  | J264 | J272 |  | HDPE | [6 empty] | 44 |  |  | 10427.6
63 |  | J272 | J276 |  | HDPE | [6 empty] | 38 |  |  | 10465.6
64 |  | J264 | J260 |  | HDPE | [6 empty] | 47 |  |  | 10512.6
65 |  |  |  |  | HDPE | [9 empty] | 10512.6
66 |  |  |  |  | HDPE | [9 empty] | 10512.6
[5 empty] | HDPE | [9 empty] | 10512.6
Work Done Qty In ( Rmt ) : | [5 empty] | 3008.2 | 1928.3 | 483.6 | 1740.1 |  | 2465.7 | 886.7 | 0 | 0 | [6 empty] | 10512.6
With Held 10 % of the Total Quantity ( In RMT ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14.7 | 0 | 0 | [6 empty] | 14.7
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 3008.2 | 1928.3 | 483.6 | 1740.1 |  | 2465.7 | 872 | 0 | 0 | [6 empty] | 10497.9
[5 empty] | WO Qtys | 4654 | 3234 | 1867 | 2197 | 0 | 3213 | 872
Prepared By Site Engineer ( Sr. Eng/AM-SMX ) ( AM-PMX ) Project Incharge

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
#REF! | [11 empty] | #REF!
Sl NO | Description | Units | Atrasand & Parasupur |  | Saray Jamuvari |  | Total |  | Balance Qty | Avilable at Site |  | Remarks
|  |  | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty |  |  | SAP Entry |  |  | Balance In Sap
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2800 | 3115 | 2600 | 3008.2 | 15250 | 13480.2 | 1769.8 |  | 5358.2 | 8122 |  | 8122 | done | 5987
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3300 | 2768.2 | 2100 | 1928.3 | 6636 | 4696.5 | 1939.5 |  | 4537.3 | 159.2 |  | 159.2 |  | 750
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2400 | 2276 | 600 | 483.6 | 4200 | 4124.6 | 75.4 |  | 2759.6 | 1365 |  | 1365
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3050 | 3275.5 | 1475 | 1740.1 | 5950 | 6052 | -102 |  | 4758.1 | 1293.9 |  | 1293.9 |  | 600
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 0 |  | 0 | 588 | 485 | 103 |  | 0 | 485 |  | 485
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 0 | 1800 | 2465.7 | 3936 | 2912.7 | 1023.3 |  | 2465.7 | 447 |  | 447
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 0 | 600 | 886.7 | 1020 | 886.7 | 133.3 |  | 886.7 | 0 |  | 0
| 250DI K-7 | Rmt | 840 | 740 |  | 0 | 840 | 740 | 100 |  |  | 740 |  | 740 |  | 300
| Total Qty In ( Rmt ) = | [5 empty] | 38420 | 33377.7 | 5042.3
2 | Specials :-
Equal Tee
| 63mm | No's | 19 | 1 | 8 |  | 27 | 1 | 26 |  | 1 | 0 |  | 0 |  | 20 | 13
| 75mm | No's | 10 | 1 |  |  | 10 | 1 | 9 |  | 1 | 0 |  | 0
| 90mm | No's | 7 | 3 | 1 |  | 10 | 3 | 7 |  | 3 | 0 |  | 0 |  | 2 | 2
| 140 | [5 empty] | 2
| Total Qty In ( No's ) = | [5 empty] | 47 | 5 | 42
Branch TEE
| 75 mm X 63 mm | No's | 10 | 7 | 4 | 3 | 14 | 14 | 0 |  | 14 | 0 |  | 0 |  | 2 | 1
| 90 mm X 63 mm | No's | 18 | 3 |  |  | 19 | 3 | 16 |  | 3 | 0 |  | 0
| 90 mm X 75 mm | No's | 15 |  |  |  | 15 | 0 | 15 |  |  | 0 |  | 0
| 110 mm X 63 mm | No's | 12 | 11 | 2 |  | 15 | 11 | 4 |  | 11 | 0 | J-7, J-13, J-32,J-2 | 0 |  | 1 | 1
| 110 mm X 75 mm | No's | 2 | 1 | 8 | 3 | 12 | 4 | 8 |  | 4 | 0 |  | 0 |  | 1 | 1
| 110mm X 90 mm | No's | 6 | 4 |  |  | 6 | 6 | 0 |  | 6 | 0 | J-68 | 0
| 140mm X 63 mm | No's |  |  | 3 | 1 | 3 | 1 | 2 |  | 1 | 0 | J-38 | 0
| 140mm X 75 mm | No's |  |  | 3 | 1 | 3 | 1 | 2 |  | 1 | 0 | J-67 | 0
| 140mm X 90 mm | No's |  |  | 2 | 1 | 2 | 1 | 1 |  |  | 1 |  | 1
| 160mm X 63 mm | No's |  |  | 2 |  | 2 | 0 | 2 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 89 | 41 | 48
4-Way Tee
| 63mm | No's | 1 |  |  |  | 1 | 0 | 1 | [6 empty] | 20 | 13
| Total Qty In ( No's ) = | [5 empty] | 1 | 0 | 1
Reducers
| 75mm X 63 mm | No's | 21 | 3 | 5 | 1 | 26 | 10 | 16 |  | 10 | 0 | J-12 | 0 |  | 3 | 3
| 90mm X 63 mm | No's | 4 | 2 | 2 |  | 18 | 3 | 15 |  | 3 | 0 | J-7 | 0 |  | 2 | 2
| 90mm X 75 mm | No's | 14 |  |  |  | 24 | 0 | 24 |  |  | 0 |  | 0 |  | 2 | 2
| 110 mm X 75 mm | No's | 2 |  |  |  | 2 | 0 | 2 |  |  | 0 | J-83,J-101 | 0 |  | 1
| 110 mm X 63 mm | No's |  |  |  |  | 5 | 0 | 5 |  |  | 0 |  | 0
| 110 mm X 90 mm | No's |  |  | 1 |  | 11 | 0 | 11 |  |  | 0 | J-130 | 0
| 125*63 | [5 empty] | 2
| 140mm X 75 mm | No's |  |  | 6 | 1 | 6 | 1 | 5 |  | 1 | 0 |  | 0
| 140mm*63 | No's |  |  |  |  | 4
| 140*90 | [5 empty] | 1
| 140*125 | [5 empty] | 1
| 160mm X 90 mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 160mm X 140mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 100 | 14 | 78
| Bends | [5 empty] | 0 | 0
| 90mm ( 45 Deg ) | [5 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
| 140mm ( 45 Deg ) | [5 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 0 | 0 | 0
| End Caps | [10 empty] | 0 |  | 0
| 63mm | No's | 27 |  |  |  | 47 | 0 | 47 |  |  | 0 |  | 0 |  | 10 | 1
| Total Qty In ( No's ) = | [5 empty] | 47 | 0 | 47
2 | FHTC
1 | G.I PIPE | MTRS |  |  |  |  | 145 | 52 | 93
2 | MDPE PIPE 20MM COIL-500MTRS | MTRS |  |  |  |  | 500 | 325 | 175
3 | PPCLamps saddle-63*1/2" | nos |  |  |  |  | 110 | 26 | 84
4 | PPCLamps saddle-75*1/2" | nos |  |  |  |  | 10 | 10 | 0
5 | PPCLamps saddle-90*1/2" | nos |  |  |  |  | 10 | 6 | 4
6 | PPCLamps saddle-110*1/2" | nos |  |  |  |  | 10 | 10 | 0
7 | PPCLamps saddle-125*1/2" | nos |  |  |  |  | 0 |  | 0
8 | PPCLamps saddle-140*1/2" | nos |  |  |  |  | 0 |  | 0
9 | PPCLamps saddle-160*1/2" | nos |  |  |  |  | 0 |  | 0
10 | PPCLamps saddle-200*1/2" | nos |  |  |  |  | 0 |  | 0
11 | pp comp fm theard adapter-20mm*1/2" | nos |  |  |  |  | 95 | 52 | 43
12 | pp comp fm theard elb off taken-20mm*1/2" | nos |  |  |  |  | 52 | 52 | 0
13 | threaded fcv-1/2"(15nb) | nos |  |  |  |  | 80 | 52 | 28
14 | GI elbow | nos |  |  |  |  | 340 | 104 | 236
15 | GI socket | nos |  |  |  |  | 195 | 52 | 143
16 | saddle g.i pipe-105mm(clamps) | nos |  |  |  |  | 130 |  | 130
17 | 15mm nipple-0.3mm | nos |  |  |  |  | 195 | 52 | 143
18 | 15mm nipple-0.5mm | nos |  |  |  |  | 195 | 52 | 143
19 | bib cock ptmt(taps) | nos |  |  |  |  | 165 | 52 | 113
20 | teflon tape | nos |  |  |  |  | 20 |  | 20
21 | GI nails | nos |  |  |  |  | 220 |  | 220
Prepared by Checked By Stores DM PMX Project Incharge

## SARSIDHI
Block |  | Mangraura |  |  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
GP |  | sarsidhi |  |  |  | 63 | 12324 | 5850 | 5588 |  |  | -262
Agency Name/ Work Order No |  | khayati enterprises |  |  |  | 90 | 1649 | 1200 | 954
63MM | [5 empty] | 110 | 1167 | 1100 | 1202
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent | 125
1 | 2023-06-08 | 650 |  |  | 20652 | 160
2 | 2023-06-19 | 650 |  |  | 20657
3 | 2023-06-21 | 350 |  |  | 20658
4 | 2023-09-23 | 1300 |  |  | 20672
5 | 2023-09-26 | 1300 |  |  | 20673
6 | 2023-09-28 | 650 |  |  | 20671
7 | 2023-10-06 | 650 |  |  | 20674
8 | 2023-10-09 | 300 |  |  | 20675 | Specials |  | Specification | Issue | Laid | Balance Against Issue | Remarks | INDENT
[6 empty] | Equal TEE |  | 63mm | 10 |  |  |  | 20671
75mm
| TOTAL | 5850 | [5 empty] | 90mm | 2 |  |  |  | 20672
75MM | [7 empty] | 110mm | 3 |  |  |  | 20671
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 125mm
1 | [7 empty] | 140mm
2 | [7 empty] | 160mm
3 | [7 empty] | 200mm
3 | [7 empty] | 250mm
[6 empty] | Branch TEE |  | 63mm X 50mm
75mm X 50mm
90 mm X 50 mm
110mm X 50mm
125mm X 50mm
140mm X 50mm
160mm X 50mm
| TOTAL | 0 | [5 empty] | 75 mm X 63 mm
90MM | [7 empty] | 90 mm X 63 mm | 5 |  |  |  | 20672
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 90 mm X 75 mm
1 | 2023-06-21 | 200 |  |  | 20658 |  |  | 110mm X 63 mm
2 | 2023-06-23 | 400 | [5 empty] | 110mm X 75 mm
3 | 2023-09-28 | 300 |  |  | 20671 |  |  | 110mm X 90 mm
4 | 2023-10-06 | 300 |  |  | 20674 |  |  | 125mm X 63 mm
125mm X75 mm
125mm X90 mm
125mm X 110mm
140mm X 63 mm
140mm X 75 mm
140mm X 90 mm
| TOTAL | 1200 | [5 empty] | 140mm X 110mm
110MM | [7 empty] | 140mm X 125 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 160mm X 63 mm
1 | [7 empty] | 160mm X 75 mm
2 | 2023-06-12 | 300 |  |  | 20653 |  |  | 160mm X 90 mm
3 | 2023-06-13 | 300 |  |  | 20654 |  |  | 160mm X 110 mm
4 | 2023-06-17 | 200 |  |  | 20655 |  |  | 160mm X 125 mm
5 | 2023-06-18 | 200 |  |  | 20656 |  |  | 160mm X 140 mm
6 | 2023-06-19 | 100 |  |  | 20657 |  |  | 200mm X 63 mm
7 | [7 empty] | 200mm X 75 mm
8 | [7 empty] | 200mm X 90 mm
200mm X 110 mm
| TOTAL | 1100 | [5 empty] | 200mm X 125 mm
200mm X 140 mm
125MM | [7 empty] | 200mm X 160 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 250mm X 63 mm
1 | 2023-10-12 | 588 |  |  | 20676 |  |  | 250mm X 75 mm
250mm X 90 mm
250mm X 110 mm
250mm X 140 mm
250mm X 160 mm
[6 empty] | 4-Way TEE |  | 63mm
75mm
| TOTAL | 588 | [5 empty] | 90mm
140MM | [7 empty] | 110mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 125mm
1 | 2023-10-12 | 456 |  |  | 20676 |  |  | 140mm
160mm
200mm
250mm
[6 empty] | Reducer |  | 75mm X 63 mm
[8 empty] | 90mm X 63 mm | 4 |  |  |  | 20673 ,20671
90mm X 75 mm
| TOTAL | 456 | [5 empty] | 110 mm X 63 mm
160MM | [7 empty] | 110 mm X 75 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  | 110 mm X 90 mm | 2 |  |  |  | 20671
1 | [7 empty] | 125 mm X 63 mm
125 mm X 75 mm
125 mm X 90 mm
125 mm X 110 mm
140mm X 63 mm
140mm X 75 mm
140mm X 90 mm
| TOTAL | 0 | [5 empty] | 140mm X 110mm
140mm X 125mm
160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110mm
160mm X 125mm
160mm X 140mm
200mm X 63mm
200mm X 75mm
200mm X 90mm
200mm X 110mm
200mm X 125mm
200mm X 140mm
200mm X 160mm
250mm X 63mm
250mm X 75mm
250mm X 110mm
250mm X 140mm
250mm X 160mm
250mm X 200mm
[6 empty] | End Caps |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
[6 empty] | Bends | 63mm | 90 Deg
45 Deg
[7 empty] | 75mm | 90 Deg
45 Deg
[7 empty] | 90mm | 90 Deg
45 Deg
[7 empty] | 110mm | 90 Deg
45 Deg
[7 empty] | 125mm | 90 Deg
45 Deg
[7 empty] | 140mm | 90 Deg
45 Deg
[7 empty] | 160mm | 90 Deg
45 Deg
[7 empty] | 200mm | 90 Deg
45 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
[6 empty] | Stubbends |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | MS Flanges |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[6 empty] | Air Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Sluice Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[6 empty] | Scour Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
DI Specials
[6 empty] | DI Bends | 200mm | 90 Deg
45 Deg
22 Deg
[7 empty] | 250mm | 90 Deg
45 Deg
22 Deg
[6 empty] | DI Branch TEE |  | 200mmx80mm
200mmx100mm
200mmx150mm
250mmx80mm
250mmx150mm
250mmx200mm
[6 empty] | DI Reducer Both Socket |  | 200mmx80mm
200mmx100mm
200mmx150mm
[6 empty] | DI Reducer Double Flanged |  | 150mmx100mm
200mmx100mm
200mmx150mm
250mmx150mm
250mmx200mm
[6 empty] | DI Flange Socket |  | 200mm
[6 empty] | DI Tail Piece 0.3m length |  | 80mm
100mm
150mm
200mm
250mm
[6 empty] | DI Equal TEE All Side Socket |  | 200mm
250mm
[6 empty] | DI 4 Way |  | 200mm
250mm
[6 empty] | Nuts & Bolts |  | Length:140mm, Dia:16mm
[6 empty] | Packing Sheet |  | 3mm Thick

## HT_Saray Jammuvaril (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Hydro Testing Report for Saray Jammuvaril (Mangraura Block)
#REF!
SL. NO. | Testing Date | Material of Pipe | ID (MM) | Dia of the Pipe | Start Node | End Node | Length | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Remarks
1 | 2023-05-20 | HDPE | 81.1 | 90 | J18 | J17 | 71.1 | 5.5KG/CM2 | 3 | 1 | 4
2 | 2023-05-20 | HDPE | 99.3 | 110 | J17 | J19 | 382.4 | 5.5KG/CM2 | 3 | 1 | 4
3 | 2023-05-20 | HDPE | 56.7 | 63 | J18 | J9 | 660.2 | 5.5KG/CM2 | 3 | 1 | 4
4 | 2023-05-20 | HDPE | 56.7 | 63 | J17 | J39 | 201.4 | 5.5KG/CM2 | 3 | 1 | 4
5 | 2023-05-20 | HDPE | 99.3 | 110 | J19 | J10 | 48 | 5.5KG/CM2 | 3 | 1 | 4
6 | 2023-05-20 | HDPE | 99.3 | 110 | J10 | J109 | 467.2 | 5.5KG/CM2 | 3 | 1 | 4
7 | 2023-05-20 | HDPE | 67.4 | 75 | J109 | J98 | 134 | 5.5KG/CM2 | 3 | 1 | 4
8 | 2023-05-20 | HDPE | 67.4 | 75 | J98 | J116 | 270 | 5.5KG/CM2 | 3 | 1 | 4
9 | 2023-05-20 | HDPE | 56.7 | 63 | J45 | J25 | 49 | 5.5KG/CM2 | 3 | 1 | 4
10 | 2023-05-20 | HDPE | 67.4 | 75 | J45 | J116 | 123 | 5.5KG/CM2 | 3 | 1 | 4
11 | 2023-05-20 | HDPE | 67.4 | 75 | J45 | J20 | 190 | 5.5KG/CM2 | 3 | 1 | 4
12 | 2023-05-20 | HDPE | 56.7 | 63 | J20 | J31 | 40 | 5.5KG/CM2 | 3 | 1 | 4
13 | 2023-05-20 | HDPE | 67.4 | 75 | J22 | J1 | 209 | 5.5KG/CM2 | 3 | 1 | 4
14 | 2023-05-20 | HDPE | 56.7 | 63 | J1 | J6 | 61 | 5.5KG/CM2 | 3 | 1 | 4
15 | 2023-05-20 | HDPE | 99.3 | 110 | J1 | J10 | 315 | 5.5KG/CM2 | 3 | 1 | 4
16 | 2023-05-20 | HDPE | 81.1 | 90 | J109 | J107 | 257.2 | 5.5KG/CM2 | 3 | 1 | 4
17 | 2023-05-20 | HDPE | 56.7 | 63 | J163 | J103 | 184.3 | 5.5KG/CM2 | 3 | 1 | 4
18 | 2023-05-20 | HDPE | 56.7 | 63 | J163 | J134 | 78.5 | 5.5KG/CM2 | 3 | 1 | 4
19 | 2023-05-20 | HDPE | 56.7 | 63 | J134 | J142 | 142 | 5.5KG/CM2 | 3 | 1 | 4
20 | 2023-05-20 | HDPE | 99.3 | 110 | J19 | J21 | 51.3 | 5.5KG/CM2 | 3 | 1 | 4
21 | 2023-05-25 | HDPE | 126.3 | 140 | J4 | J281 | 117.8 | 5.5KG/CM2 | 3 | 1 | 4
22 | 2023-05-25 | HDPE | 126.3 | 140 | J281 | J8 | 26.3 | 5.5KG/CM2 | 3 | 1 | 4
23 | 2023-05-25 | HDPE | 81.1 | 90 | J8 | J46 | 93.2 | 5.5KG/CM2 | 3 | 1 | 4
24 | 2023-05-25 | HDPE | 67.4 | 75 | J46 | J34 | 105.6 | 5.5KG/CM2 | 3 | 1 | 4
25 | 2023-05-25 | HDPE | 144.4 | 160 | J8 | J9 | 141.3 | 5.5KG/CM2 | 3 | 1 | 4
26 | 2023-05-25 | HDPE | 144.4 | 160 | J9 | J70 | 322.4 | 5.5KG/CM2 | 3 | 1 | 4
27 | 2023-05-25 | HDPE | 126.3 | 140 | J9 | J13 | 106.9 | 5.5KG/CM2 | 3 | 1 | 4
28 | 2023-05-25 | HDPE | 144.4 | 160 | J72 | J89 | 12 | 5.5KG/CM2 | 3 | 1 | 4
29 | 2023-05-25 | HDPE | 126.3 | 140 | J72 | J92 | 580.2 | 5.5KG/CM2 | 3 | 1 | 4
30 | 2023-05-25 | HDPE | 67.4 | 75 | J92 | J51 | 290.7 | 5.5KG/CM2 | 3 | 1 | 4
31 | 2023-05-25 | HDPE | 56.7 | 63 | J51 | J201 | 235.3 | 5.5KG/CM2 | 3 | 1 | 4
32 | 2023-05-25 | HDPE | 126.3 | 140 | J51 | J101 | 582.9 | 5.5KG/CM2 | 3 | 1 | 4
33 | 2023-05-25 | HDPE | 56.7 | 63 | J101 | J258 | 358.2 | 5.5KG/CM2 | 3 | 1 | 4
34 | 2023-05-25 | HDPE | 126.3 | 140 | J101 | J2 | 381.6 | 5.5KG/CM2 | 3 | 1 | 4
35 | 2023-05-25 | HDPE | 56.7 | 63 | J258 | J280 | 221.9 | 5.5KG/CM2 | 3 | 1 | 4
36 | 2023-05-25 | HDPE | 67.4 | 75 | J92 | J33 | 220.3 | 5.5KG/CM2 | 3 | 1 | 4
37 | 2023-05-25 | HDPE | 81.1 | 90 | J33 | J27 | 62.1 | 5.5KG/CM2 | 3 | 1 | 4
38 | 2023-05-25 | HDPE | 67.4 | 75 | J33 | J42 | 177.9 | 5.5KG/CM2 | 3 | 1 | 4
39 | 2023-05-25 | HDPE | 67.4 | 75 | J42 | J27 | 89.8 | 5.5KG/CM2 | 3 | 1 | 4
40 | 2023-05-25 | HDPE | 99.3 | 110 | J27 | J21 | 226.2 | 5.5KG/CM2 | 3 | 1 | 4
41 | 2023-05-25 | HDPE | 67.4 | 75 | J26 | J34 | 117.7 | 5.5KG/CM2 | 3 | 1 | 4
42 | 2023-05-10 | HDPE | 56.7 | 63 | j215 | j269 | 48 | 6KG/CM2 | 3 | 1 | 4
43 | 2023-05-10 | HDPE | 56.7 | 63 | j276 | j263 | 91 | 6KG/CM2 | 3 | 1 | 4
44 | 2023-05-10 | HDPE | 144.4 | 160 | j150 | j259 | 62 | 6KG/CM2 | 3 | 1 | 4
45 | 2023-05-10 | HDPE | 144.4 | 160 | j259 | j248 | 18 | 6KG/CM2 | 3 | 1 | 4
46 | 2023-05-10 | HDPE | 144.4 | 160 | j248 | j264 | 202 | 6KG/CM2 | 3 | 1 | 4
47 | 2023-05-10 | HDPE | 144.4 | 160 | j264 | j272 | 44 | 6KG/CM2 | 3 | 1 | 4
48 | 2023-05-10 | HDPE | 144.4 | 160 | j272 | j276 | 38 | 6KG/CM2 | 3 | 1 | 4
49 | 2023-05-10 | HDPE | 144.4 | 160 | j264 | j260 | 47 | 6KG/CM2 | 3 | 1 | 4
50 | 2023-05-10 | HDPE | 126.3 | 140 | j260 | j261 | 180 | 6KG/CM2 | 3 | 1 | 4
51 | 2023-05-10 | HDPE | 126.3 | 140 | j260 | j258 | 15 | 6KG/CM2 | 3 | 1 | 4
52 | 2023-05-10 | HDPE | 99.3 | 110 | j38 | j540 | 100 | 6KG/CM2 | 3 | 1 | 4
53 | 2023-05-10 | HDPE | 99.3 | 110 | j40 | j74 | 150 | 6KG/CM2 | 3 | 1 | 4
54 | 2023-05-10 | HDPE | 67.4 | 75 | j46 | j26 | 15 | 6KG/CM2 | 3 | 1 | 4
55 | 2023-05-10 | HDPE | 99.3 | 110 | j40 | j74 | 30 | 6KG/CM2 | 3 | 1 | 4
56 | 2023-05-10 | HDPE | 56.7 | 63 | j44 | j76 | 200 | 6KG/CM2 | 3 | 1 | 4
57 | 2023-05-10 | HDPE | 56.7 | 63 | j76 | j93 | 40 | 6KG/CM2 | 3 | 1 | 4
58 | 2023-05-10 | HDPE | 56.7 | 63 | j76 | j84 | 167 | 6KG/CM2 | 3 | 1 | 4
59 | 2023-05-10 | HDPE | 56.7 | 63 | j91 | j106 | 230 | 6KG/CM2 | 3 | 1 | 4
60 | 2023-05-10 | HDPE | 126.3 | 140 | j173 | j212 | 156 | 6KG/CM2 | 3 | 1 | 4
61 | 2023-05-10 | HDPE | 126.3 | 140 | j173 | j212 | 120 | 6KG/CM2 | 3 | 1 | 4
62 | 2023-05-10 | HDPE | 126.3 | 140 | j58 | j43 | 200 | 6KG/CM2 | 3 | 1 | 4
63
42
Total Length | [6 empty] | 10557.9
Abstract
[6 empty] | Dia | Length
[6 empty] | 63 | 3007.8
[6 empty] | 75 | 1943
[6 empty] | 90 | 483.6
[6 empty] | 110 | 1770.1
[6 empty] | 125 | 0
[6 empty] | 140 | 2466.7
[6 empty] | 160 | 886.7
[6 empty] | Total | 10557.9
Prepared By Site Engineer ( Sr.Eng/AM-SMX ) ( AM-PMX ) Project Incharge

## Sarsidih (Mangraura) (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Sarsidih (Mangura) Pipe Laying Measurement Sheet
Name of the Contractor : Kyathi Enterprises
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [8 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | 200mm | DI 250mm
1 | 2023-06-05 | J8 | J9 | k.c | hdpe | 200 | [8 empty] | 200
2 | 2023-06-05 | J8 | J9 | k.c | hdpe | 100 | [8 empty] | 300
3 | 2023-06-06 | J8 | J25 | k.c | hdpe | 200 | [8 empty] | 500
4 | 2023-06-06 | j8 | j4 | k.c | hdpe | 120 | [8 empty] | 620
5 | 2023-06-06 | j4 | j5 | k.c | hdpe | 80 | [8 empty] | 700
6 | 2023-06-07 | j4 | j5 | k.c | hdpe | 34 | [8 empty] | 734
7 | 2023-06-07 | j4 | j1 | k.c | hdpe | 126 | [8 empty] | 860
8 | 2023-06-08 | j4 | j1 | k.c | hdpe | 53 | [8 empty] | 913 |  |  |  |  | Gap Balance
9 | 2023-06-09 | j25 | j29 | k.c | hdpe | 63 | [8 empty] | 976 |  |  |  |  | Gap Balance
10 | 2023-06-11 | j25 | j29 | k.c | hdpe | 154 | [8 empty] | 1130 |  |  |  |  | Gap Balance
11 | 2023-06-11 | j29 | j31 | k.c | hdpe | 119 | [8 empty] | 1249 |  |  |  |  | Gap Balance
12 | 2023-06-11 | j31 | j32 | k.c | hdpe | 20 | [8 empty] | 1269
13 | 2023-06-11 | j32 | j36 | k.c | hdpe | 36 | [8 empty] | 1305
14 | 2023-06-11 | j50 | j48 | k.c | hdpe | 114 | [8 empty] | 1419
15 | 2023-06-12 | j51 | j55 | k.c | hdpe |  |  |  | 100 | [5 empty] | 1519
16 | 2023-06-12 | j55 | j67 | k.c | hdpe |  |  |  | 150 | [5 empty] | 1669
17 | 2023-06-13 | j55 | j67 | k.c | hdpe |  |  |  | 135 | [5 empty] | 1804
18 | 2023-06-13 | j67 | j77 | k.c | hdpe |  |  |  | 65 | [5 empty] | 1869
19 | 2023-06-14 | j67 | j77 | k.c | hdpe |  |  |  | 100 | [5 empty] | 1969
20 | 2023-06-14 | j67 | j75 | k.c | hdpe |  |  | 50 | [6 empty] | 2019
21 | 2023-06-15 | J77 | J106 | k.c | hdpe |  |  |  | 62 | [5 empty] | 2081
22 | 2023-06-15 | J67 | J75 | k.c | hdpe |  |  | 69 | [6 empty] | 2150
23 | 2023-06-16 | j77 | j106 | k.c | hdpe |  |  |  | 100 | [5 empty] | 2250
24 | 2023-06-16 | j77 | j78 | k.c | hdpe | 20 | [8 empty] | 2270
25 | 2023-06-17 | j77 | j106 | k.c | hdpe |  |  |  | 100 | [5 empty] | 2370
26 | 2023-06-18 | j77 | j106 | k.c | hdpe |  |  |  | 260 | [5 empty] | 2630
27 | 2023-06-19 | j77 | j106 | k.c | hdpe |  |  |  | 28 | [5 empty] | 2658
28 | 2023-06-19 | j106 | j107 | k.c | hdpe | 295 | [8 empty] | 2953
29 | 2023-06-20 | j77 | j78 | k.c | hdpe | 80 | [8 empty] | 3033
30 | 2023-06-20 | j78 | j80 | k.c | hdpe | 30 | [8 empty] | 3063
31 | 2023-06-20 | j80 | j105 | k.c | hdpe | 155 | [8 empty] | 3218
32 | 2023-06-21 | j80 | j105 | k.c | hdpe | 161 | [8 empty] | 3379
33 | 2023-06-21 | j80 | j76 | k.c | hdpe | 62 | [8 empty] | 3441
34 | 2023-06-21 | j76 | j75 | k.c | hdpe |  |  | 80 | [6 empty] | 3521
35 | 2023-06-22 | j67 | j75 | k.c | hdpe |  |  | 120 | [6 empty] | 3641
36 | 2023-06-22 | j75 | j59 | k.c | hdpe |  |  | 80 | [6 empty] | 3721
37 | 2023-06-23 | j59 | j57 | k.c | hdpe |  |  | 76 | [6 empty] | 3797
38 | 2023-06-23 | j59 | j60 | k.c | hdpe | 6 | [8 empty] | 3803
39 | 2023-06-23 | j57 | j58 | k.c | hdpe | 46 | [8 empty] | 3849
40 | 2023-06-23 | j57 | j54 | k.c | hdpe |  |  | 74 | [6 empty] | 3923
41 | 2023-06-25 | J105 | J116 | k.c | hdpe | 158 | [8 empty] | 4081
42 | 2023-06-25 | J80 | J105 | k.c | hdpe | 30 | [8 empty] | 4111
43 | 2023-06-25 | J105 | J103 | k.c | hdpe | 11 | [8 empty] | 4122
44 | 2023-06-25 | J57 | J54 | k.c | hdpe |  |  | 26 | [6 empty] | 4148
45 | [14 empty] | 4148
46 |  |  |  |  | HDPE | [9 empty] | 4148
Work Done Qty In ( Rmt ) : | [5 empty] | 2473 | 0 | 575 | 1100 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 4148
With Held Quantity ( In RMT ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 2473 | 0 | 575 | 1100 |  | 0 | 0 | 0 | 0 | [6 empty] | 4148
[5 empty] | WO Qtys | 12324 |  | 1649 | 1167 | 590 | 459
Prepared By Site Engineer ( Sr. Eng/AM-SMX ) ( AM-PMX ) Project Incharge

## Restoration_Attarsand (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Road Restoration Measurement Sheet for Attarsand & Parsupur GP of Mangraura Block
#REF!
Sl.No | Start Node | End Node | Type of Road | DI/HDPE | Dia Of Pipe | Restoration Status |  |  | Remarks
[6 empty] | Length | Width | Area in Sqm
1 | J638 | J266 | BOE | HDPE | 63 | 41.1 | 0.363 | 14.9193
2 | j614 | j418 | BT | HDPE | 63 | 3.5 | 0.363 | 1.2705
3 | J563 | J491 | BOE | HDPE | 63 | 35.4 | 0.363 | 12.8502
4 | j529 | J530 | BOE | HDPE | 75 | 160 | 0.375 | 60
5 | j529 | J530 | BT | HDPE | 75 | 3.5 | 0.375 | 1.3125
6 | j650 | j737 | BT | HDPE | 75 | 3.5 | 0.375 | 1.3125
7 | j711 | j457 | BT | HDPE | 90 | 3.5 | 0.39 | 1.365
8 | j711 | j719 | BT | HDPE | 90 | 3.5 | 0.39 | 1.365
9 | j508 | j325 | BOE | HDPE | 90 | 58.1 | 0.39 | 22.659
10 | j563 | j427 | Interlocking | HDPE | 110 | 72.9 | 0.41 | 29.889
11 | j427 | j418 | Interlocking | HDPE | 110 | 62.3 | 0.41 | 25.543
Total Restoration done | [5 empty] | 447.3 |  | 172.49
Abstract Sheet
| Sl. No | Road Type | Area
| 1 | BOE | 110.43
| 2 | BT | 6.63
| 3 | Interlocking | 55.43
| Total |  | 172.49
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) Project Incharge