## WO Vs Execution
POWERMECH PROJECTS LIMITED
UP JAL NIGAM RWSS PROJECT
PRAYAGRAJ DIV - PRATAPGARH DIST.
WO Qty's Vs Execution Qty's
S.No | Description of Work | Padampur (Mangraura) |  |  |  |  | Sarsathpur (Patti) | [9 empty] | Total |  |  |  |  | Remarks
|  | 6000033284 |  |  |  |  | 6000033284 | [9 empty] | 6000033284
1 | HDPE Pipes - Excavation , Lowering & laying , Jointing , specials fixing, Backfilling , Testing & Commssioning - As per Approved Drawings | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill
1.1 | 63 mm HDPE | 11213 | 8781 | 8781 | 8273 | 508 | 18762 | 6393 | 6393 | 5585 | 808 |  |  |  |  | 0 | 29975 | 15174 | 15174 | 13858 | 1316
1.2 | 75 mm HDPE | 898 | 897.5 | 897.5 | 801 | 96.5 | 1021 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1919 | 897.5 | 897.5 | 801 | 96.5
1.3 | 90 mm HDPE | 498 | 498.7 | 498.7 | 465 | 33.7 | 1275 | 300 | 300 | 300 | 0 |  |  |  |  | 0 | 1773 | 798.7 | 798.7 | 765 | 33.7
1.4 | 110mm HDPE | 347 | 346 | 346 | 330 | 16 | 256 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 603 | 346 | 346 | 330 | 16
1.5 | 125mm HDPE | 416 | 415.9 | 415.9 | 388 | 27.9 | 1116 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1532 | 415.9 | 415.9 | 388 | 27.9
1.6 | 140mm HDPE | 274 | 279.9 | 279.9 | 260 | 19.9 | 1179 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1453 | 279.9 | 279.9 | 260 | 19.9
1.7 | 160mm HDPE | 188 | 179.7 | 179.7 | 0 | 179.7 | 849 | 161 | 161 | 0 | 161 |  |  |  |  | 0 | 1037 | 340.7 | 340.7 | 0 | 340.7
1.8 | 200mm HDPE |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub Total Total |  | 13834 | 11398.7 | 11398.7 | 10517 | 881.7 | 24458 | 6854 | 6854 | 5885 | 969 | 0 | 0 | 0 | 0 | 0 | 38292 | 18252.7 | 18252.7 | 16402 | 1850.7
2 | Dismatling & Restoration of Roads
2.1 | For B.O.E Surface | [15 empty] | 0 | 0 | 0 | 0 | 0
2.2 | For Bituminous Surface | [15 empty] | 0 | 0 | 0 | 0 | 0
2.3 | For Interlocking Surface | [15 empty] | 0 | 0 | 0 | 0 | 0
2.4 | For CC Road | [15 empty] | 0 | 0 | 0 | 0 | 0
3 | Construction of Valve Chambers
a) | Sluice Valve Chamber- 1000(L)X1200(W)X1300(H)
b) | Scour Valve Chamber- 1000(L)X1200(W)X1300(H)
c) | Air valve Chamber - 350(L)X350(W)X500(H)
d) | Fire Hydrant Chamber - 750(L)X450(W)X1000(H)
4 | Fixing of FHTCS excluding Supply.
a) | On Fixing
b) | On Testing
c) | On Commissioning
5 | Stand post Fixing with required accessories excluding Supply
6 | Nala/Culvert Crossing ( width -3.5 m) upto Dia 300
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) AGM Project Incharge
8273
801
465
330
388
260
0
0
10517

## Restoration (hidden)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Road Restoration Measurement Sheet for GP of Block
Name of the Contractor :
Sl.No | Start Node | End Node | Type of Road | DI/HDPE | Dia Of Pipe | Restoration Status |  |  | Remarks
[6 empty] | Length | Width | Area in Sqm
1 |  |  |  | HDPE |  |  | 0.3 | 0
2 |  |  |  | HDPE |  |  | 0.3 | 0
3 |  |  |  | HDPE |  |  | 0.3 | 0
4 |  |  |  | HDPE |  |  | 0.3 | 0
5 |  |  |  | HDPE |  |  | 0.3 | 0
6 |  |  |  | HDPE |  |  | 0.3 | 0
7 |  |  |  | HDPE |  |  | 0.3 | 0
8 |  |  |  | HDPE |  |  | 0.3 | 0
9 |  |  |  | HDPE |  |  | 0.3 | 0
10 |  |  |  | HDPE |  |  | 0.3 | 0
11 |  |  |  | HDPE |  |  | 0.3 | 0
12 |  |  |  | HDPE |  |  | 0.3 | 0
13 |  |  |  | HDPE |  |  | 0.3 | 0
14 |  |  |  | HDPE |  |  | 0.3 | 0
15 |  |  |  | HDPE |  |  | 0.3 | 0
16 |  |  |  | HDPE |  |  | 0.3 | 0
17 |  |  |  | HDPE |  |  | 0.3 | 0
18 |  |  |  | HDPE |  |  | 0.3 | 0
19 |  |  |  | HDPE |  |  | 0.3 | 0
20 |  |  |  | HDPE |  |  | 0.3 | 0
21 |  |  |  | HDPE |  |  | 0.3 | 0
22 |  |  |  | HDPE |  |  | 0.3 | 0
23 |  |  |  | HDPE |  |  | 0.3 | 0
[7 empty] | 0.3 | 0
[7 empty] | 0.3 | 0
[7 empty] | 0.3 | 0
[7 empty] | 0.3 | 0
[7 empty] | 0.3 | 0
24 |  |  |  | HDPE |  |  | 0.3 | 0
25 |  |  |  | HDPE |  |  | 0.3 | 0
26 |  |  |  | HDPE |  |  | 0.3 | 0
27 |  |  |  | HDPE |  |  | 0.3 | 0
28 |  |  |  | HDPE |  |  | 0.3 | 0
29 |  |  |  | HDPE |  |  | 0.3 | 0
30 |  |  |  | HDPE |  |  | 0.3 | 0
Total Restoration done | [5 empty] | 0 |  | 0
Abstract Sheet
| Sl. No | Road Type | Area
| 1 | BOE | 0
| 2 | BT | 0
| Total |  | 0
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) Project Incharge

## Padampur (hidden)
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Padampur (Mangraura Block) Pipeline Measurement Sheet
#REF!
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2023-03-27 | J32 | J46 | K.C ROAD | HDPE | 106 | [7 empty] | 106
2 | 2023-03-27 | J32 | J22 | K.C ROAD | HDPE | 153 | [7 empty] | 259
3 | 2023-03-28 | J81 | J88 | K.C ROAD | HDPE | 134 | [7 empty] | 393
4 | 2023-03-28 | J88 | J115 | K.C ROAD | HDPE | 147 | [7 empty] | 540
5 | 2023-03-28 | J115 | J119 | K.C ROAD | HDPE | 67 | [7 empty] | 607
6 | 2023-03-31 | J119 | J101 | K.C ROAD | HDPE | 62 | [7 empty] | 669
7 | 2023-03-31 | J101 | J116 | K.C ROAD | HDPE | 220 | [7 empty] | 889
8 | 2023-03-31 | J88 | J112 | K.C ROAD | HDPE | 118 | [7 empty] | 1007
9 | 2023-03-31 | J112 | J127 | K.C ROAD | HDPE | 160 | [7 empty] | 1167
10 | 2023-04-02 | j22 | j20 | K.C ROAD | HDPE | 73 | [7 empty] | 1240
11 | 2023-04-02 | j20 | j16 | K.C ROAD | HDPE | 14 | [7 empty] | 1254
12 | 2023-04-02 | j16 | j12 | K.C ROAD | HDPE | 116 | [7 empty] | 1370
13 | 2023-04-03 | j119 | j132 | K.C ROAD | HDPE | 121 | [7 empty] | 1491
14 | 2023-04-03 | j132 | j85 | K.C ROAD | HDPE | 108 | [7 empty] | 1599
15 | 2023-04-03 | j85 | j111 | K.C ROAD | HDPE | 86 | [7 empty] | 1685
16 | 2023-04-08 | j92 | j99 | K.C ROAD | HDPE |  |  | 100 | [5 empty] | 1785
17 | 2023-04-08 | j99 | j80 | K.C ROAD | HDPE |  |  | 60 | [5 empty] | 1845
18 | 2023-04-08 | j80 | j84 | K.C ROAD | HDPE |  |  | 57 | [5 empty] | 1902
19 | 2023-04-08 | j84 | j79 | K.C ROAD | HDPE |  |  | 55 | [5 empty] | 1957
20 | 2023-04-09 | j75 | j81 | K.C ROAD | HDPE | 60 | [7 empty] | 2017
21 | 2023-04-09 | j81 | j68 | K.C ROAD | HDPE | 80 | [7 empty] | 2097
22 | 2023-04-09 | j68 | j98 | K.C ROAD | HDPE | 22 | [7 empty] | 2119
23 | 2023-04-09 | j98 | j97 | K.C ROAD | HDPE | 17 | [7 empty] | 2136
24 | 2023-04-09 | j97 | j71 | K.C ROAD | HDPE | 96 | [7 empty] | 2232
25 | 2023-04-09 | j98 | j76 | K.C ROAD | HDPE | 72 | [7 empty] | 2304
26 | 2023-04-09 | j76 | j74 | K.C ROAD | HDPE | 27 | [7 empty] | 2331
27 | 2023-04-09 | j74 | j56 | K.C ROAD | HDPE | 140 | [7 empty] | 2471
28 | 2023-04-12 | j147 | j122 | K.C ROAD | HDPE | 148 | [7 empty] | 2619
29 | 2023-04-12 | j147 | j142 | K.C ROAD | HDPE | 179 | [7 empty] | 2798
30 | 2023-04-12 | j142 | j141 | K.C ROAD | HDPE | 30 | [7 empty] | 2828
31 | 2023-04-12 | j141 | j153 | K.C ROAD | HDPE | 35 | [7 empty] | 2863
32 | 2023-04-12 | j141 | j155 | K.C ROAD | HDPE | 361 | [7 empty] | 3224
33 | 2023-04-13 | j97 | j103 | K.C ROAD | HDPE | 160 | [7 empty] | 3384
34 | 2023-04-17 | j80 | j64 | K.C ROAD | HDPE | 128 | [7 empty] | 3512
35 | 2023-04-17 | j64 | j53 | K.C ROAD | HDPE | 34 | [7 empty] | 3546
36 | 2023-04-21 | J51 | J70 | K.C ROAD | HDPE | 608 | [7 empty] | 4154
37 | 2023-04-22 | J70 | J78 | K.C ROAD | HDPE | 54 | [7 empty] | 4208
38 | 2023-04-22 | J70 | J82 | K.C ROAD | HDPE | 80 | [7 empty] | 4288
39 | 2023-04-23 | j118 | j147 | K.C ROAD | HDPE |  | 373 | [6 empty] | 4661
40 | 2023-04-23 | j92 | j118 | K.C ROAD | HDPE |  | 124 | [6 empty] | 4785
41 | 2023-04-23 | j92 | j91 | K.C ROAD | HDPE | 76 | [7 empty] | 4861
42 | 2023-04-23 | j84 | j89 | K.C ROAD | HDPE |  |  | 142 | [5 empty] | 5003
43 | 2023-04-24 | j52 | j121 | K.C ROAD | HDPE | 138 | [7 empty] | 5141
44 | 2023-04-24 | j52 | j47 | K.C ROAD | HDPE | 121 | [7 empty] | 5262
45 | 2023-04-24 | j64 | j69 | K.C ROAD | HDPE | 250 | [7 empty] | 5512
46 | 2023-04-24 | j94 | j111 | K.C ROAD | HDPE |  | 93 | [6 empty] | 5605
47 | 2023-04-24 | j111 | j117 | K.C ROAD | HDPE |  | 37 | [6 empty] | 5642
48 | 2023-04-24 | j79 | j75 | K.C ROAD | HDPE |  |  | 75 | [5 empty] | 5717
49 | 2023-04-24 | j75 | j49 | K.C ROAD | HDPE |  |  |  | 195 |  |  |  |  | 5912
50 | 2023-04-24 | j49 | j43 | K.C ROAD | HDPE |  |  |  | 83 |  |  |  |  | 5995
51 | 2023-04-24 | j43 | j45 | K.C ROAD | HDPE |  |  |  | 69 |  |  |  |  | 6064
52 | 2023-04-25 | J99 | J67 | K.C ROAD | HDPE | 40 | [7 empty] | 6104
53 | 2023-04-25 | J89 | J102 | K.C ROAD | HDPE | 104 | [7 empty] | 6208
54 | 2023-04-25 | J43 | J54 | K.C ROAD | HDPE | 97 | [7 empty] | 6305
55 | 2023-04-25 | J45 | J59 | K.C ROAD | HDPE | 388 | [7 empty] | 6693
56 | 2023-04-25 | J45 | J44 | K.C ROAD | HDPE |  |  |  |  | 202 |  |  |  | 6895
57 | 2023-04-25 | J44 | J40 | K.C ROAD | HDPE |  |  |  |  | 156 |  |  |  | 7051
58 | 2023-04-25 | J40 | J31 | K.C ROAD | HDPE |  |  |  |  | 50 |  |  |  | 7101
59 | 2023-05-01 | j155 | j139 | K.C ROAD | HDPE | 117 | [7 empty] | 7218
60 | 2023-05-02 | J18 | J31 | K.C ROAD | HDPE | [5 empty] | 123 |  |  | 7341
61 | 2023-05-02 | J18 | J9 | K.C ROAD | HDPE | [5 empty] | 77 |  |  | 7418
62 | 2023-05-04 | j155 | j157 | K.C ROAD | HDPE | 49 | [7 empty] | 7467
63 | 2023-05-04 | j157 | j154 | K.C ROAD | HDPE | 14 | [7 empty] | 7481
64 | 2023-05-04 | j157 | j150 | K.C ROAD | HDPE | 52 | [7 empty] | 7533
65 | 2023-05-04 | j150 | j145 | K.C ROAD | HDPE | 6 | [7 empty] | 7539
66 | 2023-05-04 | j150 | j152 | K.C ROAD | HDPE | 25 | [7 empty] | 7564
67 | 2023-05-04 | j49 | j47 | K.C ROAD | HDPE | 71 | [7 empty] | 7635
68 | 2023-05-17 | j93 | j89 | K.C ROAD | HDPE |  | 108 | [6 empty] | 7743
69 | 2023-05-17 | j101 | j123 | K.C ROAD | HDPE | 103 | [7 empty] | 7846
70 | 2023-05-17 | j101 | j96 | K.C ROAD | HDPE | 86 | [7 empty] | 7932
71 | 2023-05-17 | j115 | j83 | K.C ROAD | HDPE | 93 | [7 empty] | 8025
72 | 2023-05-19 | J120 | J149 | K.C ROAD | HDPE | 300 | [7 empty] | 8325
73 | 2023-05-20 | J84 | J93 | K.C ROAD | HDPE |  | 108 | [6 empty] | 8433
74 | 2023-05-20 | J18 | J19 | K.C ROAD | HDPE | [5 empty] | 74 |  |  | 8507
75 | 2023-05-20 | J132 | J35 | K.C ROAD | HDPE | 108 | [7 empty] | 8615
76 | 2023-05-20 | J112 | J105 | K.C ROAD | HDPE | 49 | [7 empty] | 8664
77 | 2023-05-20 | J148 | J142 | K.C ROAD | HDPE | 68 | [7 empty] | 8732
78 | 2023-05-22 | J22 | J14 | K.C ROAD | HDPE | 102 | [7 empty] | 8834
79 | 2023-05-22 | J32 | J20 | K.C ROAD | HDPE | 40 | [7 empty] | 8874
80 | 2023-05-22 | J14 | J27 | K.C ROAD | HDPE | 92 | [7 empty] | 8966
81 | 2023-05-22 | J27 | J35 | K.C ROAD | HDPE | 45 | [7 empty] | 9011
82 | 2023-05-22 | J148 | J142 | K.C ROAD | HDPE | 42 | [7 empty] | 9053
83 | 2023-05-24 | J40 | J30 | K.C ROAD | HDPE | 42 | [7 empty] | 9095
84 | 2023-05-24 | J31 | J34 | K.C ROAD | HDPE | 177 | [7 empty] | 9272
85 | 2023-05-24 | J34 | J33 | K.C ROAD | HDPE | 57 | [7 empty] | 9329
86 | 2023-05-24 | J33 | J61 | K.C ROAD | HDPE | 34 | [7 empty] | 9363
87 | 2023-05-24 | J74 | J56 | K.C ROAD | HDPE | 30 | [7 empty] | 9393
88 | 2023-05-24 | J115 | J83 | K.C ROAD | HDPE | 93 | [7 empty] | 9486
89 | 2023-05-25 | J9 | J4 | K.C ROAD | HDPE | 106 | [7 empty] | 9592
90 | 2023-05-25 | J110 | J120 | K.C ROAD | HDPE | 40 | [7 empty] | 9632
91 | 2023-05-25 | J134 | J125 | K.C ROAD | HDPE | 107 | [7 empty] | 9739
92 | 2023-05-25 | J125 | J117 | K.C ROAD | HDPE | 37 | [7 empty] | 9776
93 | 2023-05-25 | J117 | J113 | K.C ROAD | HDPE | 21 | [7 empty] | 9797
94 | 2023-05-25 | J113 | J129 | K.C ROAD | HDPE | 95 | [7 empty] | 9892
95 | 2023-05-25 | J129 | J133 | K.C ROAD | HDPE | 66 | [7 empty] | 9958
96 | 2023-05-25 | J113 | J130 | K.C ROAD | HDPE | 36 | [7 empty] | 9994
97 | 2023-05-25 | J130 | J120 | K.C ROAD | HDPE | 107 | [7 empty] | 10101
98 | 2023-05-25 | J34 | J42 | K.C ROAD | HDPE | 61 | [7 empty] | 10162
99 | 2023-05-25 | J42 | J10 | K.C ROAD | HDPE | 110 | [7 empty] | 10272
100 | 2023-05-25 | J42 | J25 | K.C ROAD | HDPE | 52 | [7 empty] | 10324
101 | 2023-05-25 | J19 | J1 | K.C ROAD | HDPE | 24 | [7 empty] | 10348
102 | 2023-05-25 | J19 | J5 | K.C ROAD | HDPE | 55 | [7 empty] | 10403
103 | 2023-05-25 | JJ5 | J18 | K.C ROAD | HDPE | 61 | [7 empty] | 10464
104 | 2023-05-25 | J8 | J26 | K.C ROAD | HDPE | 45 | [7 empty] | 10509
105 | 2023-05-25 | J26 | J30 | K.C ROAD | HDPE | 44 | [7 empty] | 10553
106 | 2023-05-25 | J9 | J30 | K.C ROAD | HDPE | 74 | [7 empty] | 10627
107 | 2023-05-25 | J30 | J6 | K.C ROAD | HDPE | 128 | [7 empty] | 10755
108 | 2023-05-25 | J35 | J37 | K.C ROAD | HDPE | 37 | [7 empty] | 10792
109 | 2023-05-25 | J35 | J36 | K.C ROAD | HDPE | 98 | [7 empty] | 10890
110 | [13 empty] | 10890
Work Done Qty In ( Rmt ) : | [5 empty] | 8529 | 843 | 489 | 347 | 408 | 274 | 0 | 0
With Held 10 % of the Total Quantity ( In RMT ) | [5 empty] | 256 | 42 | 24 | 17 | 20 | 14 | 0 | 0
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 8273 | 801 | 465 | 330 | 388 | 260 | 0 | 0
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) AGM Project Incharge

## PADAMPUR (2)
PADAMPUR(JMR)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) |  |  | CUMMULATIVE | REMARKS
1 | J130 | J120 |  |  | 63 | 144.2 |  |  | 144.2
2 | J75 | J81 | B.T ROAD | 0.36 | 63 | 8.2 |  |  | 152.4
3 | J75 | J81 |  |  | 63 | 58.6 |  |  | 211
4 | J81 | J98 |  |  | 63 | 105.8 |  |  | 316.8
5 | J98 | J74 |  |  | 63 | 100.2 |  |  | 417
6 | J74 | J56 |  |  | 63 | 151.7 |  |  | 568.7
7 | J98 | J97 |  |  | 63 | 13.6 |  |  | 582.3
8 | J97 | J71 |  |  | 63 | 89.5 |  |  | 671.8
9 | J97 | J105 |  |  | 63 | 93.9 |  |  | 765.7
10 | J97 | J105 | B.T ROAD | 0.36 | 63 | 3.4 |  |  | 769.1
11 | J88 | J112 |  |  | 63 | 118.8 |  |  | 887.9
12 | J112 | J127 |  |  | 63 | 165.3 |  |  | 1053.2
13 | J112 | J105 |  |  | 63 | 1.8 |  |  | 1055
14 | J88 | J115 |  |  | 63 | 146.6 |  |  | 1201.6
15 | J115 | J83 |  |  | 63 | 106.4 |  |  | 1308
16 | J115 | J83 | B.T ROAD | 0.36 | 63 | 3 |  |  | 1311
17 | J115 | J119 |  |  | 63 | 82.6 |  |  | 1393.6
18 | J119 | J101 |  |  | 63 | 60.6 |  |  | 1454.2
19 | J101 | J123 |  |  | 63 | 119.1 |  |  | 1573.3
20 | J101 | J96 |  |  | 63 | 65.1 |  |  | 1638.4
21 | J132 | J111 |  |  | 63 | 75.4 |  |  | 1713.8
22 | J119 | J132 |  |  | 63 | 209.2 |  |  | 1923 | [9 empty] | 1968
23 | J113 | J129 | BRICK ROAD | 0.36 | 63 | 2.6 |  |  | 1925.6
24 | J113 | J129 |  |  | 63 | 83.1 |  |  | 2008.7
25 | J113 | J130 |  |  | 63 | 45.5 |  |  | 2054.2
26 | J135 | J140A |  |  | 63 | 86.9 |  |  | 2141.1
27 | J135 | J140A | INTERLOCKING | 0.36 | 63 | 3.1 |  |  | 2144.2
28 | J140A | J124 |  |  | 63 | 103.3 |  |  | 2247.5
29 | J92 | J91 |  |  | 63 | 2.8 |  |  | 2250.3
30 | J81 | J88 | B.T ROAD | 0.36 | 63 | 3.6 |  |  | 2253.9
31 | J81 | J88 |  |  | 63 | 137.6 |  |  | 2391.5
32 | J155 | J139 |  |  | 63 | 94.6 |  |  | 2486.1
33 | J155 | J150 |  |  | 63 | 106.1 |  |  | 2592.2
34 | J155 | J141 |  |  | 63 | 377.3 |  |  | 2969.5
35 | J141 | J153 |  |  | 63 | 52 |  |  | 3021.5
36 | J141 | J147 |  |  | 63 | 220.9 |  |  | 3242.4
37 | J147 | J122 |  |  | 63 | 153.6 |  |  | 3396
38 | J93 | J132 |  |  | 63 | 197.3 |  |  | 3593.3
39 | J44 | J41 |  |  | 63 | 52.3 |  |  | 3645.6
40 | J40 | J38 |  |  | 63 | 38.2 |  |  | 3683.8
41 | J12 | J22 |  |  | 63 | 174.7 |  |  | 3858.5
42 | J22 | J32 |  |  | 63 | 167.4 |  |  | 4025.9
43 | J22 | J32 | B.T ROAD | 0.36 | 63 | 4 |  |  | 4029.9
44 | J32 | J46 |  |  | 63 | 90.6 |  |  | 4120.5
45 | J22 | J14 |  |  | 63 | 84.1 |  |  | 4204.6
46 | J14 | J27 | C.C. | 0.36 | 63 | 88.8 |  |  | 4293.4
47 | J14 | J27 |  |  | 63 | 1.4 |  |  | 4294.8
48 | J27 | J35 | C.C. | 0.36 | 63 | 50.7 |  |  | 4345.5
49 | J32 | J28 |  |  | 63 | 61.3 |  |  | 4406.8
50 | J32 | J28 | B.T ROAD | 0.36 | 63 | 3 |  |  | 4409.8
51 | J35 | J36 |  |  | 63 | 92 |  |  | 4501.8
52 | J36 | J39 |  |  | 63 | 7.1 |  |  | 4508.9
53 | J26 | J36 |  |  | 63 | 43 |  |  | 4551.9
54 | J5 | J42 | C.C. | 0.36 | 63 | 114.6 |  |  | 4666.5
55 | J42 | J34 | C.C. | 0.36 | 63 | 21.9 |  |  | 4688.4
56 | J42 | J34 |  |  | 63 | 2.9 |  |  | 4691.3
57 | J34 | J33 |  |  | 63 | 46.5 |  |  | 4737.8
58 | J80 | J64 |  |  | 63 | 131.3 |  |  | 4869.1
59 | J64 | J52 |  |  | 63 | 33 |  |  | 4902.1
60 | J64 | J52 | B.T ROAD | 0.36 | 63 | 5 |  |  | 4907.1
61 | J52 | J121 |  |  | 63 | 112.9 |  |  | 5020
62 | J52 | J47 |  |  | 63 | 83.5 |  |  | 5103.5
63 | J64 | J53 |  |  | 63 | 340.1 |  |  | 5443.6
64 | J152 | J150 |  |  | 63 | 27.1 |  |  | 5470.7
65 | j78 | j51 |  |  | 63 | 685.6 |  |  | 6156.3
66 | j59 | j57 |  |  | 63 | 64.1 |  |  | 6220.4
67 | j45 | j59 |  |  | 63 | 258.3 |  |  | 6478.7
68 | j43 | j54 |  |  | 63 | 76.9 |  |  | 6555.6
69 | j94 | j131 |  |  | 63 | 90.6 |  |  | 6646.2
70 | j131 | j143 |  |  | 63 | 432 |  |  | 7078.2
71 | j131 | j143 | brick road | 0.36 | 63 | 2.6 |  |  | 7080.8
72 | j131 | j120 |  |  | 63 | 120.7 |  |  | 7201.5
73 | j149 | j120 |  |  | 63 | 177.4 |  |  | 7378.9
74 | j149 | j120 | BRICK ROAD | 0.36 | 63 | 116.3 |  |  | 7495.2 |  |  | 685.6
75 | j34 | j31 |  |  | 63 | 160.2 |  |  | 7655.4 |  |  | 250.3
76 | J6 | j30 |  |  | 63 | 186.8 |  |  | 7842.2 |  |  | 71.9
77 | j30 | j8 |  |  | 63 | 29 |  |  | 7871.2 |  |  | 79.8
78 | j92 | j91 |  |  | 63 | 66.1 |  |  | 7937.3 |  |  | 43.2
79 | J8 | J27 | C.C. | 0.36 | 63 | 58.8 |  |  | 7996.1 |  |  | 2.6
80 | j8 | j26 | C.C. | 0.36 | 63 | 46.8 |  |  | 8042.9 |  |  | 120.7
81 | j8 | j26 |  |  | 63 | 1.3 |  |  | 8044.2 |  |  | 174.4
82 | j8 | j26 | cc road | 0.36 | 63 | 5.4 |  |  | 8049.6 |  |  | 116.3
83 | j26 | j25 | C.C. | 0.36 | 63 | 21.1 |  |  | 8070.7 |  |  | 197.3
84 | j26 | j36 | cc road | 0.36 | 63 | 3 |  |  | 8073.7 |  |  | 158.2
85 | J9 | J30 | cc road | 0.36 | 63 | 4.1 |  |  | 8077.8 |  |  | 130.8
86 | J9 | J30 | C.C. | 0.36 | 63 | 63.4 |  |  | 8141.2 |  |  | 29
87 | J30 | J27 |  |  | 63 | 8.2 |  |  | 8149.4 |  |  | 133.2
88 | J30 | J27 | C.C. | 0.36 | 63 | 75.1 |  |  | 8224.5 |  |  | 62.1
89 | J30 | J6 | C.C. | 0.36 | 63 | 40.2 |  |  | 8264.7
90 | j6 | j8 |  |  | 63 | 29 |  |  | 8293.7 | [5 empty] | 424.9
91 | j89 | j102 |  |  | 63 | 133.4 |  |  | 8427.1 |  |  | 48.1
92 | j117 | j113 | BRICK ROAD | 0.36 | 63 | 50.1 |  |  | 8477.2 |  |  | 5.4
93 | j117 | j113 |  |  | 63 | 39.1 |  |  | 8516.3
94 | j110 | j128 | INTERLOCKING | 0.36 | 63 | 3.2 |  |  | 8519.5 |  |  | 21.1
95 | J110 | J128 |  |  | 63 | 64.2 |  |  | 8583.7
96 | J93A | J132 |  |  | 63 | 197.3 |  |  | 8781 |  |  | 3
97 | J111 | J117 |  |  | 75 | 42.4 |  |  | 8823.4
98 | J147 | J118 |  |  | 75 | 3.2 |  |  | 8826.6
99 | J147 | J118 |  |  | 75 | 347.2 |  |  | 9173.8
100 | J147 | J118 | INTERLOCKING | 0.38 | 75 | 8.6 |  |  | 9182.4
101 | j110 | j135 |  |  | 75 | 63.3 |  |  | 9245.7
102 | j135 | j117 |  |  | 75 | 97.1 |  |  | 9342.8
103 | J111 | J93A |  |  | 75 | 25.1 |  |  | 9367.9
104 | J93A | J89 |  |  | 75 | 115.6 |  |  | 9483.5
105 | J118 | J110 |  |  | 75 | 58.2 |  |  | 9541.7
106 | J118 | J92 | B.T ROAD | 0.38 | 75 | 4.6 |  |  | 9546.3
107 | J118 | J92 |  |  | 75 | 132.2 |  |  | 9678.5
108 | J92 | J80 |  |  | 90 | 148.6 |  |  | 9827.1
109 | J80 | J84 | B.T ROAD | 0.39 | 90 | 6.6 |  |  | 9833.7
110 | J80 | J84 |  |  | 90 | 54.4 |  |  | 9888.1
111 | J84 | J75 |  |  | 90 | 137.3 |  |  | 10025.4
112 | J84 | J89 | B.T ROAD | 0.39 | 90 | 3 |  |  | 10028.4
113 | J84 | J89 |  |  | 90 | 148.8 |  |  | 10177.2
114 | J75 | J43 |  |  | 110 | 275.5 |  |  | 10452.7
115 | j45 | j43 |  |  | 110 | 2.4 |  |  | 10455.1 | extra 2.4m culvert
116 | j45 | j43 |  |  | 110 | 3.3 |  |  | 10458.4
117 | j45 | j43 |  |  | 110 | 64.8 |  |  | 10523.2
118 | J44 | J45 |  |  | 125 | 201.9 |  |  | 10725.1
119 | J44 | J40 |  |  | 125 | 155.8 |  |  | 10880.9 |  |  |  | 8549
120 | J40 | J31 |  |  | 125 | 58.2 |  |  | 10939.1 | [9 empty] | 11219
121 | J31 | J9 |  |  | 140 | 279.9 |  |  | 11219 |  |  |  |  | -180.1
122 | J9 | J12 | cc road | 0.46 | 160 | 4.4 |  |  | 11223.4 |  |  |  | 118
123 | J9 | J12 |  |  | 160 | 167.4 |  |  | 11390.8
124 | J12 | J22 |  |  | 160 | 7.9 |  |  | 11398.7
|  | 63 | 75 | 90 | 110 |  |  |  | 125 | 140 | 160
|  | 8781 | 897.5 | 498.7 | 346 |  |  |  | 415.9 | 279.9 | 179.7
|  | 11213 | 898 | 498 | 347 |  |  |  | 416 | 274 | 188 |  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT. |  |  |  |  | 63 | 11213 | 9293 | 8529 | 764
DESIGNATION |  |  |  | DESIGNATION |  |  |  |  | DESIGNATION |  |  |  |  | 75 | 898 | 900 | 843 | 57
NAME |  |  |  | NAME |  |  |  |  | NAME |  |  |  |  | 90 | 489 | 500 | 489 | 11
SIGN.with date |  |  |  | SIGN.with date |  |  |  |  | SIGN.with date |  |  |  |  | 110 | 347 | 400 | 347 | 53
[14 empty] | 125 | 408 | 408 | 408 | 0
[14 empty] | 140 | 200 | 274 | 274 | 0
[14 empty] | 160 | 188 | 192 | 0 | 192
PADAMPUR(JMR)
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) |  |  | CUMMULATIVE | REMARKS
1 | J130 | J120 |  |  | 63 | 142.2 |  |  | 142.2
2 | J75 | J81 | B.T ROAD |  | 63 | 8.2 |  |  | 150.4
3 | J75 | J81 |  |  | 63 | 58.6 |  |  | 209
4 | J81 | J98 |  |  | 63 | 105.8 |  |  | 314.8
5 | J98 | J74 |  |  | 63 | 100.2 |  |  | 415
6 | J74 | J56 |  |  | 63 | 144.7 |  |  | 559.7
7 | J98 | J97 |  |  | 63 | 13.6 |  |  | 573.3
8 | J97 | J71 |  |  | 63 | 87.5 |  |  | 660.8
9 | J97 | J105 |  |  | 63 | 89.9 |  |  | 750.7
10 | J97 | J105 | B.T ROAD |  | 63 | 3.4 |  |  | 754.1
11 | J88 | J112 |  |  | 63 | 118.8 |  |  | 872.9
12 | J112 | J127 |  |  | 63 | 162.3 |  |  | 1035.2
13 | J112 | J105 |  |  | 63 | 1.8 |  |  | 1037
14 | J88 | J115 |  |  | 63 | 146.6 |  |  | 1183.6
15 | J115 | J83 |  |  | 63 | 106.4 |  |  | 1290
16 | J115 | J83 | B.T ROAD |  | 63 | 3 |  |  | 1293
17 | J115 | J119 |  |  | 63 | 82.6 |  |  | 1375.6
18 | J119 | J101 |  |  | 63 | 56.6 |  |  | 1432.2
19 | J101 | J123 |  |  | 63 | 116.1 |  |  | 1548.3
20 | J101 | J96 |  |  | 63 | 63.1 |  |  | 1611.4
21 | J119 | J132 |  |  | 63 | 209.2 |  |  | 1820.6
22 | J113 | J129 | BRICK ROAD |  | 63 | 2.6 |  |  | 1823.2
23 | J113 | J129 |  |  | 63 | 79.1 |  |  | 1902.3
24 | J113 | J130 |  |  | 63 | 45.5 |  |  | 1947.8
25 | J135 | J140A |  |  | 63 | 86.9 |  |  | 2034.7
26 | J135 | J140A | INTERLOCKING |  | 63 | 3.1 |  |  | 2037.8
27 | J140A | J124 |  |  | 63 | 103.3 |  |  | 2141.1
28 | J92 | J91 |  |  | 63 | 2.8 |  |  | 2143.9
29 | J81 | J88 | B.T ROAD |  | 63 | 3.6 |  |  | 2147.5
30 | J81 | J88 |  |  | 63 | 137.6 |  |  | 2285.1
31 | J155 | J139 |  |  | 63 | 88.6 |  |  | 2373.7
32 | J155 | J150 |  |  | 63 | 106.1 |  |  | 2479.8
33 | J155 | J141 |  |  | 63 | 375.3 |  |  | 2855.1
34 | J141 | J153 |  |  | 63 | 52 |  |  | 2907.1
35 | J141 | J147 |  |  | 63 | 218.9 |  |  | 3126
36 | J147 | J122 |  |  | 63 | 148.6 |  |  | 3274.6
37 | J93 | J132 |  |  | 63 | 197.3 |  |  | 3471.9
38 | J44 | J41 |  |  | 63 | 52.3 |  |  | 3524.2
39 | J40 | J38 |  |  | 63 | 36.2 |  |  | 3560.4
40 | J12 | J22 |  |  | 63 | 171.7 |  |  | 3732.1
41 | J22 | J32 |  |  | 63 | 167.4 |  |  | 3899.5
42 | J22 | J32 | B.T ROAD |  | 63 | 4 |  |  | 3903.5
43 | J32 | J46 |  |  | 63 | 83.6 |  |  | 3987.1
44 | J22 | J14 |  |  | 63 | 78.1 |  |  | 4065.2
45 | J14 | J27 | C.C. |  | 63 | 88.8 |  |  | 4154
46 | J14 | J27 |  |  | 63 | 1.4 |  |  | 4155.4
47 | J27 | J35 | C.C. |  | 63 | 50.7 |  |  | 4206.1
48 | J32 | J28 |  |  | 63 | 59.3 |  |  | 4265.4
49 | J32 | J28 | B.T ROAD |  | 63 | 3 |  |  | 4268.4
50 | J35 | J36 |  |  | 63 | 92 |  |  | 4360.4
51 | J36 | J39 |  |  | 63 | 7.1 |  |  | 4367.5
52 | J26 | J36 |  |  | 63 | 43 |  |  | 4410.5
53 | J5 | J42 | C.C. |  | 63 | 114.6 |  |  | 4525.1
54 | J42 | J34 | C.C. |  | 63 | 21.9 |  |  | 4547
55 | J42 | J34 |  |  | 63 | 2.9 |  |  | 4549.9
56 | J34 | J33 |  |  | 63 | 44.5 |  |  | 4594.4
57 | J80 | J64 |  |  | 63 | 131.3 |  |  | 4725.7
58 | J64 | J52 |  |  | 63 | 33 |  |  | 4758.7
59 | J64 | J52 | B.T ROAD |  | 63 | 5 |  |  | 4763.7
60 | J52 | J121 |  |  | 63 | 106.9 |  |  | 4870.6
61 | J52 | J47 |  |  | 63 | 79.5 |  |  | 4950.1
62 | J64 | J53 |  |  | 63 | 282.1 |  |  | 5232.2
63 | J152 | J150 |  |  | 63 | 22.1 |  |  | 5254.3
64 | j78 | j51 |  |  | 63 | 685.6 |  |  | 5939.9 | INCOMPLETE
65 | j59 | j57 |  |  | 63 | 60.1 |  |  | 6000 | INCOMPLETE
66 | j45 | j59 |  |  | 63 | 250.3 |  |  | 6250.3
67 | j43 | j54 |  |  | 63 | 71.9 |  |  | 6322.2
68 | j94 | j131 |  |  | 63 | 86.6 |  |  | 6408.8
69 | j131 | j143 |  |  | 63 | 432 |  |  | 6840.8 | INCOMPLETE
70 | j131 | j143 | brick road |  | 63 | 2.6 |  |  | 6843.4
71 | j131 | j120 |  |  | 63 | 120.7 |  |  | 6964.1 | INCOMPLETE
72 | j149 | j120 |  |  | 63 | 174.4 |  |  | 7138.5
73 | j149 | j120 | BRICK ROAD |  | 63 | 116.3 |  |  | 7254.8
74 | j34 | j31 |  |  | 63 | 158.2 |  |  | 7413
75 | J6 | j30 |  |  | 63 | 130.8 |  |  | 7543.8
76 | j30 | j8 |  |  | 63 | 29 |  |  | 7572.8
77 | j92 | j91 |  |  | 63 | 62.1 |  |  | 7634.9
78 | J8 | J27 | C.C. |  | 63 | 58.8 |  |  | 7693.7
79 | j8 | j26 | C.C. |  | 63 | 46.8 |  |  | 7740.5
80 | j8 | j26 |  |  | 63 | 1.3 |  |  | 7741.8
81 | j8 | j26 | cc road |  | 63 | 5.4 |  |  | 7747.2
82 | j26 | j25 | C.C. |  | 63 | 21.1 |  |  | 7768.3
83 | j26 | j36 | cc road |  | 63 | 3 |  |  | 7771.3
84 | J9 | J30 | cc road |  | 63 | 4.1 |  |  | 7775.4
85 | J9 | J30 | C.C. |  | 63 | 63.4 |  |  | 7838.8
86 | J30 | J27 |  |  | 63 | 8.2 |  |  | 7847
87 | J30 | J27 | C.C. |  | 63 | 75.1 |  |  | 7922.1
88 | J30 | J6 | C.C. |  | 63 | 40.2 |  |  | 7962.3
89 | j6 | j8 |  |  | 63 | 29 |  |  | 7991.3
90 | j89 | j102 |  |  | 63 | 128.4 |  |  | 8119.7
91 | j117 | j113 | BRICK ROAD |  | 63 | 50.1 |  |  | 8169.8
92 | j117 | j113 |  |  | 63 | 39.1 |  |  | 8208.9
93 | J93A | J132 |  |  | 63 | 197.3 |  |  | 8406.2
94 | J111 | J117 |  |  | 75 | 42.4 |  |  | 8448.6
95 | J147 | J118 |  |  | 75 | 3.2 |  |  | 8451.8
96 | J147 | J118 |  |  | 75 | 352.2 |  |  | 8804
97 | J147 | J118 | INTERLOCKING |  | 75 | 8.6 |  |  | 8812.6
98 | j110 | j135 |  |  | 75 | 57.3 |  |  | 8869.9
99 | j135 | j117 |  |  | 75 | 97.1 |  |  | 8967
100 | J111 | J93A |  |  | 75 | 25.1 |  |  | 8992.1
101 | J93A | J89 |  |  | 75 | 116.6 |  |  | 9108.7
102 | J118 | J110 |  |  | 75 | 58.2 |  |  | 9166.9
103 | J118 | J92 | B.T ROAD |  | 75 | 4.6 |  |  | 9171.5
104 | J118 | J92 |  |  | 75 | 132.2 |  |  | 9303.7
105 | J92 | J80 |  |  | 90 | 160.6 |  |  | 9464.3
106 | J80 | J84 | B.T ROAD |  | 90 | 6.6 |  |  | 9470.9
107 | J80 | J84 |  |  | 90 | 53.4 |  |  | 9524.3
108 | J84 | J75 |  |  | 90 | 129.3 |  |  | 9653.6
109 | J84 | J89 | B.T ROAD |  | 90 | 3 |  |  | 9656.6
110 | J84 | J89 |  |  | 90 | 145.8 |  |  | 9802.4
111 | J75 | J43 |  |  | 110 | 284.4 |  |  | 10086.8
112 | j45 | j43 |  |  | 110 | 2.4 |  |  | 10089.2 | extra 2.4m culvert
113 | j45 | j43 |  |  | 110 | 3.3 |  |  | 10092.5
114 | j45 | j43 |  |  | 110 | 56.9 |  |  | 10149.4
115 | J44 | J45 |  |  | 125 | 201.9 |  |  | 10351.3
116 | J44 | J40 |  |  | 125 | 155.8 |  |  | 10507.1
117 | J40 | J31 |  |  | 125 | 58.2 |  |  | 10565.3
118 | J31 | J9 |  |  | 140 | 279.9 |  |  | 10845.2
119 | J9 | J12 | cc road |  | 160 | 4.4 |  |  | 10849.6
120 | J9 | J12 |  |  | 160 | 167.4 |  |  | 11017
121 | J12 | J22 |  |  | 160 | 7.9 |  |  | 11024.9
|  |  | 63 | 75 | 90 | 110 | 125 |  | 140 | 160
|  |  | 8406.2 | 897.5 | 498.7 | 347 | 415.9 | 0 | 279.9 | 179.7

## padampur hydro
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | J130 | J120 | 63 | 142.2 | 5.5 | 3 | 1 | 4 | no
2 | J75 | J81 | 63 | 8.2 | 5.5 | 3 | 1 | 4 | no
3 | J75 | J81 | 63 | 58.6 | 5.5 | 3 | 1 | 4 | no
4 | J81 | J98 | 63 | 105.8 | 5.5 | 3 | 1 | 4 | no
5 | J98 | J74 | 63 | 100.2 | 5.5 | 3 | 1 | 4 | no
6 | J74 | J56 | 63 | 144.7 | 5.5 | 3 | 1 | 4 | no
7 | J98 | J97 | 63 | 13.6 | 5.5 | 3 | 1 | 4 | no
8 | J97 | J71 | 63 | 87.5 | 5.5 | 3 | 1 | 4 | no
9 | J97 | J105 | 63 | 89.9 | 5.5 | 3 | 1 | 4 | no
10 | J97 | J105 | 63 | 3.4 | 5.5 | 3 | 1 | 4 | no
11 | J88 | J112 | 63 | 118.8 | 5.5 | 3 | 1 | 4 | no
12 | J112 | J127 | 63 | 162.3 | 5.5 | 3 | 1 | 4 | no
13 | J112 | J105 | 63 | 1.8 | 5.5 | 3 | 1 | 4 | no
14 | J88 | J115 | 63 | 146.6 | 5.5 | 3 | 1 | 4 | no
15 | J115 | J83 | 63 | 106.4 | 5.5 | 3 | 1 | 4 | no
16 | J115 | J83 | 63 | 3 | 5.5 | 3 | 1 | 4 | no
17 | J115 | J119 | 63 | 82.6 | 5.5 | 3 | 1 | 4 | no
18 | J119 | J101 | 63 | 56.6 | 5.5 | 3 | 1 | 4 | no
19 | J101 | J123 | 63 | 116.1 | 5.5 | 3 | 1 | 4 | no
20 | J101 | J96 | 63 | 63.1 | 5.5 | 3 | 1 | 4 | no
21 | J119 | J132 | 63 | 209.2 | 5.5 | 3 | 1 | 4 | no
22 | J113 | J129 | 63 | 2.6 | 5.5 | 3 | 1 | 4 | no
23 | J113 | J129 | 63 | 79.1 | 5.5 | 3 | 1 | 4 | no
24 | J113 | J130 | 63 | 45.5 | 5.5 | 3 | 1 | 4 | no
25 | J135 | J140A | 63 | 86.9 | 5.5 | 3 | 1 | 4 | no
26 | J135 | J140A | 63 | 3.1 | 5.5 | 3 | 1 | 4 | no
27 | J140A | J124 | 63 | 183.3 | 5.5 | 3 | 1 | 4 | no
28 | J92 | J91 | 63 | 2.8 | 5.5 | 3 | 1 | 4 | no
29 | J81 | J88 | 63 | 3.6 | 5.5 | 3 | 1 | 4 | no
30 | J81 | J88 | 63 | 150.6 | 5.5 | 3 | 1 | 4 | no
31 | J155 | J139 | 63 | 88.6 | 5.5 | 3 | 1 | 4 | no
32 | J155 | J150 | 63 | 106.1 | 5.5 | 3 | 1 | 4 | no
33 | J155 | J141 | 63 | 375.3 | 5.5 | 3 | 1 | 4 | no
34 | J141 | J153 | 63 | 52 | 5.5 | 3 | 1 | 4 | no
35 | J141 | J147 | 63 | 218.9 | 5.5 | 3 | 1 | 4 | no
36 | J147 | J122 | 63 | 148.6 | 5.5 | 3 | 1 | 4 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | J93 | J132 | 63 | 197.3 | 6 | 3.3 | 1 | 4.3 | no
2 | J44 | J41 | 63 | 52.3 | 6 | 3.3 | 1 | 4.3 | no
3 | J40 | J38 | 63 | 36.2 | 6 | 3.3 | 1 | 4.3 | no
4 | J12 | J22 | 63 | 171.7 | 6 | 3.3 | 1 | 4.3 | no
5 | J22 | J32 | 63 | 167.4 | 6 | 3.3 | 1 | 4.3 | no
6 | J22 | J32 | 63 | 4 | 6 | 3.3 | 1 | 4.3 | no
7 | J32 | J46 | 63 | 83.6 | 6 | 3.3 | 1 | 4.3 | no
8 | J22 | J14 | 63 | 78.1 | 6 | 3.3 | 1 | 4.3 | no
9 | J14 | J27 | 63 | 88.8 | 6 | 3.3 | 1 | 4.3 | no
10 | J14 | J27 | 63 | 1.4 | 6 | 3.3 | 1 | 4.3 | no
11 | J27 | J35 | 63 | 50.7 | 6 | 3.3 | 1 | 4.3 | no
12 | J32 | J28 | 63 | 59.3 | 6 | 3.3 | 1 | 4.3 | no
13 | J32 | J28 | 63 | 3 | 6 | 3.3 | 1 | 4.3 | no
14 | J35 | J36 | 63 | 92 | 6 | 3.3 | 1 | 4.3 | no
15 | J36 | J39 | 63 | 7.1 | 6 | 3.3 | 1 | 4.3 | no
16 | J26 | J36 | 63 | 43 | 6 | 3.3 | 1 | 4.3 | no
17 | J5 | J42 | 63 | 114.6 | 6 | 3.3 | 1 | 4.3 | no
18 | J42 | J34 | 63 | 21.9 | 6 | 3.3 | 1 | 4.3 | no
19 | J42 | J34 | 63 | 2.9 | 6 | 3.3 | 1 | 4.3 | no
20 | J34 | J33 | 63 | 44.5 | 6 | 3.3 | 1 | 4.3 | no
21 | J80 | J64 | 63 | 131.3 | 6 | 3.3 | 1 | 4.3 | no
22 | J64 | J52 | 63 | 33 | 6 | 3.3 | 1 | 4.3 | no
23 | J64 | J52 | 63 | 5 | 6 | 3.3 | 1 | 4.3 | no
24 | J52 | J121 | 63 | 196.9 | 6 | 3.3 | 1 | 4.3 | no
25 | J52 | J47 | 63 | 79.5 | 6 | 3.3 | 1 | 4.3 | no
26 | J64 | J53 | 63 | 282.1 | 6 | 3.3 | 1 | 4.3 | no
27 | J152 | J150 | 63 | 22.1 | 6 | 3.3 | 1 | 4.3 | no
28 | j78 | j51 | 63 | 685.6 | 6 | 3.3 | 1 | 4.3 | no
29 | j59 | j57 | 63 | 60.1 | 6 | 3.3 | 1 | 4.3 | no
30 | j45 | j59 | 63 | 250.3 | 6 | 3.3 | 1 | 4.3 | no
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | j43 | j54 | 63 | 71.9 | 5.5 | 3.5 | 1 | 4.5 | No
2 | j94 | j131 | 63 | 86.6 | 5.5 | 3.5 | 1 | 4.5 | No
3 | j131 | j143 | 63 | 432 | 5.5 | 3.5 | 1 | 4.5 | No
4 | j131 | j143 | 63 | 2.6 | 5.5 | 3.5 | 1 | 4.5 | No
5 | j131 | j120 | 63 | 120.7 | 5.5 | 3.5 | 1 | 4.5 | No
6 | j149 | j120 | 63 | 174.4 | 5.5 | 3.5 | 1 | 4.5 | No
7 | j149 | j120 | 63 | 116.3 | 5.5 | 3.5 | 1 | 4.5 | No
8 | j34 | j31 | 63 | 158.2 | 5.5 | 3.5 | 1 | 4.5 | No
9 | J101 | J116 | 63 | 274.2 | 5.5 | 3.5 | 1 | 4.5 | No
10 | J6 | j30 | 63 | 130.8 | 5.5 | 3.5 | 1 | 4.5 | No
11 | j30 | j8 | 63 | 29 | 5.5 | 3.5 | 1 | 4.5 | No
12 | j92 | j91 | 63 | 62.1 | 5.5 | 3.5 | 1 | 4.5 | No
13 | J8 | J27 | 63 | 58.8 | 5.5 | 3.5 | 1 | 4.5 | No
14 | j8 | j26 | 63 | 146.8 | 5.5 | 3.5 | 1 | 4.5 | No
15 | j8 | j26 | 63 | 1.3 | 5.5 | 3.5 | 1 | 4.5 | No
16 | j8 | j26 | 63 | 5.4 | 5.5 | 3.5 | 1 | 4.5 | No
17 | j26 | j25 | 63 | 21.1 | 5.5 | 3.5 | 1 | 4.5 | No
18 | j26 | j36 | 63 | 3 | 5.5 | 3.5 | 1 | 4.5 | No
19 | J9 | J30 | 63 | 4.1 | 5.5 | 3.5 | 1 | 4.5 | No
20 | J9 | J30 | 63 | 163.4 | 5.5 | 3.5 | 1 | 4.5 | No
21 | J30 | J27 | 63 | 8 | 5.5 | 3.5 | 1 | 4.5 | No
22 | J30 | J27 | 63 | 75.1 | 5.5 | 3.5 | 1 | 4.5 | No
23 | J30 | J6 | 63 | 39.2 | 5.5 | 3.5 | 1 | 4.5 | No
24 | j6 | j8 | 63 | 29 | 5.5 | 3.5 | 1 | 4.5 | No
25 | j89 | j102 | 63 | 121.4 | 5.5 | 3.5 | 1 | 4.5 | No
26 | j117 | j113 | 63 | 50.1 | 5.5 | 3.5 | 1 | 4.5 | No
27 | j117 | j113 | 63 | 39.1 | 5.5 | 3.5 | 1 | 4.5 | No
28 | J93A | J132 | 63 | 197.3 | 5.5 | 3.5 | 1 | 4.5 | No
29 | J111 | J117 | 75 | 42.4 | 5.5 | 3.5 | 1 | 4.5 | No
30 | J147 | J118 | 75 | 3.2 | 5.5 | 3.5 | 1 | 4.5 | No
31 | J147 | J118 | 75 | 352.2 | 5.5 | 3.5 | 1 | 4.5 | No
32 | J147 | J118 | 75 | 8.6 | 5.5 | 3.5 | 1 | 4.5 | No
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date
Project :- |  | Rural water Supply project under JJM, Pratapgarh, Uttar Pradesh
Client:- |  | State Water & Sanitation Mission Govt Of Uttar Pradesh
TPI:- |  | Medhaj Techno Concept Pvt. Ltd.
Contractor:- |  | Power Mech Project Ltd.
Block :- |  | Mangraura
GP :- |  | Padampur
Sl.No | Start Node | End Node | Dia of pipe | Pipe Length (M) | Appliede test pressure (kg /cm'2) | Pressure test rising time (Hrs) | Pressure Released time(Hrs) | Total Duration Hrs | Observation | Remarks
1 | j110 | j135 | 75 | 57.3 | 6 | 3 | 1 | 4 | No
2 | j135 | j117 | 75 | 97.1 | 6 | 3 | 1 | 4 | No
3 | J111 | J93A | 75 | 25.1 | 6 | 3 | 1 | 4 | No
4 | J93A | J89 | 75 | 116.6 | 6 | 3 | 1 | 4 | No
5 | J118 | J110 | 75 | 58.2 | 6 | 3 | 1 | 4 | No
6 | J118 | J92 | 75 | 4.6 | 6 | 3 | 1 | 4 | No
7 | J118 | J92 | 75 | 132.2 | 6 | 3 | 1 | 4 | No
8 | J92 | J80 | 90 | 156.6 | 6 | 3 | 1 | 4 | No
9 | J80 | J84 | 90 | 6.6 | 6 | 3 | 1 | 4 | No
10 | J80 | J84 | 90 | 54.4 | 6 | 3 | 1 | 4 | No
11 | J84 | J75 | 90 | 128.3 | 6 | 3 | 1 | 4 | No
12 | J84 | J89 | 90 | 3 | 6 | 3 | 1 | 4 | No
13 | J84 | J89 | 90 | 149.8 | 6 | 3 | 1 | 4 | No
14 | J75 | J43 | 110 | 284.4 | 6 | 3 | 1 | 4 | No
15 | j45 | j43 | 110 | 2.4 | 6 | 3 | 1 | 4 | No
16 | j45 | j43 | 110 | 3.3 | 6 | 3 | 1 | 4 | No
17 | j45 | j43 | 110 | 55.9 | 6 | 3 | 1 | 4 | No
18 | J44 | J45 | 125 | 201.9 | 6 | 3 | 1 | 4 | No
19 | J44 | J40 | 125 | 155.8 | 6 | 3 | 1 | 4 | No
20 | J40 | J31 | 125 | 58.2 | 6 | 3 | 1 | 4 | No
21 | J31 | J9 | 140 | 279.9 | 6 | 3 | 1 | 4 | No
22 | J9 | J12 | 160 | 4.4 | 6 | 3 | 1 | 4 | No
23 | J9 | J12 | 160 | 167.4 | 6 | 3 | 1 | 4 | No
24 | J12 | J22 | 160 | 7.9 | 6 | 3 | 1 | 4 | No
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  | MEDHAJ CONSULTANCY (THIRD PARTY INS.) |  |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  | DESIGNATION |  |  |  |  | DESIGNATION
NAME |  |  | NAME |  |  |  |  | NAME
SIGN.with date |  |  | SIGN.with date |  |  |  |  | SIGN.with date

## padampur pipe issue
Block |  | Mangraura
GP |  | PADAMPUR
Agency Name/ Work Order No |  | MAA SHARDHA CONSTRUCTION
63MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
1 | 2023-04-06 | 1300 |  |  | 20004 | 63 | 11213 | 9293 | 8529 | 764
2 |  | 3043 |  |  | 20003 | 75 | 898 | 900 | 843 | 57
3 | 2023-03-22 | 3000 |  |  | 20001 | 90 | 489 | 500 | 489 | 11
4 | 2023-04-11 | 1950 |  |  | 20005 | 110 | 347 | 400 | 347 | 53
[6 empty] | 125 | 408 | 408 | 408 | 0
[6 empty] | 140 | 200 | 274 | 274 | 0
[6 empty] | 160 | 188 | 192 | 0 | 192
| TOTAL | 9293
75MM
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
1 | 2023-04-06 | 450 |  |  | 20004 |  | Specials |  | Specification | Issue | Laid | Balance Against Issue | Remarks
2 | 2023-04-11 | 450 |  |  | 20005 |  | Equal TEE |  | 63mm
3 | [8 empty] | 75mm
3 | [8 empty] | 90mm
110mm
125mm
140mm
160mm
200mm
250mm
[7 empty] | Branch TEE |  | 63mm X 50mm
| TOTAL | 900 | [6 empty] | 75mm X 50mm
90MM | [8 empty] | 90 mm X 50 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  | 110mm X 50mm
1 | 2023-04-06 | 300 |  |  | 20004 |  |  |  | 125mm X 50mm
2 | 2023-04-11 | 200 |  |  | 20005 |  |  |  | 140mm X 50mm
160mm X 50mm
75 mm X 63 mm
90 mm X 63 mm
90 mm X 75 mm
110mm X 63 mm
110mm X 75 mm
110mm X 90 mm
125mm X 63 mm
| TOTAL | 500 | [6 empty] | 125mm X75 mm
110MM | [8 empty] | 125mm X90 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  | 125mm X 110mm
1 | 2023-04-06 | 400 |  |  | 20004 |  |  |  | 140mm X 63 mm
2 | [8 empty] | 140mm X 75 mm
3 | [8 empty] | 140mm X 90 mm
4 | [8 empty] | 140mm X 110mm
5 | [8 empty] | 140mm X 125 mm
6 | [8 empty] | 160mm X 63 mm
7 | [8 empty] | 160mm X 75 mm
8 | [8 empty] | 160mm X 90 mm
160mm X 110 mm
| TOTAL | 400 | [6 empty] | 160mm X 125 mm
160mm X 140 mm
125MM | [8 empty] | 200mm X 63 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  | 200mm X 75 mm
1 | 2023-02-26 | 408 |  |  | 20002 |  |  |  | 200mm X 90 mm
2 | [8 empty] | 200mm X 110 mm
3 | [8 empty] | 200mm X 125 mm
4 | [8 empty] | 200mm X 140 mm
5 | [8 empty] | 200mm X 160 mm
6 | [8 empty] | 250mm X 63 mm
7 | [8 empty] | 250mm X 75 mm
8 | [8 empty] | 250mm X 90 mm
250mm X 110 mm
| TOTAL | 408 | [6 empty] | 250mm X 140 mm
250mm X 160 mm
140MM | [6 empty] | 4-Way TEE |  | 63mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  | 75mm
1 | 2023-02-26 | 274 |  |  | 20002 |  |  |  | 90mm
110mm
125mm
140mm
160mm
200mm
250mm
| TOTAL | 274 |  |  |  |  | Reducer |  | 75mm X 63 mm
160MM | [8 empty] | 90mm X 63 mm
Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  | 90mm X 75 mm
1 | 2023-02-26 | 192 |  |  | 20002 |  |  |  | 110 mm X 63 mm
110 mm X 75 mm
110 mm X 90 mm
125 mm X 63 mm
125 mm X 75 mm
125 mm X 90 mm
125 mm X 110 mm
| TOTAL | 192 | [6 empty] | 140mm X 63 mm
140mm X 75 mm
140mm X 90 mm
140mm X 110mm
140mm X 125mm
160mm X 63 mm
160mm X 75 mm
160mm X 90 mm
160mm X 110mm
160mm X 125mm
160mm X 140mm
200mm X 63mm
200mm X 75mm
200mm X 90mm
200mm X 110mm
200mm X 125mm
200mm X 140mm
200mm X 160mm
250mm X 63mm
250mm X 75mm
250mm X 110mm
250mm X 140mm
250mm X 160mm
250mm X 200mm
[7 empty] | End Caps |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
[7 empty] | Bends | 63mm | 90 Deg
45 Deg
[8 empty] | 75mm | 90 Deg
45 Deg
[8 empty] | 90mm | 90 Deg
45 Deg
[8 empty] | 110mm | 90 Deg
45 Deg
[8 empty] | 125mm | 90 Deg
45 Deg
[8 empty] | 140mm | 90 Deg
45 Deg
[8 empty] | 160mm | 90 Deg
45 Deg
[8 empty] | 200mm | 90 Deg
45 Deg
[8 empty] | 250mm | 90 Deg
45 Deg
[7 empty] | Stubbends |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[7 empty] | MS Flanges |  | 50mm
63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
[7 empty] | Air Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[7 empty] | Sluice Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
250mm
[7 empty] | Scour Valves |  | 63mm
75mm
90mm
110mm
125mm
140mm
160mm
200mm
DI Specials
[7 empty] | DI Bends | 200mm | 90 Deg
45 Deg
22 Deg
[8 empty] | 250mm | 90 Deg
45 Deg
22 Deg
[7 empty] | DI Branch TEE |  | 200mmx80mm
200mmx100mm
200mmx150mm
250mmx80mm
250mmx150mm
250mmx200mm
[7 empty] | DI Reducer Both Socket |  | 200mmx80mm
200mmx100mm
200mmx150mm
[7 empty] | DI Reducer Double Flanged |  | 150mmx100mm
200mmx100mm
200mmx150mm
250mmx150mm
250mmx200mm
[7 empty] | DI Flange Socket |  | 200mm
[7 empty] | DI Tail Piece 0.3m length |  | 80mm
100mm
150mm
200mm
250mm
[7 empty] | DI Equal TEE All Side Socket |  | 200mm
250mm
[7 empty] | DI 4 Way |  | 200mm
250mm
[7 empty] | Nuts & Bolts |  | Length:140mm, Dia:16mm
[7 empty] | Packing Sheet |  | 3mm Thick

## Sarsathpur
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Sarsathpur ( Patti Block) Pipeline Measurement Sheet
#REF!
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | DI 250mm
1 | 2023-06-05 | J-264 | J-253 | BT(S) | HDPE | 333 | [7 empty] | 333
2 | 2023-06-05 | J-253 | J-261 | BT(S) | HDPE | 39 | [7 empty] | 372
3 | 2023-06-05 | J-261 | J-262 | BT(S) | HDPE | 41 | [7 empty] | 413
4 | 2023-06-05 | J-262 | J-263 | BT(S) | HDPE | 18 | [7 empty] | 431
5 | 2023-06-05 | J-263 | J-260 | BT(S) | HDPE | 62 | [7 empty] | 493
6 | 2023-06-05 | J-260 | J-257 | BT(S) | HDPE | 63 | [7 empty] | 556
7 | 2023-06-05 | J-257 | J-258 | BT(S) | HDPE | 519 | [7 empty] | 1075
8 | 2023-06-05 | J-258 | J-266 | BT(S) | HDPE | 105 | [7 empty] | 1180
9 | 2023-06-05 | J-265 | J-152 | BT(S) | HDPE | 131 | [7 empty] | 1311
10 | 2023-06-05 | J-266 | J-265 | BT(S) | HDPE | 197 | [7 empty] | 1508
11 | 2023-06-05 | J-265 | J-205 | SOIL | HDPE | 106 | [7 empty] | 1614
12 | 2023-06-05 | J-222 | J-203 | SOIL | HDPE | 161 | [7 empty] | 1775
13 | 2023-06-05 | J-203 | J-147 | SOIL | HDPE | 458 | [7 empty] | 2233
14 | 2023-06-05 | J-147 | J-165 | SOIL | HDPE | 447 | [7 empty] | 2680
15 | 2023-06-10 | J-165 | J-105 | SOIL | HDPE | 430 | [7 empty] | 3110
16 | 2023-06-11 | J-165 | J-133 | SOIL | HDPE | 120 | [7 empty] | 3230
17 | 2023-06-11 | J-105 | J-1 | SOIL | HDPE | 51 | [7 empty] | 3281
18 | 2023-06-19 | J-102 | J-156 |  | HDPE |  |  | 300 | [5 empty] | 3581
19 | 2023-06-21 | J-121 | J-147 |  | HDPE | 479 | [7 empty] | 4060
20 | 2023-06-21 | J-78 | J-140 |  | HDPE | 384 | [7 empty] | 4444
21 | 2023-06-22 | J-54 | J-52 |  | HDPE | 73 | [7 empty] | 4517
22 | 2023-06-22 | J-48 | J-54 |  | HDPE | 426 | [7 empty] | 4943
23 | 2023-06-22 | J-56 | J-23 |  | HDPE | 229 | [7 empty] | 5172
24 | 2023-06-22 | J-115 | J-195 |  | HDPE | 113 | [7 empty] | 5285 |  | SARSATHPUR
25 | 2023-06-22 | J-75 | J-115 |  | HDPE | 450 | [7 empty] | 5735 |  | Sarsathpur
26 | 2023-06-22 | J-73 | J-75 |  | HDPE | 110 | [7 empty] | 5845
27 | 2023-06-22 | J-67 | J-73 |  | HDPE | 40 | [7 empty] | 5885
28 | 2023-07-07 | J-62 | J-64 |  | HDPE | 36 | [7 empty] | 5921
29 | 2023-07-07 | J-64 | J-67 |  | HDPE | 59 | [7 empty] | 5980
30 | 2023-07-07 | J-67 | J-73 |  | HDPE | 40 | [7 empty] | 6020
31 | 2023-07-07 | J-73 | J-75 |  | HDPE | 110 | [7 empty] | 6130
32 | 2023-07-07 | J-75 | J-115 |  | HDPE | 450 | [7 empty] | 6580
33 | 2023-07-07 | J-115 | J-195 |  | HDPE | 113 | [7 empty] | 6693
34 | 2023-07-11 | J-2 | J-14 |  | HDPE | [6 empty] | 117 |  | 6810
35 | 2023-07-11 | J-14 | J-195 |  | HDPE | [6 empty] | 15 |  | 6825
36 | 2023-07-11 | J-19 | J-31 |  | HDPE | [6 empty] | 29 |  | 6854
37 | [13 empty] | 6854
38 | [13 empty] | 6854
39 | [13 empty] | 6854
40 | [13 empty] | 6854
41 | [13 empty] | 6854
42 | [13 empty] | 6854
43 | [13 empty] | 6854
44 | [13 empty] | 6854
45 | [13 empty] | 6854
46 | [13 empty] | 6854
47 | [13 empty] | 6854
48 | [13 empty] | 6854
49 | [13 empty] | 6854
50 | [13 empty] | 6854
51 | [13 empty] | 6854
52 | [13 empty] | 6854
53 | [13 empty] | 6854
54 | [13 empty] | 6854
55 | [13 empty] | 6854
56 | [13 empty] | 6854
57 | [13 empty] | 6854
58 | [13 empty] | 6854
59 | [13 empty] | 6854
60 | [13 empty] | 6854
61 | [13 empty] | 6854
62 | [13 empty] | 6854
63 | [13 empty] | 6854
64 | [13 empty] | 6854
65 | [13 empty] | 6854
66 | [13 empty] | 6854
67 | [13 empty] | 6854
68 | [13 empty] | 6854
69 | [13 empty] | 6854
70 | [13 empty] | 6854
71 | [13 empty] | 6854
72 | [13 empty] | 6854
73 | [13 empty] | 6854
74 | [13 empty] | 6854
75 | [13 empty] | 6854
76 | [13 empty] | 6854
77 | [13 empty] | 6854
78 | [13 empty] | 6854
79 | [13 empty] | 6854
80 | [13 empty] | 6854
81 | [13 empty] | 6854
82 | [13 empty] | 6854
83 | [13 empty] | 6854
84 | [13 empty] | 6854
85 | [13 empty] | 6854
86 | [13 empty] | 6854
87 | [13 empty] | 6854
88 | [13 empty] | 6854
89 | [13 empty] | 6854
90 | [13 empty] | 6854
91 | [13 empty] | 6854
92 | [13 empty] | 6854
93 | [13 empty] | 6854
94 | [13 empty] | 6854
95 | [13 empty] | 6854
96 | [13 empty] | 6854
97 | [13 empty] | 6854
98 | [13 empty] | 6854
99 | [13 empty] | 6854
100 | [13 empty] | 6854
101 | [13 empty] | 6854
102 | [13 empty] | 6854
103 | [13 empty] | 6854
104 | [13 empty] | 6854
105 | [13 empty] | 6854
106 | [13 empty] | 6854
107 | [13 empty] | 6854
108 | [13 empty] | 6854
109 | [13 empty] | 6854
110 | [13 empty] | 6854
111 | [13 empty] | 6854
112 | [13 empty] | 6854
113 | [13 empty] | 6854
114 | [13 empty] | 6854
115 | [13 empty] | 6854
Work Done Qty In ( Rmt ) : | [5 empty] | 6393 | 0 | 300 | 0 | 0 | 0 | 161 | 0
With Held 10 % of the Total Quantity ( In RMT ) | [11 empty] | 16.1 | 0
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 6393 | 0 | 300 | 0 | 0 | 0 | 144.9 | 0
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) AGM Project Incharge

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
#REF! | [8 empty] | #REF!
Sl NO | Description | Units | Padampur | Sarsathpur | Quantity In Rmt |  | Balance Qty | SAP Entry | Remarks
[5 empty] | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 18000 | 15174 | 2826 | 8529 | 6645 |  | TRUE | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 900 | 897.5 | 2.5 | 843 | 54.5 |  | TRUE | 63 | 11213 | 9293 | 8529 | 764
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1000 | 798.7 | 201.3 | 489 | 309.7 |  | TRUE | 75 | 898 | 900 | 843 | 57
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 400 | 346 | 54 | 347 | -1 |  | TRUE | 90 | 489 | 500 | 489 | 11
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1592 | 415.9 | 1176.1 | 408 | 7.9 | 132.6667 | TRUE | 110 | 347 | 400 | 347 | 53
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1392 | 279.9 | 1112.1 | 274 | 5.9 | 116 | TRUE | 125 | 408 | 408 | 408 | 0
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1032 | 340.7 | 691.3 |  | 340.7 | 86 | TRUE | 140 | 200 | 274 | 274 | 0
| Total Qty In ( Rmt ) = |  |  |  | 24316 | 18252.7 | 6063.3 |  |  |  | FALSE | 160 | 188 | 192 | 0 | 192
2 | Specials :- | [9 empty] | TRUE
| Equal Tee | [9 empty] | TRUE
| 63mm | No's |  |  | 30 |  | 30 |  | 0 |  | TRUE
| 90mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 110mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 30 | 0 | 30 |  |  |  | TRUE
| Branch TEE | [9 empty] | TRUE
| 90 mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 90 mm X 75 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 110mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 160mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 160mm X 90 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| 4 Way Tee | [9 empty] | TRUE
| 75mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 160mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| Reducers | [9 empty] | TRUE
| 75mm X 63 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 90mm X 63 mm | No's |  |  | 5 |  | 5 |  |  |  | TRUE
| 90mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 110 mm X 63 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 110 mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 160 mm X 63 mm | No's |  |  | 5 |  | 5 |  |  |  | TRUE
| 125 mm X 110 mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 140mm X 125 mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 160mm X 140mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 200mm X 110mm | [5 empty] | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 16 | 0 | 16 |  |  |  | TRUE
| Bends | [9 empty] | TRUE
| 90mm ( 45 Deg ) | [5 empty] | 0 |  |  |  | TRUE
| 140mm ( 45 Deg ) | [5 empty] | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| End Caps | [9 empty] | TRUE
| 63mm | No's |  |  | 80 |  | 80 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 80 | 0 | 80 |  |  |  | TRUE
| Bends | [9 empty] | TRUE
| 160mm (90 deg) | No's |  |  |  |  | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
Prepared by Checked By Store AM PMX Project Incharge