## WO Vs Execution
POWERMECH PROJECTS LIMITED
UP JAL NIGAM RWSS PROJECT
PRAYAGRAJ DIV - PRATAPGARH DIST.
WO Qty's Vs Execution Qty's
#REF! | [19 empty] | #REF! |  | #REF!
S.No | Description of Work | Maruaan & Saraynankar | [14 empty] | Total |  |  |  |  | Remarks | chandadhi & darouli
|  | #REF! | [14 empty] | #REF! | [5 empty] | #REF!
1 | HDPE Pipes - Excavation , Lowering & laying , Jointing , specials fixing, Backfilling , Testing & Commssioning - As per Approved Drawings | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill |  | WO Qty's | Laying Up to Date | Billed up to Date | Up to Previous | This Bill
1.1 | 63 mm HDPE | 10221 | 7140 | 7140 | 6365 | 775 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 10221 | 7140 | 7140 | 6365 | 775 |  | 5421 | 2365 | - | - | 2365
1.2 | 75 mm HDPE | 891 | 864 | 864 | 864 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 891 | 864 | 864 | 864 | 0 |  | 277
1.3 | 90 mm HDPE | 523 | 511 | 511 | 511 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 523 | 511 | 511 | 511 | 0 |  | 166
1.4 | 110mm HDPE | 748 | 502 | 502 | 502 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 748 | 502 | 502 | 502 | 0 |  | 0
1.5 | 125mm HDPE | 1020 | 513 | 513 | 343 | 170 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 1020 | 513 | 513 | 343 | 170 |  | 0
1.6 | 140mm HDPE | 1423 | 964 | 964 | 671 | 293 |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 1423 | 964 | 964 | 671 | 293 |  | 685
1.7 | 160mm HDPE | 546 | 549 | 546 | 546 | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 | 546 | 549 | 546 | 546 | 0 |  | 322
1.8 | 200mm HDPE | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub Total Total |  | 15372 | 11043 | 11040 | 9802 | 1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15372 | 11043 | 11040 | 9802 | 1238 |  | 6871 |  |  |  | 2365
2 | Dismatling & Restoration of Roads
2.1 | For B.O.E Surface | 709.682 | [14 empty] | 709.682 | 0 | 0 | 0 | 0
2.2 | For Bituminous Surface | 1448.29 | [14 empty] | 1448.29 | 0 | 0 | 0 | 0
2.3 | For Interlocking Surface | 184.861 | [14 empty] | 184.861 | 0 | 0 | 0 | 0
2.4 | For CC Road | 130.317 | [14 empty] | 130.317 | 0 | 0 | 0 | 0
3 | Construction of Valve Chambers
a) | Sluice Valve Chamber- 1000(L)X1200(W)X1300(H)
b) | Scour Valve Chamber- 1000(L)X1200(W)X1300(H)
c) | Air valve Chamber - 350(L)X350(W)X500(H)
d) | Fire Hydrant Chamber - 750(L)X450(W)X1000(H)
4 | Fixing of FHTCS excluding Supply.
5 | Stand post Fixing with required accessories excluding Supply
6 | Nala/Culvert Crossing ( width -3.5 m) upto Dia 300
[23 empty] | 63 | 75 | 90 | 110 | 125 | 140 | 160
[23 empty] | 10401 | 207 | 532 | 510 | 0 | 0 | 0 | 11650
[23 empty] | 17783 | 484 | 762 | 509 | 775 | 685 | 322 | 21320
[22 empty] | RUDRA | 5421 | 277 | 166 | 0 | 0 | 685 | 322 | 6871
[22 empty] | ROHIT | 12362 | 207 | 596 | 509 | 775 | 0 | 0 | 14449
Prepared By Site Engineer ( AM-SMX ) ( AM-PMX ) AGM Project Incharge

## Saraynankar
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Maruaan & Saraynankar (Baba Belkharnath Dham ) Laying Qty's
#REF!
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [6 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
1 | 2023-03-03 | J-119 | J-146 | KC | HDPE | 45 | [6 empty] | 45
2 | 2023-03-03 | J-120 | J-119 | KC | HDPE | 82 | [6 empty] | 127
3 | 2023-03-04 | J-117 | J-128 | KC | HDPE | 180 | [6 empty] | 307
4 | 2023-03-17 | J-133 | J-136 | KC | HDPE | 212 | [6 empty] | 519
5 | 2023-03-17 | J-136 | J-137 | KC | HDPE | 198 | [6 empty] | 717
6 | 2023-03-21 | J-137 | J-138 | KC | HDPE | 112 | [6 empty] | 829
7 | 2023-03-21 | J-138 | J-125 | KC | HDPE | 207 | [6 empty] | 1036
8 | 2023-03-24 | J-118 | J-120 | KC | HDPE | 93 | [6 empty] | 1129
9 | 2023-03-24 | J-118 | J-116 | KC | HDPE |  |  | 90 |  |  |  |  | 1219
10 | 2023-03-25 | J-116 | J-103 | KC | HDPE |  |  | 130 |  |  |  |  | 1349
11 | 2023-03-27 | J-103 | J-83 | KC | HDPE |  |  |  | 88 |  |  |  | 1437
12 | 2023-03-28 | J-83 | J-75 | KC | HDPE |  |  |  | 18 |  |  |  | 1455
13 | 2023-03-28 | J-75 | J-72 | BOE | HDPE |  |  |  | 90 |  |  |  | 1545
14 | 2023-03-28 | J-72 | J-50 | BOE | HDPE |  |  |  | 98 |  |  |  | 1643
15 | 2023-03-31 | J-5 | J-25 | BOE | HDPE | [5 empty] | 212 |  | 1855
16 | 2023-04-01 | J-50 | J-31 | BOE | HDPE | 150 | [6 empty] | 2005
17 | 2023-04-03 | J-50 | J-31 | BOE | HDPE | 219 | [6 empty] | 2224
18 | 2023-04-04 | J-31 | J-27 | BOE | HDPE | 28 | [6 empty] | 2252
19 | 2023-04-04 | J-31 | J-6 | BOE | HDPE | 65 | [6 empty] | 2317
20 | 2023-04-04 | J-6 | J-32 | KC | HDPE | 11 | [6 empty] | 2328
21 | 2023-04-04 | J-103 | J-95 | KC | HDPE | 20 | [6 empty] | 2348
22 | 2023-04-05 | J-75 | J-82 | KC | HDPE | 42 | [6 empty] | 2390
23 | 2023-04-05 | J-103 | J-95 | KC | HDPE | 30 | [6 empty] | 2420
24 | 2023-04-05 | J-32 | J-69 | KC | HDPE | 53 | [6 empty] | 2473
25 | 2023-04-07 | J-31 | J-82 | KC | HDPE | 220 | [6 empty] | 2693
26 | 2023-04-10 | J-52A | J-52 | BOE | HDPE | [6 empty] | 160 | 2853
27 | 2023-04-11 | J- 52 | J- 64 | BOE | HDPE | 190 | [6 empty] | 3043
28 | 2023-04-13 | J-55 | J-49 | KC | HDPE | 91 | [6 empty] | 3134
29 | 2023-04-13 | J-52 | J-37 | KC | HDPE | 22 | [6 empty] | 3156
30 | 2023-04-14 | J-52A | J- 55 | KC | HDPE | [5 empty] | 99 |  | 3255
31 | 2023-04-15 | J-52 | J-63 | KC | HDPE | [6 empty] | 69 | 3324
32 | 2023-04-22 | J-63 | J-05 | BOE | HDPE | [6 empty] | 128 | 3452
33 | 2023-04-24 | J-05 | J-25 | BOE | HDPE | [5 empty] | 154 |  | 3606
34 | 2023-04-25 | J-02 | J-05 | BOE | HDPE | [6 empty] | 192 | 3798
35 | 2023-04-26 | J-05 | J-24 | KC | HDPE | [5 empty] | 206 |  | 4004
36 | 2023-03-31 | J-50 | J-48 | BOE | HDPE |  |  |  |  | 212 |  |  | 4216
37 | 2023-05-29 | J-142 | J-139 | KC | HDPE | 67 | [6 empty] | 4283
38 | 2023-05-29 | J-142 | J-125 | KC | HDPE | 207 | [6 empty] | 4490
39 | 2023-05-29 | J-139 | J-130 | KC | HDPE | 96 | [6 empty] | 4586
40 | 2023-05-29 | J-130 | J-122 | KC | HDPE | 310 | [6 empty] | 4896
41 | 2023-05-30 | J-115 | J-99 | KC | HDPE |  |  | 152 |  |  |  |  | 5048
42 | 2023-05-30 | J-99 | J-85 | KC | HDPE |  |  | 76 |  |  |  |  | 5124
43 | 2023-05-30 | J-85 | J-79 | KC | HDPE |  |  | 63 |  |  |  |  | 5187
44 | 2023-05-30 | J-109 | J-115 | KC | HDPE |  | 503 | [5 empty] | 5690
45 | 2023-05-30 | J-115 | J-78 | KC | HDPE | 270 | [6 empty] | 5960
46 | 2023-05-31 | J-130 | J-129 | KC | HDPE | 182 | [6 empty] | 6142
47 | 2023-05-31 | J-129 | J-134 | KC | HDPE | 18 | [6 empty] | 6160
48 | 2023-05-31 | J-129 | J-127 | KC | HDPE | 159 | [6 empty] | 6319
49 | 2023-05-31 | J-110 | J-54 | KC | HDPE | 309 | [6 empty] | 6628
50 | 2023-05-31 | J-54 | J-56 | KC | HDPE | 15 | [6 empty] | 6643
51 | 2023-05-31 | J-54 | J-25 | KC | HDPE | 171 | [6 empty] | 6814
52 | 2023-05-31 | J-25 | J-86 | KC | HDPE | 216 | [6 empty] | 7030
53 | 2023-05-31 | J-25 | J-46 | KC | HDPE | 27 | [6 empty] | 7057
54 | 2023-05-31 | J-46 | J-87 | KC | HDPE | 15 | [6 empty] | 7072
55 | 2023-05-31 | J-46 | J-35 | KC | HDPE | 35 | [6 empty] | 7107
56 | 2023-05-31 | J-133 | J-135 | KC | HDPE | 71 | [6 empty] | 7178
57 | 2023-05-31 | J-135 | J-131 | KC | HDPE | 114 | [6 empty] | 7292
58 | 2023-05-31 | J-135 | J-126 | KC | HDPE | 159 | [6 empty] | 7451
59 | 2023-06-01 | J-99 | J-68 | KC | HDPE | 206 | [6 empty] | 7657
60 | 2023-06-01 | J-110 | J-113 | KC | HDPE | 61 | [6 empty] | 7718
61 | 2023-06-01 | J-113 | J-77 | KC | HDPE | 193 | [6 empty] | 7911
62 | 2023-06-01 | J-110 | J-88 | KC | HDPE | 127 | [6 empty] | 8038
63 | 2023-06-01 | J-88 | J-92 | KC | HDPE | 52 | [6 empty] | 8090
64 | 2023-06-02 | J-133A | J-133B | KC | HDPE | 70 | [6 empty] | 8160
65 | 2023-06-05 | J-24 | J-23 | KC | HDPE |  |  |  |  | 21 |  |  | 8181
66 | 2023-06-05 | J-23 | J-22 | KC | HDPE |  |  |  |  | 27 |  |  | 8208
67 | 2023-06-05 | J-22 | J-45 | KC | HDPE |  |  |  |  | 83 |  |  | 8291
68 | 2023-07-12 | J-87 | J-87A | KC | HDPE | 350 | [6 empty] | 8641
69 | 2023-07-13 | J-87 | J-87A | KC | HDPE | 150 | [6 empty] | 8791
70 | 2023-07-14 | J-87 | J-87A | KC | HDPE | 50 | [6 empty] | 8841
71 | 2023-07-18 | J-104 | J-84 | KC | HDPE |  | 95 | [5 empty] | 8936
72 | 2023-07-18 | J-84 | J-97 | KC | HDPE |  | 138 | [5 empty] | 9074
73 | 2023-07-20 | J-107 | J-77 | KC | HDPE |  |  |  | 108 |  |  |  | 9182
74 | 2023-07-20 | J-77 | J-77A | KC | HDPE |  |  |  | 100 |  |  |  | 9282
75 | 2023-07-21 | J-116 | J-104 | KC | HDPE |  | 128 | [5 empty] | 9410
76 | 2023-07-21 | J-104 | J-93 | KC | HDPE | 143 | [6 empty] | 9553
77 | 2023-07-22 | J-87A | J-87B | KC | HDPE | 209 | [6 empty] | 9762
78 | 2023-07-22 | J-87A | J-87C | KC | HDPE | 43 | [6 empty] | 9805
Work Done Qty In ( Rmt ) : | [5 empty] | 6365 | 864 | 511 | 502 | 343 | 671 | 549 | 9.802
With Held Quantites ( In RMT ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 6365 | 864 | 511 | 502 | 343 | 671 | 546 |  |  | FALSE
[5 empty] | WO Qtys | 10221 | 891 | 523 | 748 | 1020 | 1423 | 546
Prepared By Site Engineer ( Sr Eng/AM-SMX ) ( AM-PMX ) AGM Project Incharge

## chandauadhi & darauoli
Mangraura
chandauadi & darauoli
RUDRA Enterprises
S.NO | DATE | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) |  |  |  |  | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 140mm | 160MM
1 | 2023-10-04 | J30 | J49 |  | HDPE | 430 |  |  |  |  | 430
2 | 2023-10-06 | J53 | J51 |  | HDPE | 80 |  |  |  |  | 510
3 | 2023-10-06 | J51 | J75 |  | HDPE | 132 |  |  |  |  | 642
4 | 2023-10-06 | J75 | J101 |  | HDPE | 139 |  |  |  |  | 781
5 | 2023-10-08 | J108 | J109 |  | HDPE | 83 |  |  |  |  | 864
6 | 2023-10-08 | J109 | J110 |  | HDPE | 133 |  |  |  |  | 997
7 | 2023-10-08 | J110 | J106 |  | HDPE | 12 |  |  |  |  | 1009
8 | 2023-10-08 | J106 | J105 |  | HDPE | 116 |  |  |  |  | 1125
9 | 2023-10-08 | J105 | J103 |  | HDPE | 43 |  |  |  |  | 1168
10 | 2023-10-09 | J101 | J86 |  | HDPE | 138 |  |  |  |  | 1306
11 | 2023-10-09 | J86 | J88 |  | HDPE | 40 |  |  |  |  | 1346
12 | 2023-10-09 | J88 | J92 |  | HDPE | 47 |  |  |  |  | 1393
13 | 2023-10-09 | J92 | J108 |  | HDPE | 74 |  |  |  |  | 1467
14 | 2023-10-10 | J108 | J115 |  | HDPE | 156 |  |  |  |  | 1623
15 | 2023-10-10 | J115 | J113 |  | HDPE | 157 |  |  |  |  | 1780
16 | 2023-10-12 | J51 | J43 |  | HDPE | 64 |  |  |  |  | 1844
17 | 2023-10-12 | J43 | J39 |  | HDPE | 16 |  |  |  |  | 1860
18 | 2023-10-12 | J39 | J32 |  | HDPE | 57 |  |  |  |  | 1917
19 | 2023-10-12 | J115 | J85 |  | HDPE | 274 |  |  |  |  | 2191
20 | 2023-10-12 | J85 | J109 |  | HDPE | 50 |  |  |  |  | 2241
21 | 2023-10-12 | J71 | J67 |  | HDPE | 124 |  |  |  |  | 2365
22

## Draft (hidden)
Block |  | Sadar
GP |  | Jaithipurkathar
Total Length (M) |  | 14356
FHTC (No's) |  | 653
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Laying Qty's
#REF!
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [6 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
1 | [12 empty] | 0
2 | [12 empty] | 0
3 | [12 empty] | 0
4 | [12 empty] | 0
5 | [12 empty] | 0
6 | [12 empty] | 0
7 | [12 empty] | 0
8 | [12 empty] | 0
9 | [12 empty] | 0
10 | [12 empty] | 0
11 | [12 empty] | 0
12 | [12 empty] | 0
13 | [12 empty] | 0
14 | [12 empty] | 0
15 | [12 empty] | 0
16 | [12 empty] | 0
17 | [12 empty] | 0
18 | [12 empty] | 0
19 | [12 empty] | 0
20 | [12 empty] | 0
21 | [12 empty] | 0
22 | [12 empty] | 0
23 | [12 empty] | 0
24 | [12 empty] | 0
25 | [12 empty] | 0
26 | [12 empty] | 0
27 | [12 empty] | 0
28 | [12 empty] | 0
29 | [12 empty] | 0
30 | [12 empty] | 0
31 | [12 empty] | 0
32 | [12 empty] | 0
33 | [12 empty] | 0
34 | [12 empty] | 0
35 | [12 empty] | 0
36 | [12 empty] | 0
37 | [12 empty] | 0
38 | [12 empty] | 0
39 | [12 empty] | 0
40 | [12 empty] | 0
41 | [12 empty] | 0
42 | [12 empty] | 0
43 | [12 empty] | 0
44 | [12 empty] | 0
45 | [12 empty] | 0
46 | [12 empty] | 0
47 | [12 empty] | 0
48 | [12 empty] | 0
49 | [12 empty] | 0
50 | [12 empty] | 0
51 | [12 empty] | 0
52 | [12 empty] | 0
53 | [12 empty] | 0
54 | [12 empty] | 0
55 | [12 empty] | 0
56 | [12 empty] | 0
57 | [12 empty] | 0
58 | [12 empty] | 0
59 | [12 empty] | 0
60 | [12 empty] | 0
61 | [12 empty] | 0
62 | [12 empty] | 0
63 | [12 empty] | 0
64 | [12 empty] | 0
65 | [12 empty] | 0
66 | [12 empty] | 0
67 | [12 empty] | 0
68 | [12 empty] | 0
69 | [12 empty] | 0
70 | [12 empty] | 0
71 | [12 empty] | 0
0
Work Done Qty In ( Rmt ) : | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
With Held Quantites If Any ( In RMT ) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Quantity Considered for bill ( In RMT )= | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TRUE
[5 empty] | WO Qtys | [6 empty] | 0
Prepared By Site Engineer ( Sr Eng/AM-SMX ) ( AM-PMX ) AGM Accounts Project Incharge

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
Name of the Contractor : 210524_ Rudra Eneterprises | [10 empty] | #REF!
Sl NO | Description | Units | Sarayjamuari |  |  |  | Total |  | Balance Qty | SAP Entry | Remarks
|  |  | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 1850 | 7140 |  | 0 | 19443 | 9505 | 9938 | 2270 | 7235
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 450 | 864 |  | 0 | 2000 | 864 | 1136 |  | 864
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 400 | 511 |  | 0 | 1100 | 511 | 589 | 220 | 291
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 300 | 502 |  | 0 | 675 | 502 | 173 | 294 | 208
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 456 | 513 |  | 0 | 1032 | 513 | 519 | 212 | 301 |  | 86
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 964 |  | 0 | 1428 | 964 | 464 | 671 | 293 |  | 119
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 549 |  | 0 | 552 | 549 | 3 | 549 | 0 |  | 46
| 200 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | [8 empty] | 0
| Total Qty In ( Rmt ) = | [5 empty] | 26230 | 13408 | 12822
2 | Specials :-
Equal Tee
| 63mm | No's | 25 |  |  |  | 25 | 0 | 25 |  | 0
| 75mm | No's |  |  |  |  | 0 | 0 | 0
| 90mm | No's |  |  |  |  | 0 | 0 | 0
| 140 mm | No's |  |  |  |  | 0 | 0 | 0
| 160mm | No's |  |  |  |  | 0 | 0 | 0
| Total Qty In ( No's ) = | [5 empty] | 25 | 0 | 25
Branch TEE
| 75 mm X 63 mm | No's |  |  |  |  | 10 | 0 | 10 |  | 0 | J-140
| 90 mm X 63 mm | No's | 4 |  |  |  | 4 | 0 | 4 |  | 0 | J-140
| 90 mm X 75 mm | No's |  |  |  |  | 0 | 0 | 0 |  | 0 | J-140
| 110mm X 63 mm | No's | 2 |  |  |  | 2 | 0 | 2 |  | 0 | J-79,J-35,J-152
| 110mm X 90 mm | No's |  |  |  |  | 0 | 0 | 0 |  | 0 | J-79,J-35,J-152
| 140mm X 63 mm | No's |  |  |  |  | 5 | 0 | 5 |  | 0
| 140mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | 0
| 140mm X 90 mm | No's |  |  |  |  | 0 |  |  |  | 0
| 140*125 | No's |  |  |  |  | 1
| 160mm X 63 mm | No's |  |  |  |  | 0 |  |  |  | 0
| 160mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | 0
| 160mm X 90 mm | No's |  |  |  |  | 0 | 0 | 0 |  | 0 | J-68
| Total Qty In ( No's ) = | [5 empty] | 22 | 0 | 21
4 Way Tee
| 75mm | No's |  |  |  |  | 0 | 0 | 0
| 110mm | No's
| 140mm | No's
| 160mm | No's |  |  |  |  | 0 | 0 | 0
| Total Qty In ( No's ) = | [5 empty] | 0 | 0 | 0
Reducers
| 75mm X 63 mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | J-12
| 90mm X 63 mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | J-7
| 90mm X 75 mm | No's |  |  |  |  | 0 | 0 | 0
| 110 mm X 63 mm | No's |  |  |  |  | 0 | 0 | 0 |  | 0 | J-83,J-101
| 110 mm X 90 mm | No's | 1 |  |  |  | 1 | 0 | 1 |  | 0 | J-130
| 140 mm X 63 mm | No's |  |  |  |  | 2 | 0 | 2 |  |  | J-129
| 160*140 | No's |  |  |  |  | 1
| 140 mm X 110 mm | No's |  |  |  |  | 0 | 0 | 0
| 160mm X 90 mm | No's |  |  |  |  | 1 | 0 | 1
| 160mm X 110mm | No's |  |  |  |  | 0 | 0 | 0
| 200mm X 110mm | [5 empty] | 0 | 0 | 0
| Total Qty In ( No's ) = | [5 empty] | 5 | 0 | 4
Bends
| 90mm ( 45 Deg ) | [5 empty] | 0 | 0 | 0
| 160mm ( 90 Deg ) | [5 empty] | 0 | 0 | 0
| Total Qty In ( No's ) = | [5 empty] | 0 | 0 | 0
End Caps
| 63mm | No's | 15 |  |  |  | 15 | 0 | 15 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 15 | 0 | 15
Bends
| 160mm (90 deg) | No's |  |  |  |  | 0 | 0 | 0
| Total Qty In ( No's ) = | [5 empty] | 0 | 0 | 0
Prepared by Checked By Store AM PMX Project Incharge