## Sheet1
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP_____DEHRI DIGAR________Block______mangraura_____________ Pipeline Laying Measurement Sheet
Name of the Contractor : TANISH ENTERPRISES
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 160mm | 180mm | 200mm
1 | 2023-09-05 | J265 | J264 | KC ROAD | HDPE | 187
2 | 2023-09-05 | J264 | J263 | KC ROAD | HDPE | 151 | [10 empty] | 14
3 | 2023-09-05 | J263 | J254 | KC ROAD | HDPE | 214 | [10 empty] | 105
4 | 2023-09-05 | J254 | J216 | KC ROAD | HDPE | 116 | [10 empty] | 78.5
5 | 2023-09-05 | J260 | J262 | KC ROAD | HDPE | 92 | [10 empty] | 23.8
6 | 2023-09-06 | J79 | J256 | KC ROAD | HDPE | 965 | [10 empty] | 41.2
7 | 2023-09-06 | J256 | J258 | KC ROAD | HDPE | 7 | [10 empty] | 74.8
8 | 2023-09-07 | J264 | J260 | KC ROAD | HDPE | 246 | [10 empty] | 24.5
9 | 2023-09-07 | J258 | J259 | KC ROAD | HDPE | 218 | [10 empty] | 18.5
10 | 2023-09-07 | J216 | J205 | KC ROAD | HDPE |  |  |  | 208 | [7 empty] | 60
11 | 2023-09-08 | J205 | J218 | KC ROAD | HDPE |  | 372 | [9 empty] | 29.5
12 | 2023-09-08 | J218 | J220 | KC ROAD | HDPE |  | 24 | [9 empty] | 55.4
13 | 2023-09-08 | J220 | J213 | KC ROAD | HDPE | 367 | [10 empty] | 25.4
14 | 2023-09-08 | J213 | J221 | KC ROAD | HDPE |  | 42 | [9 empty] | 15.4
15 | 2023-09-09 | J220 | J226 | KC ROAD | HDPE | 56 | [10 empty] | 77.3
16 | 2023-09-09 | J226 | J239 | KC ROAD | HDPE | 120 | [10 empty] | 24.5
17 | 2023-09-09 | J213 | J221 | KC ROAD | HDPE |  | 104 | [9 empty] | 22.1
18 | 2023-09-11 | J221 | J225 | KC ROAD | HDPE | 40 | [10 empty] | 47.5
19 | 2023-09-11 | J240 | J245 | KC ROAD | HDPE | 207 | [10 empty] | 19
20 | 2023-09-11 | J222 | J233 | KC ROAD | HDPE | 45 | [10 empty] | 39.9
21 | 2023-09-12 | J1A | J1B | KC ROAD | HDPE | 64 | [10 empty] | 18.4
22 | 2023-09-20 | J244 | J238 | KC ROAD | HDPE | 173 | [10 empty] | 123.5
23 | 2023-09-20 | J232 | J231 | KC ROAD | HDPE | 20 | [10 empty] | 68.2
24 | 2023-09-20 | J183 | J191 | KC ROAD | HDPE | 108 | [10 empty] | 95.7
25 | 2023-09-20 | J191 | J200 | KC ROAD | HDPE | 127 | [10 empty] | 61.5
26 | 2023-09-21 | j231 | j207 | KC ROAD | HDPE | 236 | [10 empty] | 8.4
27 | 2023-09-21 | j232 | j231 | KC ROAD | HDPE | 100 | [10 empty] | 157
28 | 2023-09-21 | j218 | j219 | KC ROAD | HDPE | 30 | [10 empty] | 22.2
29 | 2023-09-22 | j255 | j253 | KC ROAD | HDPE | 96 | [10 empty] | 69.8
30 | 2023-09-22 | j253 | j250 | KC ROAD | HDPE | 29 | [10 empty] | 84.2
31 | 2023-09-22 | j250 | j248 | KC ROAD | HDPE | 126 | [10 empty] | 28.5
32 | 2023-09-22 | j248 | j246 | KC ROAD | HDPE | 98 | [10 empty] | 117.2
33 | 2023-09-22 | j246 | j216 | KC ROAD | HDPE | 91 | [10 empty] | 16
34 | 2023-09-24 | j207 | j211 | KC ROAD | HDPE | 158 | [10 empty] | 96.3
35 | 2023-09-24 | j211 | j215 | KC ROAD | HDPE | 140 | [10 empty] | 288.8
36 | 2023-09-24 | j239 | j241 | KC ROAD | HDPE | 80 | [10 empty] | 115.1
37 | 2023-09-24 | j239 | j243 | KC ROAD | HDPE | 60 | [10 empty] | 34.2
38 | 2023-09-24 | j235 | j234 | KC ROAD | HDPE | 75 | [10 empty] | 73.5
39 | 2023-09-24 | j183 | j206 | KC ROAD | HDPE |  | 150 | [9 empty] | 47
40 | 2023-09-24 | j185 | j186 | KC ROAD | HDPE | 65 | [10 empty] | 637
41 | 2023-09-25 | j241 | j242 | KC ROAD | HDPE | 45 | [10 empty] | 7
42 | 2023-09-25 | j241a | j241b | KC ROAD | HDPE | 65 | [10 empty] | 275.6
43 | 2023-09-25 | j222 | j223 | KC ROAD | HDPE | 28 | [10 empty] | 11
44 | 2023-09-25 | j46 | j53 | KC ROAD | HDPE | 354 | [10 empty] | 3
45 | 2023-09-25 | j37 | j46 | KC ROAD | HDPE | 83 | [10 empty] | 8
46 | 2023-09-25 | j2 | j5 | KC ROAD | HDPE |  |  | 108
47 | 2023-09-25 | j5 | j7 | KC ROAD | HDPE |  |  | 102
228
Work Done Qty In ( Rmt ) : | [5 empty] | 5482 | 692 | 210 | 208 | 0 | 228 |  |  | 6592
Restricting Exceeded Qty's to WO Qty's
Total Quantity Considered for bill ( In RMT )=
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% | [6 empty] | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks
1.1 | 63 mm HDPE | 16122 | 5482 | 5482 | 5482 |  |  |  |  | 0 | 10411.9 |  | 10411.9 |  |  | 0
1.2 | 75 mm HDPE | 571 | 692 | 692 | 692 |  |  |  |  | 0 | 2054.4 |  | 2054.4 |  |  | 0
1.3 | 90 mm HDPE | 1238 | 210 | 210 | 210 |  |  |  |  | 0 | 1402.8 |  | 1402.8 |  |  | 0
1.4 | 110mm HDPE | 1614 | 208 | 208 | 208 |  |  |  |  | 0 | 1819 |  | 1819 |  |  | 0
1.5 | 125mm HDPE | - | 0 | 0 | 0 |  |  |  |  | 0 | 528 |  | 528 |  |  | 0
1.6 | 140mm HDPE | 309 | 0 | 0 | 0 |  |  |  |  | 0 | 982 |  | 982 |  |  | 0
1.7 | 160mm HDPE | 0 |  | 0 | 0 |  |  |  |  | 0 | 228 |  | 228 |  |  | 0
1.8 | 180mm HDPE |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
1.9 | 200mm HDPE |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
Sub Total = |  | 19854 | 6592 | 6592 | 6592 | 0 |  | 17426.1 | 15760 | 1666.1 |  | 0 | 17426.1 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ AM-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Reconsilation Statement AB (2)
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
Name of the Contractor : 210109_Tanish Project Company (CL36) | [12 empty] | RA Bill-07
Sl NO | Description | Units | Makaipur |  | Basauli |  | Purebhikha and Raigarh |  | Total |  | Balance Qty | SAP Entries | Remarks
|  |  | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 12300 | 10845 |  | 6689 | 14700 | 21284.7 | 75930 | 74163 | 1767 | 43858 | 30305 | TRUE
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 1200 | 1165.5 |  | 1161 | 1550 | 1731.9 | 7235 | 7218.4 | 16.6 | 4146.5 | 3071.9 | TRUE
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 100 | 862.5 |  | 1043 | 2000 | 1504.7 | 7530 | 6031.2 | 1498.8 | 5135.5 | 895.7 | TRUE
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 1155 | 1165.4 |  | 1619 | 900 | 821.3 | 7865 | 7705 | 160 | 5036.4 | 2668.6 | TRUE
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | 0 |  | 1199 | 396 | 332.7 | 3720 | 2463.7 | 1256.3 | 2527 | -63.3 | TRUE
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2544 | 2499.6 |  | 2257 | 840 | 840 | 12036 | 7140.6 | 4895.4 | 5594.6 | 1546 | TRUE
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 216 | 167.4 |  | 1487 |  | 26 | 4428 | 3048.4 | 1379.6 | 1654.4 | 1394 | TRUE
| Total Qty In ( Rmt ) = | [7 empty] | 118744 | 107770.3 | 10973.7 |  |  | TRUE
2 | Specials :- | [12 empty] | TRUE
| Equal Tee | [12 empty] | TRUE
| 63mm | No's | 40 | 17 |  |  |  |  | 385 | 17 | 368 | 17 | 0 | TRUE
| 75mm | No's | 4 | [5 empty] | 22 | 0 | 22 |  | 0 | TRUE
| 90mm | No's | 3 | 2 |  |  |  |  | 25 | 2 | 23 | 2 | 0 | TRUE
| 110mm | No's | 8 | [5 empty] | 34 | 0 | 34 |  | 0 | TRUE
| 140mm | No's | 4 | [5 empty] | 22 | 0 | 22 |  | 0 | TRUE
| 160mm | No's | 1 | [5 empty] | 6 | 0 | 6 |  | 0 | TRUE
| Total Qty In ( No's ) = | [7 empty] | 494 | 19 | 475 |  |  | TRUE
| Branch TEE | [12 empty] | TRUE
| 75 mm X 63 mm | No's | 4 | [5 empty] | 12 | 0 | 12 |  | 0 | TRUE
| 90 mm X 63 mm | No's | 10 | 3 |  |  |  |  | 29 | 3 | 26 | 3 | 0 | TRUE
| 90 mm X 75 mm | No's | 1 | [5 empty] | 5 | 0 | 5 |  | 0 | TRUE
| 110mm X 63 mm | No's | 2 | [5 empty] | 7 | 0 | 7 |  | 0 | TRUE
| 110mm X 90 mm | No's | [6 empty] | 0 | 0 | 0 |  | 0 | TRUE
| 140mm X 63 mm | No's | 4 | [5 empty] | 4 | 0 | 4 |  | 0 | TRUE
| 140mm X 75 mm | No's | [6 empty] | 0 | 0 | 0 |  | 0 | TRUE
| 140mm X 90 mm | No's | [6 empty] | 0 | 0 | 0 |  | 0 | TRUE
| 140mm X 110mm | No's | [6 empty] | 0 | 0 | 0 |  | 0 | TRUE
| Total Qty In ( No's ) = | [7 empty] | 57 | 3 | 54 |  |  | TRUE
| Reducers | [12 empty] | TRUE
| 75mm X 63 mm | No's | 13 | 1 |  |  |  |  | 34 | 1 | 33 | 1 | 0 | TRUE
| 90mm X 63 mm | No's | 6 | 2 |  |  |  |  | 11 | 2 | 9 | 2 | 0 | TRUE
| 90mm X 75 mm | No's | 2 | 1 |  |  |  |  | 13 | 1 | 12 | 1 | 0 | TRUE | 200032204
| 110 mm X 63 mm | No's | 6 | [5 empty] | 16 | 0 | 16 |  | 0 | TRUE
| 110 mm X 75 mm | No's | 1 | [5 empty] | 1 | 0 | 1 |  | 0 | TRUE
| 110 mm X 90 mm | No's | 7 | [5 empty] | 17 | 0 | 17 |  | 0 | TRUE
| 125 mm X 63 mm | No's | [7 empty] | 0 | 0 |  | 0 | TRUE
| 140mm X 63 mm | No's | 8 | [5 empty] | 13 | 0 | 13 |  | 0 | TRUE
| 140mm X 75 mm | No's | 1 | [5 empty] | 1 | 0 | 1 |  | 0 | TRUE
| 140mm X 90 mm | No's | 3 | [5 empty] | 7 | 0 | 7 |  | 0 | TRUE
| 140mm X 110mm | No's | 5 | [5 empty] | 16 | 0 | 16 |  | 0 | TRUE
| 160mm X 63 mm | No's | 2 | [5 empty] | 2 | 0 | 2 |  | 0 | TRUE
| 160mm X 140mm | No's | 4 | [5 empty] | 13 | 0 | 13 |  | 0 | TRUE
| Total Qty In ( No's ) = | [7 empty] | 144 | 4 | 140 |  |  | TRUE
| End Caps | [12 empty] | TRUE
| 63mm | No's | 90 | 20 |  |  |  |  | 382 | 50 | 332 | 50 | 0 | TRUE | 200030277
| Total Qty In ( No's ) = | [7 empty] | 382 | 50 | 332 |  |  | TRUE
| Bend | [12 empty] | TRUE
| 63 mm X 45 Deg |  | 5 | [5 empty] | 5 | 0 | 5 |  | 0 | TRUE
| 63 mm X 90 Deg | [7 empty] | 1 | 0 | 1 |  | 0 | TRUE
| 75 mm X 90 Deg |  | 3 | [5 empty] | 3 | 0 | 3 |  | 0 | TRUE
| 75 mm X 45 Deg |  | 3 | [5 empty] | 3 | 0 | 3 |  | 0 | TRUE
| 90 mm X 90 Deg |  | 4 | [5 empty] | 4 | 0 | 4 |  | 0 | TRUE
| 110 mm X 45 Deg |  | 4 | [5 empty] | 4 | 0 | 4 |  | 0 | TRUE
| 140 mm X 90 Deg |  | 4 | [5 empty] | 4 | 0 | 4 |  | 0 | TRUE
| 140 mm X 45 Deg |  | 2 | [5 empty] | 2 | 0 | 2 |  | 0 | TRUE
| 160 mm X 90 Deg |  | 2 | [6 empty] | 0 |  |  | 0 | TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
Prepared by Checked By Store AM-PMX Project Incharge