## Sheet1
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP_____Barasarai________Block______mangraura_____________ Pipeline Laying Measurement Sheet
Name of the Contractor : AGS Construction | [16 empty] | actor
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [8 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | 180mm | 200mm
[6 empty] | 100 | 100 | 100 | 100 | 100
1 | J4 | J5 | B.T ROAD |  | 63 | 3.2
2 | J4 | J7 |  |  | 63 | 11.5 | [11 empty] | 14
3 | J22 | J21 |  |  | 63 | 9 | [11 empty] | 105
4 | J22 | J21 | BRICK ROAD |  | 63 | 14 | [11 empty] | 78.5
5 | J24 | J23 |  |  | 63 | 105 | [11 empty] | 23.8
6 | J25 | J39 |  |  | 63 | 78.5 | [11 empty] | 41.2
7 | J23 | J39 | BRICK ROAD |  | 63 | 23.8 | [11 empty] | 74.8
8 | J39 | J45 |  |  | 63 | 41.2 | [11 empty] | 24.5
9 | J45 | J53 |  |  | 63 | 74.8 | [11 empty] | 18.5
10 | J72 | J71 |  |  | 63 | 24.5 | [11 empty] | 60
11 | J71 | J70 |  |  | 63 | 18.5 | [11 empty] | 29.5
12 | J70 | J68 |  |  | 63 | 60 | [11 empty] | 55.4
13 | J68 | J52 |  |  | 63 | 29.5 | [11 empty] | 25.4
14 | J52 | J68 | BRICK ROAD |  | 63 | 55.4 | [11 empty] | 15.4
15 | J52 | J50 |  |  | 63 | 25.4 | [11 empty] | 77.3
16 | J52 | J46 |  |  | 63 | 15.4 | [11 empty] | 24.5
17 | J46 | J45 |  |  | 63 | 77.3 | [11 empty] | 22.1
18 | J39 | J38 |  |  | 63 | 24.5 | [11 empty] | 47.5
19 | J38 | J37 | BRICK ROAD |  | 63 | 22.1 | [11 empty] | 19
20 | J38 | J43 | BRICK ROAD |  | 63 | 47.5 | [11 empty] | 39.9
21 | J43 | J46 |  |  | 63 | 19 | [11 empty] | 18.4
22 | J43 | J44 | BRICK ROAD |  | 63 | 39.9 | [11 empty] | 123.5
23 | J68 | J69 | BRICK ROAD |  | 63 | 18.4 | [11 empty] | 68.2
24 | J73 | J74 | BRICK ROAD |  | 63 | 123.5 | [11 empty] | 95.7
25 | J76 | J75 | BRICK ROAD |  | 63 | 68.2 | [11 empty] | 61.5
26 | J76 | J71 |  |  | 63 | 95.7 | [11 empty] | 8.4
27 | J70 | J75 |  |  | 63 | 61.5 | [11 empty] | 157
28 | J89 | J90 | BRICK ROAD |  | 63 | 8.4 | [11 empty] | 22.2
29 | J89 | J90 |  |  | 63 | 157 | [11 empty] | 69.8
30 | J83 | J82 |  |  | 63 | 22.2 | [11 empty] | 84.2
31 | J82 | J88 |  |  | 63 | 69.8 | [11 empty] | 28.5
32 | J82 | J80 |  |  | 63 | 84.2 | [11 empty] | 117.2
33 | J80 | J79 |  |  | 63 | 28.5 | [11 empty] | 16
34 | J80 | J86 |  |  | 63 | 117.2 | [11 empty] | 96.3
35 | J80 | J86 | BRICK ROAD |  | 63 | 16 | [11 empty] | 288.8
36 | J86 | J81 | BRICK ROAD |  | 63 | 96.3 | [11 empty] | 115.1
37 | J92 | J93 |  |  | 63 | 288.8 | [11 empty] | 34.2
38 | J36 | J32 |  |  | 63 | 115.1 | [11 empty] | 73.5
39 | J32 | J33 | BRICK ROAD |  | 63 | 34.2 | [11 empty] | 47
40 | J32 | J30 | BRICK ROAD |  | 63 | 73.5 | [11 empty] | 637
41 | J30 | J27 |  |  | 63 | 47 | [11 empty] | 7
42 | J79 | J133 |  |  | 63 | 637 | [11 empty] | 275.6
43 | J133 | J140 |  |  | 63 | 7 | [11 empty] | 11
44 | J133 | J140 |  |  | 63 | 275.6 | [11 empty] | 3
45 | J133 | J140 |  |  | 63 | 11 | [11 empty] | 8
46 | J133 | J140 | B.T ROAD |  | 63 | 3 | [11 empty] | 113
47 | J144 | J144A |  |  | 63 | 8 | [11 empty] | 66.3
48 | J144A | J144B |  |  | 63 | 113 | [11 empty] | 73
49 | J144A | J141 |  |  | 63 | 66.3 | [11 empty] | 50
50 | J141 | J141A |  |  | 63 | 73 | [11 empty] | 168
51 | J141 | J141B |  |  | 63 | 50 | [11 empty] | 148.5
52 | J127 | J128 |  |  | 63 | 168 | [11 empty] | 3
53 | J96 | J97 |  |  | 63 | 148.5 | [11 empty] | 134
54 | J54 | J57 | B.T ROAD |  | 63 | 3 | [11 empty] | 3
55 | J54 | J57 |  |  | 63 | 134 | [11 empty] | 268.9
56 | J57 | J61 | B.T ROAD |  | 63 | 3 | [11 empty] | 140
57 | J57 | J61 |  |  | 63 | 268.9 | [11 empty] | 147
58 | J57 | J62 |  |  | 63 | 140 | [11 empty] | 3
59 | J62 | J63 |  |  | 63 | 147 | [11 empty] | 181.7
60 | J62 | J63 | B.T ROAD |  | 63 | 3 | [11 empty] | 216.5
61 | J55 | J56 |  |  | 63 | 181.7 | [11 empty] | 98
62 | J67 | J49 |  |  | 63 | 216.5 | [11 empty] | 164
63 | J186 | J188 |  |  | 63 | 98 | [11 empty] | 88
64 | J213 | J219 |  |  | 63 | 164 | [11 empty] | 30
65 | J213 | J217 |  |  | 63 | 88 | [11 empty] | 28
66 | J213 | J217 | BRICK ROAD |  | 63 | 30 | [11 empty] | 17.2
67 | J217 | J226 | BRICK ROAD |  | 63 | 28 | [11 empty] | 12.7
68 | J217 | J226 |  |  | 63 | 17.2 | [11 empty] | 12.2
69 | J226 | J226A |  |  | 63 | 12.7 | [11 empty] | 36.3
70 | J226A | J226B |  |  | 63 | 12.2 | [11 empty] | 12.4
71 | J226A | J226C |  |  | 63 | 36.3 | [11 empty] | 46
72 | J209 | J207 |  |  | 63 | 12.4 | [11 empty] | 17.7
73 | J209 | J208 |  |  | 63 | 46 | [11 empty] | 26.3
74 | J209A | J209B |  |  | 63 | 17.7 | [11 empty] | 70
75 | j201 | j201A |  |  | 63 | 26.3 | [11 empty] | 46.7
76 | J210 | J210A | BRICK ROAD |  | 63 | 70 | [11 empty] | 27.5
77 | J210A | J210B |  |  | 63 | 46.7 | [11 empty] | 3
78 | J210A | J212 | BRICK ROAD |  | 63 | 27.5 | [11 empty] | 32
79 | J216 | J215 | B.T ROAD |  | 63 | 3 | [11 empty] | 3
80 | J216 | J215 | BRICK ROAD |  | 63 | 32 | [11 empty] | 64.3
81 | J218 | J223 | B.T ROAD |  | 63 | 3 | [11 empty] | 125
82 | J218 | J223 |  |  | 63 | 64.3 | [11 empty] | 3
83 | J200 | J199 |  |  | 63 | 125 | [11 empty] | 21
84 | J223 | J224 | B.T ROAD |  | 63 | 3 | [11 empty] | 59.6
85 | J223 | J224 | BRICK ROAD |  | 63 | 21 | [11 empty] | 3
86 | J232 | J233 |  |  | 63 | 59.6 | [11 empty] | 26.6
87 | J233 | J233A | B.T ROAD |  | 63 | 3 | [11 empty] | 109.5
88 | J233 | J233A |  |  | 63 | 26.6 | [11 empty] | 63
89 | J233A | J233B |  |  | 63 | 109.5 | [11 empty] | 107.3
90 | J233A | J226 |  |  | 63 | 63 | [11 empty] | 1.5
91 | J234 | J251 | INTERLOCKING |  | 63 | 107.3 | [11 empty] | 10
92 | J251 | J254 | INTERLOCKING |  | 63 | 1.5 | [11 empty] | 32.1
93 | J251 | J254 |  |  | 63 | 10 | [11 empty] | 87.2
94 | J254 | J255 | BRICK ROAD |  | 63 | 32.1 | [11 empty] | 17.8
95 | J254 | J255 |  |  | 63 | 87.2 | [11 empty] | 4
96 | J251 | J252 | INTERLOCKING |  | 63 | 17.8 | [11 empty] | 11
97 | J252 | J253 | INTERLOCKING |  | 63 | 4 | [11 empty] | 29
98 | J252 | J253 |  |  | 63 | 11 | [11 empty] | 165
99 | J252 | J249 | INTERLOCKING |  | 63 | 29 | [11 empty] | 108.3
100 | J252 | J249 |  |  | 63 | 165 | [11 empty] | 162
101 | J249 | J250 |  |  | 63 | 108.3 | [11 empty] | 23
102 | J249 | J232 |  |  | 63 | 162 | [11 empty] | 79
103 | J249 | J232 | BRICK ROAD |  | 63 | 23 | [11 empty] | 10
104 | J157 | J154 |  |  | 63 | 79 | [11 empty] | 18
105 | J157 | J155 |  |  | 63 | 10 | [11 empty] | 305
106 | J138 | J139 |  |  | 63 | 18 | [11 empty] | 314.6
107 | J1 | J3 |  |  | 63 | 305 | [11 empty] | 16.7
108 | J52 | J46 |  |  | 63 | 314.6 | [11 empty] | 79.6
109 | J114 | J117 | INTERLOCKING |  | 63 | 16.7 | [11 empty] | 78
110 | J114 | J117 |  |  | 63 | 79.6 | [11 empty] | 12.5
111 | J117 | J118 |  |  | 63 | 78 | [11 empty] | 35.3
112 | J117 | J120 |  |  | 63 | 12.5 | [11 empty] | 75
113 | J120 | J121 |  |  | 63 | 35.3 | [11 empty] | 75
114 | J120 | J122 |  |  | 63 | 75 | [11 empty] | 69
115 | J115 | J116 |  |  | 63 | 75 | [11 empty] | 298.5
116 | J158 | J159 |  |  | 63 | 69 | [11 empty] | 115.2
117 | J158 | J170 |  |  | 63 | 298.5 | [11 empty] | 22.4
118 | J170 | J177 |  |  | 63 | 115.2 | [11 empty] | 227
119 | J177 | J185 |  |  | 63 | 22.4 | [11 empty] | 107.3
120 | J177 | J185 | BRICK ROAD |  | 63 | 227 | [11 empty] | 90.8
121 | J177 | J171 |  |  | 63 | 107.3 | [11 empty] | 70
122 | J170 | J166 |  |  | 63 | 90.8 | [11 empty] | 61.6
123 | J166 | J169 |  |  | 63 | 70 | [11 empty] | 70
124 | J166 | J161 |  |  | 63 | 61.6 | [11 empty] | 29.6
125 | J161 | J162 |  |  | 63 | 70 | [11 empty] | 23.9
126 | J161 | j157 |  |  | 63 | 29.6 | [11 empty] | 48.6
127 | J112 | J111 |  |  | 63 | 23.9
128 | J94 | J110 |  |  | 63 | 48.6 | [11 empty] | 190.8
129 | J91 | J98 | BRICK ROAD |  | 63 | 190.8 | [11 empty] | 11
130 | J91 | J98 |  |  | 63 | 11 | [11 empty] | 70
131 | J98 | J99 |  |  | 63 | 66 | [11 empty] | 133.3
132 | J99 | J105 |  |  | 63 | 70 | [11 empty] | 58
133 | J99 | J107 |  |  | 63 | 133.3 | [11 empty] | 113.8
134 | J107 | J108 |  |  | 63 | 58 | [11 empty] | 58.4
135 | J107 | J109 |  |  | 63 | 113.8
136 | J98 | J100 |  |  | 63 | 58.4 | [11 empty] | 188
137 | J110 | J114 |  |  | 63 | 188 | [11 empty] | 1.8
138 | J114 | J113 |  |  | 63 | 21 | [11 empty] | 31
139 | J114 | J113 |  |  | 63 | 1.8 | [11 empty] | 124
140 | J82A | J82B |  |  | 63 | 31 | [11 empty] | 33.3
141 | J23 | J18 |  |  | 63 | 129 | [11 empty] | 282.1
142 | J209 | J209A |  |  | 75 |  | 33.3 | [10 empty] | 185
143 | J146 | J158 |  |  | 75 |  | 282.1 | [10 empty] | 95.5
144 | J155 | J151 |  |  | 75 |  | 185 | [10 empty] | 129
145 | J151 | J145 |  |  | 75 |  | 95.5 | [10 empty] | 86.6
146 | J151 | J154 |  |  | 75 |  | 129 | [10 empty] | 88
147 | J154 | J160 |  |  | 75 |  | 86.6 | [10 empty] | 69
148 | J10 | J22 | BRICK ROAD |  | 75 |  | 88 | [10 empty] | 27.6
149 | J10 | J22 |  |  | 75 |  | 69 | [10 empty] | 37.5
150 | J22 | J24 |  |  | 75 |  | 27.6 | [10 empty] | 164.5
151 | J24 | J25 |  |  | 75 |  | 37.5 | [10 empty] | 136.1
152 | J25 | J53 |  |  | 75 |  | 164.5 | [10 empty] | 243
153 | J53 | J72 |  |  | 75 |  | 136.1 | [10 empty] | 62.2
154 | J72 | J79 |  |  | 75 |  | 243 | [10 empty] | 151
155 | J217 | J209 | BRICK ROAD |  | 75 |  | 62.2 | [10 empty] | 72
156 | J209 | J198 |  |  | 75 |  | 151 | [10 empty] | 30.2
157 | J201 | J201A |  |  | 75 |  | 72 | [10 empty] | 4
158 | J216 | J218 |  |  | 75 |  | 30.2 | [10 empty] | 55.8
159 | J218 | J200 |  |  | 75 |  | 4 | [10 empty] | 102
160 | J200 | J223 |  |  | 75 |  | 55.8 | [10 empty] | 42.5
161 | J223 | J232 |  |  | 75 |  | 102 | [10 empty] | 278.5
162 | J192 | J193 |  |  | 90 |  |  | 42.5 | [9 empty] | 48
163 | J196 | J213 |  |  | 90 |  |  | 278.5 | [9 empty] | 46.5
164 | J196 | J198 |  |  | 90 |  |  | 48 | [9 empty] | 5
165 | J198 | J201 |  |  | 90 |  |  | 46.5 | [9 empty] | 117
166 | J198 | J201 | INTERLOCKING |  | 90 |  |  | 5 | [9 empty] | 5
167 | J201 | J204 |  |  | 90 |  |  | 117 | [9 empty] | 43
168 | J201 | J204 | B.T ROAD |  | 90 |  |  | 5 | [9 empty] | 38.3
169 | J204 | J210 |  |  | 90 |  |  | 43 | [9 empty] | 113
170 | J210 | J216 |  |  | 90 |  |  | 38.3 | [9 empty] | 3
171 | J204 | J197 |  |  | 90 |  |  | 113 | [9 empty] | 663
172 | J204 | J197 | B.T ROAD |  | 90 |  |  | 3 | [9 empty] | 50.9
173 | J197 | J145 |  |  | 90 |  |  | 663 | [9 empty] | 9
174 | J69 | J73 | BRICK ROAD |  | 110 |  |  |  | 50.9 | [8 empty] | 16.7
175 | J73 | J76 |  |  | 110 |  |  |  | 9 | [8 empty] | 151.6
176 | J73 | J76 | BRICK ROAD |  | 110 |  |  |  | 16.7 | [8 empty] | 20
177 | J76 | J81 |  |  | 110 |  |  |  | 151.6 | [8 empty] | 5
178 | J81 | J89 | BRICK ROAD |  | 110 |  |  |  | 20 | [8 empty] | 3
179 | J89 | J92 | culvert |  | 110 |  |  |  | 5 | [8 empty] | 10
180 | J89 | J92 | B.T ROAD |  | 110 |  |  |  | 3 | [8 empty] | 42
181 | J89 | J92 | BRICK ROAD |  | 110 |  |  |  | 10 | [8 empty] | 154.2
182 | J144 | J140 |  |  | 110 |  |  |  | 42 | [8 empty] | 350
183 | J140 | J127 |  |  | 110 |  |  |  | 154.2 | [8 empty] | 6
184 | J127 | J96 |  |  | 110 |  |  |  | 350 | [8 empty] | 28.7
185 | J127 | J96 | B.T ROAD |  | 110 |  |  |  | 6 | [8 empty] | 182.8
186 | J96 | J92 |  |  | 110 |  |  |  | 28.7 | [8 empty] | 152.7
187 | J144 | J186 |  |  | 110 |  |  |  | 182.8 | [8 empty] | 8
188 | J186 | J192 |  |  | 110 |  |  |  | 152.7 | [8 empty] | 177
189 | J192 | J196 | B.T ROAD |  | 110 |  |  |  | 8 | [8 empty] | 144
190 | J192 | J196 |  |  | 110 |  |  |  | 177 | [8 empty] | 141
191 | J11 | J19 |  |  | 110 |  |  |  | 144 | [8 empty] | 31
192 | J19 | J50 |  |  | 110 |  |  |  | 141 | [8 empty] | 8
193 | J115 | J124 | BRICK ROAD |  | 110 |  |  |  | 31 | [8 empty] | 40
194 | J115 | J124 | culvert |  | 110 |  |  |  | 8
195 | J115 | J124 |  |  | 110 |  |  |  | 40
196 | J26 | J51 |  |  | 110 |  |  |  | 19 | [8 empty] | 65.1
197 | J51 | J69 |  |  | 110 |  |  |  | 69 | [8 empty] | 48
198 | J113 | J112 |  |  | 125 |  |  |  |  | 65.1 | [7 empty] | 327
199 | J94 | J91 |  |  | 125 |  |  |  |  | 48 | [7 empty] | 87.9
200 | J91 | J67 |  |  | 125 |  |  |  |  | 327 | [7 empty] | 172.5
201 | J113 | J115 | BRICK ROAD |  | 125 |  |  |  |  | 87.9 | [7 empty] | 80
202 | J2 | J3 |  |  | 140 | [5 empty] | 172.5 | [6 empty] | 19.8
203 | J3 | J11 |  |  | 140 | [5 empty] | 80 | [6 empty] | 29.2
204 | J3 | J4 |  |  | 140 | [5 empty] | 19.8 | [6 empty] | 3
205 | J4 | J10 |  |  | 140 | [5 empty] | 29.2 | [6 empty] | 3
206 | J4 | J10 | B.T ROAD |  | 140 | [5 empty] | 3 | [6 empty] | 403
207 | J10 | J49 | culvert |  | 140 | [5 empty] | 3 | [6 empty] | 121
208 | J10 | J49 |  |  | 140 | [5 empty] | 403 | [6 empty] | 29
209 | J49 | J54 |  |  | 140 | [5 empty] | 121 | [6 empty] | 121.5
210 | J54 | J55 |  |  | 140 | [5 empty] | 29 | [6 empty] | 228
211 | J55 | J67 |  |  | 140 | [5 empty] | 121.5
212 | J1 | J2 |  |  | 160 | [6 empty] | 228
Work Done Qty In ( Rmt ) : | [5 empty] | 10411.9 | 2054.4 | 1402.8 | 1819.6 | 528 | 982 | 228
Restricting Exceeded Qty's to WO Qty's
Total Quantity Considered for bill ( In RMT )=
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks
1.1 | 63 mm HDPE | 14448 | 10411.9 | 10411.9 | 10411 | 0.9 | 14448 | 10411.9 | - | 10411.9 | 14448 | 10411.9 |  | 10411.9 |  |  | 0
1.2 | 75 mm HDPE | 2831 | 2054.4 | 2054.4 | 1438 | 616.4 | 2831 | 2054.4 | - | 2054.4 | 2831 | 2054.4 |  | 2054.4 |  |  | 0
1.3 | 90 mm HDPE | 1614 | 1402.8 | 1402.8 | 535 | 867.8 | 1614 | 1402.8 | - | 1402.8 | 1614 | 1402.8 |  | 1402.8 |  |  | 0
1.4 | 110mm HDPE | 2095 | 1819 | 1819 | 1563 | 256 | 2095 | 1819 | - | 1819 | 2095 | 1819 |  | 1819 |  |  | 0
1.5 | 125mm HDPE | 751 | 528 | 528 | 738 | -210 | 751 | 528 | - | 528 | 751 | 528 |  | 528 |  |  | 0
1.6 | 140mm HDPE | 1022 | 982 | 982 | 975 | 7 | 1022 | 982 | - | 982 | 1022 | 982 |  | 982 |  |  | 0
1.7 | 160mm HDPE | 287 | 228 | 228 | 100 | 128 | 287 | 228 | - | 228 | 287 | 228 |  | 228 |  |  | 0
1.8 | 180mm HDPE |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
1.9 | 200mm HDPE |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
Sub Total = |  | 23048 | 17426.1 | 17426.1 | 15760 | 1666.1 |  | 17426.1 | 15760 | 1666.1 |  |  | 0 | 17426.1 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ AM-SMX ) (Dy.M-PMX ) AGM Project Incharge
|  |  | 14448 | 10411 | 10411 | 9890 | 521
|  |  | 2831 | 1438 | 1438 | 1348 | 90
|  |  | 1614 | 535 | 535 | 535 | 0
|  |  | 2095 | 1563 | 1563 | 1080 | 483
|  |  | 751 | 738 | 444 | 0 | 444
|  |  | 1022 | 975 | 414 | 0 | 414
|  |  | 287 | 100 | 100 | 0 | 100
|  |  | 23048 | 15760 | 14905 | 12853 | 2052

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
Name of the Contractor : 205451_ALTRUIST GEOTECHNICAL SERVICES PVT.LTD. (CL35) | [11 empty] | RA Bill-09
Sl NO | Description | Units | Attarsand |  | Bhati Khued |  | Barasarai | Total |  | Balance Qty | SAP Entry | Remarks
|  |  | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Consumed Qty | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3800 | 2674.2 | 7950 | 12695 | 10411 | 30000 | 25781.1 | 4218.9 | 16781 |  |  | 9000.1 | TRUE |  | 0.9
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2250 | 1248.5 | 900 | 835 | 1438 | 4250 | 4137.9 | 112.1 | 2397 |  |  | 1740.9 | TRUE |  | 616.4
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 4800 | 3674.55 | 595 | 590 | 535 | 6390 | 5667.35 | 722.65 | 4094.55 |  |  | 1572.8 | TRUE |  | 867.8
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 1650 | 1384.25 | 450 | 447 | 1563 | 3557 | 3650.25 | -93.25 | 1679 |  |  | 1971.25 | TRUE |  | 256
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  |  |  | 738 | 444 | 528 | -84 |  |  |  | 528 | TRUE |  | -210
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  |  |  | 975 | 324 | 324 | 0 |  |  |  | 324 | TRUE |  | 7
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3792 | 3491.75 |  | 0 | 100 | 4584 | 3719.75 | 864.25 | 3491.75 |  |  | 228 | TRUE |  | 128
| 200 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2832 | 2735.5 |  | 0 |  | 2832 | 2735.5 | 96.5 | 2735.5 |  |  | 0 | TRUE
| Total Qty In ( Rmt ) = | [6 empty] | 52381 | 46543.85 | 5837.15 |  |  |  |  | TRUE
2 | Specials :- | [13 empty] | TRUE
| Equal Tee | [13 empty] | TRUE
| 63mm | No's | 21 | 4 | 66 | 36 |  | 108 | 40 | 68 | 36 |  |  | 4 | TRUE
| 75mm | No's | 7 | 2 |  | 3 |  | 18 | 5 | 13 | 5 |  |  | 0 | TRUE
| 90mm | No's | 11 | 11 | 12 |  |  | 35 | 11 | 24 | 11 |  |  | 0 | TRUE
| 110mm | No's | 2 | 2 |  |  |  | 12 | 2 | 10 | 2 |  |  | 0 | TRUE
| 125mm | No's |  |  | 4 |  |  | 5 | 0 | 5 |  |  |  | 0 | TRUE
| 140mm | No's |  |  | 2 |  |  | 2 | 0 | 2 |  |  |  | 0 | TRUE
| 160mm | No's | 5 | 1 |  |  |  | 6 | 1 | 5 | 1 |  |  | 0 | TRUE
| 200mm | No's | 8 | 5 |  |  |  | 8 | 6 | 2 | 6 |  |  | 0 | TRUE | 200030300
| Total Qty In ( No's ) = |  | 54 | 25 |  |  |  | 194 | 65 | 129 |  |  |  |  | TRUE
| Branch TEE | [13 empty] | TRUE
| 75 mm X 63 mm | No's | 2 | 2 | 7 | 4 |  | 15 | 2 | 13 | 2 |  |  | 0 | TRUE
| 90 mm X 63 mm | No's | 13 | 5 | 3 |  |  | 19 | 5 | 14 | 5 |  | J-140 | 0 | TRUE
| 90 mm X 75 mm | No's | 2 |  |  |  |  | 1 | 0 | 1 |  |  | J-140 | 0 | TRUE
| 110mm X 63 mm | No's | 6 | 5 | 1 | 1 |  | 6 | 6 | 0 | 6 |  | J-79,J-35,J-152 | 0 | TRUE
| 110mm X 75 mm | No's | 1 |  |  |  |  | 1 | 0 | 1 |  |  |  | 0 | TRUE
| 110mm X 90 mm | No's |  |  | 4 |  |  | 4 | 0 | 4 |  |  |  | 0 | TRUE
| 160mm X 63 mm | No's | 14 | 8 |  |  |  | 14 | 8 | 6 | 8 |  |  | 0 | TRUE
| 160mm X 90 mm | No's | 6 | 5 |  |  |  | 6 | 5 | 1 | 5 |  | J-68 | 0 | TRUE
| 200mm X 110mm | No's | 1 | 1 |  |  |  | 1 | 1 | 0 |  |  |  | 1 | TRUE
| 200mm X 160mm | No's | 2 |  |  |  |  | 1 | 0 | 1 |  |  |  | 0 | TRUE
| Total Qty In ( No's ) = |  | 47 | 26 |  |  |  | 68 | 27 | 41 |  |  |  |  | TRUE
| 4 Way Tee | [13 empty] | TRUE
| 63mm | No's |  |  | 1 |  |  | 1 | 0 | 1 |  |  |  | 0 | TRUE
| 75mm | No's | 1 |  |  |  |  | 1 | 0 | 1 |  |  |  | 0 | TRUE
| 90mm | No's |  |  | 2 |  |  | 2 | 0 | 2 |  |  |  | 0 | TRUE
| 110mm | No's |  |  | 1 | 1 |  | 1 | 1 | 0 | 1 |  |  | 0 | TRUE
| 125mm | No's |  |  | 1 | 1 |  | 1 | 1 | 0 | 1 |  |  | 0 | TRUE
| 160mm | No's | 3 | 1 |  |  |  | 3 | 1 | 2 | 1 |  |  | 0 | TRUE
| Total Qty In ( No's ) = |  | 4 | 1 |  |  |  | 9 | 3 | 6 |  |  |  |  | TRUE
| Reducers | [13 empty] | TRUE
| 75mm X 63 mm | No's | 10 | 1 | 17 | 6 |  | 27 | 7 | 20 | 6 |  | J-12 | 1 | TRUE
| 90mm X 63 mm | No's | 8 | 5 | 15 |  |  | 31 | 5 | 26 | 5 |  | J-7 | 0 | TRUE
| 90mm X 75 mm | No's | 3 | 2 | 12 |  |  | 17 | 2 | 15 | 2 |  |  | 0 | TRUE
| 110 mm X 63 mm | No's | 1 | 1 | [5 empty] | 0 |  |  | J-83,J-101 | 0 | TRUE
| 110 mm X 90 mm | No's | 2 | 1 | 5 | 1 |  | 8 | 2 | 6 | 2 |  | J-130 | 0 | TRUE
| 125 mm X 63 mm | No's |  |  | 1 |  |  | 2 | 0 | 2 |  |  |  | 0 | TRUE
| 140 mm X 63 mm | No's |  |  | 1 | 2 |  | 2 | 2 | 0 |  |  |  | 2 | TRUE
| 160 mm X 63 mm | No's | 4 | 4 |  |  |  | 9 | 4 | 5 | 4 |  | J-129 | 0 | TRUE
| 160mm X 90 mm | No's | 5 |  |  |  |  | 2 | 0 | 2 |  |  |  | 0 | TRUE
| 160mm X 110mm | No's | 3 | 3 |  |  |  | 3 | 3 | 0 | 3 |  |  | 0 | TRUE
| 200mm X 63mm | No's | 2 | 0 |  |  |  | 2 | 0 | 2 |  |  |  | 0 | TRUE
| 200mm X 110mm | No's | 4 | 2 |  |  |  | 4 | 2 | 2 | 2 |  |  | 0 | TRUE
| 200mm X 160mm | No's | 1 | 1 |  |  |  | 1 | 1 | 0 |  |  |  | 1 | TRUE
| Total Qty In ( No's ) = |  | 43 | 20 |  |  |  | 108 | 28 | 80 |  |  |  |  | TRUE
| Bends | [13 empty] | TRUE
| 160mm (90 deg) |  | 4 | 0 |  |  |  | 4 | 0 | 4 |  |  |  |  | TRUE
| 200mm (90 deg) |  | 1 | 0 |  |  |  | 1 | 0 | 1 |  |  |  |  | TRUE
| Total Qty In ( No's ) = |  | 5 | 0 |  |  |  | 5 | 0 | 5 |  |  |  |  | TRUE
| End Caps | [13 empty] | TRUE
| 63mm | No's | 61 | 31 | 40 | 15 |  | 159 | 46 | 113 | 46 |  |  | 0 | TRUE
| Total Qty In ( No's ) = |  | 61 | 31 |  |  |  | 159 | 46 | 113 |  |  |  |  | TRUE
| FHTCs Materials | [13 empty] | TRUE
| MSERW GI PIPES 15 GI M PE | Mtrs. |  |  | 120 |  |  | 198 | 95 | 103 | 95 |  |  | 0 | TRUE
| MDPE 20 MM COIL - 500 Mtrs. | Mtrs. |  |  | 1000 |  |  | 3000 | 575 | 2425 | 575 |  |  | 0 | TRUE
| PP CLAMP SADDLE - 63 MM X 1/2" | No's |  |  | 100 |  |  | 370 | 95 | 275 | 95 |  |  | 0 | TRUE
| PP CLAMP SADDLE - 75 MM X 1/2" | No's |  |  | 50 |  |  | 120 | 0 | 120 |  |  |  | 0 | TRUE
| PP CLAMP SADDLE - 90 MM X 1/2" | No's |  |  | 50 |  |  | 100 | 0 | 100 |  |  |  | 0 | TRUE
| PP COMPR. FM. THREAD ADAPTER - 20 MM X 1/2"(FTA) | No's |  |  | 200 |  |  | 390 | 95 | 295 | 95 |  |  | 0 | TRUE
| PP COMPR. FM. THREAD ELB. OFF TAKE - 20 MM X 1/2" (FTO) | No's |  |  | 200 |  |  | 280 | 95 | 185 | 95 |  |  | 0 | TRUE
| THREADED FCV - 1/2 " (15NB) | No's |  |  | 200 |  |  | 550 | 95 | 455 | 95 |  |  | 0 | TRUE
| GI ELBOW | No's |  |  | 200 |  |  | 260 | 95 | 165 | 95 |  |  | 0 | TRUE
| GI SOCKET | No's | [5 empty] | 130 | 95 | 35 | 95 |  |  | 0 | TRUE
| WALL MOUNT SADDLE GI PIPE - 15 MM (Clamp) | No's | [5 empty] | 260 | 95 | 165 | 95 |  |  | 0 | TRUE
| 15 MM GI NIPPLE - 0.3 Mtr LENGTH | No's |  |  | 50 |  |  | 130 | 95 | 35 | 95 |  |  | 0 | TRUE
| 15 MM GI NIPPLE - 0.5 Mtr LENGTH | No's |  |  | 50 |  |  | 130 | 95 | 35 | 95 |  |  | 0 | TRUE
| BIB COCK PTMT (Taps) | No's |  |  | 50 |  |  | 130 | 95 | 35 | 95 |  |  | 0 | TRUE
| Teflon Tape | No's | [5 empty] | 0 | 0 | 0
| GI Nails | No's | [5 empty] | 0 | 0 | 0
|  | No's | [5 empty] | 0 | 0 | 0
Prepared by Checked By Store DM_PMX Project Incharge