## Sheet1
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP PADAMPUR_______Block______mangraura_____________ Pipeline Laying Measurement Sheet
Name of the Contractor :
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [8 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm | 180mm | 200mm
1 | J135 | J140 |  |  | 63 | 81.8
2 | J75 | J81 | B.T ROAD |  | 63 | 8.2 | [11 empty] | 14
3 | J75 | J81 |  |  | 63 | 58.6 | [11 empty] | 105
4 | J81 | J98 |  |  | 63 | 105.8 | [11 empty] | 78.5
5 | J98 | J74 |  |  | 63 | 100.2 | [11 empty] | 23.8
6 | J74 | J56 |  |  | 63 | 144.7 | [11 empty] | 41.2
7 | J98 | J97 |  |  | 63 | 13.6 | [11 empty] | 74.8
8 | J97 | J71 |  |  | 63 | 87.5 | [11 empty] | 24.5
9 | J97 | J105 |  |  | 63 | 89.9 | [11 empty] | 18.5
10 | J97 | J105 | B.T ROAD |  | 63 | 3.4 | [11 empty] | 60
11 | J88 | J112 |  |  | 63 | 118.8 | [11 empty] | 29.5
12 | J112 | J127 |  |  | 63 | 162.3 | [11 empty] | 55.4
13 | J112 | J105 |  |  | 63 | 1.8 | [11 empty] | 25.4
14 | J88 | J115 |  |  | 63 | 146.6 | [11 empty] | 15.4
15 | J115 | J83 |  |  | 63 | 106.4 | [11 empty] | 77.3
16 | J115 | J83 | B.T ROAD |  | 63 | 3 | [11 empty] | 24.5
17 | J115 | J119 |  |  | 63 | 82.6 | [11 empty] | 22.1
18 | J119 | J101 |  |  | 63 | 56.6 | [11 empty] | 47.5
19 | J101 | J123 |  |  | 63 | 116.1 | [11 empty] | 19
20 | J101 | J96 |  |  | 63 | 63.1 | [11 empty] | 39.9
21 | J119 | J132 |  |  | 63 | 209.2 | [11 empty] | 18.4
22 | J132 | J95 |  |  | 63 | 81.6 | [11 empty] | 123.5
23 | J95 | J93 |  |  | 63 | 45.7 | [11 empty] | 68.2
24 | J132 | J111 |  |  | 63 | 120.3 | [11 empty] | 95.7
25 | J111 | J117 |  |  | 75 | 42.4 | [11 empty] | 61.5
26 | J117 | J113 |  |  | 63 | 34.8 | [11 empty] | 8.4
27 | J117 | J113 | BRICK ROAD |  | 63 | 55.4 | [11 empty] | 157
28 | J113 | J129 | BRICK ROAD |  | 63 | 2.6 | [11 empty] | 22.2
29 | J113 | J129 |  |  | 63 | 55.3 | [11 empty] | 69.8
30 | J113 | J130 |  |  | 63 | 45.5 | [11 empty] | 84.2
31 | J120 | J149 | BRICK ROAD |  | 63 | 130.9 | [11 empty] | 28.5
32 | J120 | J149 |  |  | 63 | 162.4 | [11 empty] | 117.2
33 | J117 | J125 |  |  | 63 | 42.8 | [11 empty] | 16
34 | J135 | J140A |  |  | 63 | 86.9 | [11 empty] | 96.3
35 | J135 | J140A | INTERLOCKING |  | 63 | 3.1 | [11 empty] | 288.8
36 | J140A | J124 |  |  | 63 | 103.3 | [11 empty] | 115.1
37 | J92 | J91 |  |  | 63 | 2.8 | [11 empty] | 34.2
38 | J81 | J88 | B.T ROAD |  | 63 | 3.6 | [11 empty] | 73.5
39 | J81 | J88 |  |  | 63 | 137.6 | [11 empty] | 47
40 | J155 | J150 |  |  | 63 | 106.1 | [11 empty] | 637
41 | J155 | J141 |  |  | 63 | 375.3 | [11 empty] | 7
42 | J141 | J153 |  |  | 63 | 52 | [11 empty] | 275.6
43 | J141 | J147 |  |  | 63 | 218.9 | [11 empty] | 11
44 | J147 | J122 |  |  | 75 |  | 148.6 | [10 empty] | 3
45 | J147 | J118 |  |  | 75 |  | 3.2 | [10 empty] | 8
46 | J147 | J118 |  |  | 75 |  | 377.2 | [10 empty] | 113
47 | J147 | J118 | INTERLOCKING |  | 63 | 8.6 | [11 empty] | 66.3
48 | J43 | J54 |  |  | 63 | 73.9 | [11 empty] | 73
49 | J44 | J41 |  |  | 63 | 52.3 | [11 empty] | 50
50 | J40 | J38 |  |  | 63 | 36.2 | [11 empty] | 168
51 | J12 | J22 |  |  | 63 | 171.7 | [11 empty] | 148.5
52 | J22 | J32 |  |  | 63 | 167.4 | [11 empty] | 3
53 | J22 | J32 | B.T ROAD |  | 63 | 4 | [11 empty] | 134
54 | J32 | J46 |  |  | 63 | 83.6 | [11 empty] | 3
55 | J22 | J14 |  |  | 63 | 78.1 | [11 empty] | 268.9
56 | J14 | J27 | C.C. |  | 63 | 88.8 | [11 empty] | 140
57 | J14 | J27 |  |  | 63 | 1.4 | [11 empty] | 147
58 | J27 | J35 | C.C. |  | 63 | 51.3 | [11 empty] | 3
59 | J32 | J28 |  |  | 63 | 59.3 | [11 empty] | 181.7
60 | J32 | J28 | B.T ROAD |  | 63 | 3 | [11 empty] | 216.5
61 | J35 | J36 |  |  | 63 | 92 | [11 empty] | 98
62 | J36 | J39 |  |  | 63 | 6.7 | [11 empty] | 164
63 | J36 | J26 |  |  | 63 | 43 | [11 empty] | 88
64 | J26 | J25 | C.C. |  | 63 | 13.4 | [11 empty] | 30
65 | J26 | J25 |  |  | 63 | 8.8 | [11 empty] | 28
66 | J26 | J6 |  |  | 63 | 70.1 | [11 empty] | 17.2
67 | J5 | J42 |  |  | 63 | 114.6 | [11 empty] | 12.7
68 | J42 | J34 | C.C. |  | 63 | 21.9 | [11 empty] | 12.2
69 | J42 | J34 |  |  | 63 | 2.9 | [11 empty] | 36.3
70 | J34 | J33 |  |  | 63 | 44.5 | [11 empty] | 12.4
71 | J80 | J64 |  |  | 63 | 131.3 | [11 empty] | 46
72 | J64 | J52 |  |  | 63 | 33 | [11 empty] | 17.7
73 | J64 | J52 | B.T ROAD |  | 63 | 5 | [11 empty] | 26.3
74 | J52 | J121 |  |  | 63 | 106.9 | [11 empty] | 70
75 | J52 | J47 |  |  | 63 | 79.5 | [11 empty] | 46.7
76 | J64 | J53 |  |  | 63 | 282.1 | [11 empty] | 27.5
77 | J84 | J102 |  |  | 63 | 80.1 | [11 empty] | 3
78 | J152 | J150 |  |  | 63 | 22.1 | [11 empty] | 32
79 | j78 | j51 |  |  | 63 | 685.6 | [11 empty] | 3
80 | j45 | j59 |  |  | 63 | 60.1 | [11 empty] | 64.3
81 | j45 | j57 |  |  | 63 | 250.3 | [11 empty] | 125
82 | j43 | j54 |  |  | 63 | 71.9 | [11 empty] | 3
83 | j113 | j129 |  |  | 63 | 79.8 | [11 empty] | 21
84 | j94 | j131 |  |  | 63 | 86.6 | [11 empty] | 59.6
85 | j131 | j143 |  |  | 63 | 432 | [11 empty] | 3
86 | j131 | j143 | brick road |  | 63 | 2.6 | [11 empty] | 26.6
87 | j131 | j120 |  |  | 63 | 120.7 | [11 empty] | 109.5
88 | j149 | j120 |  |  | 63 | 174.4 | [11 empty] | 63
89 | j149 | j120 | BRICK ROAD |  | 63 | 116.3 | [11 empty] | 107.3
90 | j93 | j132 |  |  | 63 | 197.3 | [11 empty] | 1.5
91 | j34 | j31 |  |  | 63 | 158.2 | [11 empty] | 10
92 | J64 | j30 |  |  | 63 | 130.8 | [11 empty] | 32.1
93 | j30 | j8 |  |  | 63 | 29 | [11 empty] | 87.2
94 | j30 | j8 | cc road |  | 63 | 133.2 | [11 empty] | 17.8
95 | j92 | j91 |  |  | 63 | 62.1 | [11 empty] | 4
96 | J8 | J27 |  |  | 63 | 58.8 | [11 empty] | 11
97 | j8 | j26 | C.C. |  | 63 | 46.8 | [11 empty] | 29
98 | j8 | j26 |  |  | 63 | 1.3 | [11 empty] | 165
99 | j8 | j26 | cc road |  | 63 | 5.4 | [11 empty] | 108.3
100 | j26 | j25 | C.C. |  | 63 | 21.1 | [11 empty] | 162
101 | j26 | j36 | cc road |  | 63 | 3 | [11 empty] | 23
102 | J9 | J30 | cc road |  | 63 | 4.1 | [11 empty] | 79
103 | J9 | J30 | C.C. |  | 63 | 63.4 | [11 empty] | 10
104 | J30 | J27 |  |  | 63 | 8.2 | [11 empty] | 18
105 | J30 | J27 | C.C. |  | 63 | 75.1 | [11 empty] | 305
106 | J30 | J6 | C.C. |  | 63 | 40.2 | [11 empty] | 314.6
107 | j6 | j8 |  |  | 63 | 29 | [11 empty] | 16.7
108 | j89 | j102 |  |  | 63 | 128.4 | [11 empty] | 79.6
109 | j117 | j113 | BRICK ROAD |  | 75 |  | 50.1 | [10 empty] | 78
110 | j117 | j113 |  |  | 75 |  | 39.1 | [10 empty] | 12.5
111 | j110 | j135 |  |  | 75 |  | 57.3 | [10 empty] | 35.3
112 | j135 | j117 |  |  | 75 |  | 97.1 | [10 empty] | 75
113 | j111 | j93a |  |  | 75 |  | 25.1 | [10 empty] | 75
114 | J118 | J110 |  |  | 75 |  | 58.2 | [10 empty] | 69
115 | J118 | J92 | B.T ROAD |  | 75 |  | 4.6 | [10 empty] | 298.5
116 | J118 | J92 |  |  | 75 |  | 132.2 | [10 empty] | 115.2
117 | J92 | J80 |  |  | 90 |  |  | 167.6 | [9 empty] | 22.4
118 | J80 | J84 | B.T ROAD |  | 90 |  |  | 6.6 | [9 empty] | 227
119 | J80 | J84 |  |  | 90 |  |  | 54.4 | [9 empty] | 107.3
120 | J84 | J75 |  |  | 90 |  |  | 135.3 | [9 empty] | 90.8
121 | J84 | J89 | B.T ROAD |  | 90 |  |  | 3 | [9 empty] | 70
122 | J84 | J89 |  |  | 90 |  |  | 149.8 | [9 empty] | 61.6
123 | J75 | J43 |  |  | 110 |  |  |  | 284.4 | [8 empty] | 70
124 | j45 | j43 |  |  | 110 |  |  |  | 3.3 | [8 empty] | 29.6
125 | j45 | j43 |  |  | 110 |  |  |  | 64.8 | [8 empty] | 23.9
126 | J44 | J45 |  |  | 125 |  |  |  |  | 216.1 | [7 empty] | 48.6
127 | J44 | J40 |  |  | 125 |  |  |  |  | 161.5
128 | J40 | J31 |  |  | 125 |  |  |  |  | 62 | [7 empty] | 190.8
129 | J31 | J9 |  |  | 140 | [5 empty] | 279.9 | [6 empty] | 11
130 | J9 | J12 | cc road |  | 160 | [6 empty] | 4.4 | [5 empty] | 70
131 | J9 | J12 |  |  | 160 | [6 empty] | 167.4 | [5 empty] | 133.3
132 | J12 | J22 |  |  | 160 | [6 empty] | 7.9 | [5 empty] | 58
Work Done Qty In ( Rmt ) : | [5 empty] | 8982.7 | 992.7 | 516.7 | 352.5 | 439.6 | 279.9 | 179.7
Restricting Exceeded Qty's to WO Qty's
Total Quantity Considered for bill ( In RMT )=
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% |  |  |  | Hydro Test - 15% |  |  |  | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | WO/DPR Qty's | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks
1.1 | 63 mm HDPE | 11213 | 8982.7 | 8982.7 | 8273 | 709.7 | [7 empty] | 0 |  |  | 0
1.2 | 75 mm HDPE | 898 | 992.7 | 992.7 | 801 | 191.7 | [7 empty] | 0 |  |  | 0
1.3 | 90 mm HDPE | 498 | 516.7 | 516.7 | 465 | 51.7 | [7 empty] | 0 |  |  | 0
1.4 | 110mm HDPE | 347 | 352.5 | 352.5 | 330 | 22.5 | [7 empty] | 0 |  |  | 0
1.5 | 125mm HDPE | 416 | 439.6 | 439.6 | 388 | 51.6 | [7 empty] | 0 |  |  | 0
1.6 | 140mm HDPE | 274 | 279.9 | 279.9 | 260 | 19.9 | [7 empty] | 0 |  |  | 0
1.7 | 160mm HDPE | 188 | 179.7 | 179.7 | 0 | 179.7 | [7 empty] | 0 |  |  | 0
1.8 | 180mm HDPE |  |  |  |  | 0 | [7 empty] | 0 |  |  | 0
1.9 | 200mm HDPE |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  | 0
Sub Total = |  | 13834 | 11743.8 | 11743.8 | 10517 | 1226.8 |  | 17426.1 | 15760 | 1666.1 |  |  | 0 | 0 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ AM-SMX ) (Dy.M-PMX ) AGM Project Incharge
|  |  | 14448 | 10411 | 10411 | 9890 | 521
|  |  | 2831 | 1438 | 1438 | 1348 | 90
|  |  | 1614 | 535 | 535 | 535 | 0
|  |  | 2095 | 1563 | 1563 | 1080 | 483
|  |  | 751 | 738 | 444 | 0 | 444
|  |  | 1022 | 975 | 414 | 0 | 414
|  |  | 287 | 100 | 100 | 0 | 100
|  |  | 23048 | 15760 | 14905 | 12853 | 2052

## Reconsilation Statement AB (2
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
Name of the Contractor :210614_ Maa Sharda Construction (SC16) | [8 empty] | RA Bill-04
Sl NO | Description | Units | Padampur | Sarsathpur | Quantity In Rmt |  | Balance Qty | SAP Entry | Remarks
[5 empty] | Issued Qty | Consumed Qty
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 18000 | 15631.1 | 2368.9 | 8529 | 7102.1 |  | TRUE
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 900 | 1034 | -134 | 843 | 191 |  | TRUE
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1000 | 840.7 | 159.3 | 489 | 351.7 |  | TRUE
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 400 | 369.5 | 30.5 | 347 | 22.5 |  | TRUE
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1592 | 789.6 | 802.4 | 408 | 381.6 | 132.6667 | TRUE
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1392 | 293.9 | 1098.1 | 274 | 19.9 | 116 | TRUE
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  |  | 1032 | 340.7 | 691.3 |  | 340.7 | 86 | TRUE
| Total Qty In ( Rmt ) = |  |  |  | 24316 | 19299.5 | 5016.5 |  |  |  | TRUE
2 | Specials :- | [9 empty] | TRUE
| Equal Tee | [9 empty] | TRUE
| 63mm | No's |  |  | 30 |  | 30 |  | 0 |  | TRUE
| 90mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 110mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 30 | 0 | 30 |  |  |  | TRUE
| Branch TEE | [9 empty] | TRUE
| 90 mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 90 mm X 75 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 110mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 160mm X 63 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| 160mm X 90 mm | No's |  |  |  |  | 0 |  | 0 |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| 4 Way Tee | [9 empty] | TRUE
| 75mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 160mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| Reducers | [9 empty] | TRUE
| 75mm X 63 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 90mm X 63 mm | No's |  |  | 5 |  | 5 |  |  |  | TRUE
| 90mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 110 mm X 63 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 110 mm X 75 mm | No's |  |  |  |  | 0 |  |  |  | TRUE
| 160 mm X 63 mm | No's |  |  | 5 |  | 5 |  |  |  | TRUE
| 125 mm X 110 mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 140mm X 125 mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 160mm X 140mm | No's |  |  | 2 |  | 2 |  |  |  | TRUE
| 200mm X 110mm | [5 empty] | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 16 | 0 | 16 |  |  |  | TRUE
| Bends | [9 empty] | TRUE
| 90mm ( 45 Deg ) | [5 empty] | 0 |  |  |  | TRUE
| 140mm ( 45 Deg ) | [5 empty] | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
| End Caps | [9 empty] | TRUE
| 63mm | No's |  |  | 80 |  | 80 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 80 | 0 | 80 |  |  |  | TRUE
| Bends | [9 empty] | TRUE
| 160mm (90 deg) | No's |  |  |  |  | 0 |  |  |  | TRUE
| Total Qty In ( No's ) = |  |  |  | 0 | 0 | 0 |  |  |  | TRUE
Prepared by Checked By Store AM PMX Project Incharge