## Sheet1
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
GP_____SARSIDHI________Block______mangraura_____________ Pipeline Laying Measurement Sheet
Name of the Contractor ;khayathi ENTERPRISES
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (Rmt) | [7 empty] | Cumulative Length (M) | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 160mm | 180mm | 200mm
1 | 2023-06-05 | J8 | J9 | k.c | hdpe | 200
2 | 2023-06-05 | J8 | J9 | k.c | hdpe | 100 | [10 empty] | 14
3 | 2023-06-06 | J8 | J25 | k.c | hdpe | 200 | [10 empty] | 105
4 | 2023-06-06 | j8 | j4 | k.c | hdpe | 120 | [10 empty] | 78.5
5 | 2023-06-06 | j4 | j5 | k.c | hdpe | 80 | [10 empty] | 23.8
6 | 2023-06-07 | j4 | j5 | k.c | hdpe | 34 | [10 empty] | 41.2
7 | 2023-06-07 | j4 | j1 | k.c | hdpe | 126 | [10 empty] | 74.8
8 | 2023-06-08 | j4 | j1 | k.c | hdpe | 53 | [10 empty] | 24.5
9 | 2023-06-09 | j25 | j29 | k.c | hdpe | 63 | [10 empty] | 18.5
10 | 2023-06-11 | j25 | j29 | k.c | hdpe | 154 | [10 empty] | 60
11 | 2023-06-11 | j29 | j31 | k.c | hdpe | 119 | [10 empty] | 29.5
12 | 2023-06-11 | j31 | j32 | k.c | hdpe | 20 | [10 empty] | 55.4
13 | 2023-06-11 | j32 | j36 | k.c | hdpe | 36 | [10 empty] | 25.4
14 | 2023-06-11 | j50 | j48 | k.c | hdpe | 114 | [10 empty] | 15.4
15 | 2023-06-12 | j51 | j55 | k.c | hdpe |  |  | 100 | [8 empty] | 77.3
16 | 2023-06-12 | j55 | j67 | k.c | hdpe |  |  | 150 | [8 empty] | 24.5
17 | 2023-06-13 | j55 | j67 | k.c | hdpe |  |  | 135 | [8 empty] | 22.1
18 | 2023-06-13 | j67 | j77 | k.c | hdpe |  |  | 65 | [8 empty] | 47.5
19 | 2023-06-14 | j67 | j77 | k.c | hdpe |  |  | 100 | [8 empty] | 19
20 | 2023-06-14 | j67 | j75 | k.c | hdpe |  | 50 | [9 empty] | 39.9
21 | 2023-06-15 | J77 | J106 | k.c | hdpe |  |  | 62 | [8 empty] | 18.4
22 | 2023-06-15 | J67 | J75 | k.c | hdpe |  | 69 | [9 empty] | 123.5
23 | 2023-06-16 | j77 | j106 | k.c | hdpe |  |  | 100 | [8 empty] | 68.2
24 | 2023-06-16 | j77 | j78 | k.c | hdpe | 20 | [10 empty] | 95.7
25 | 2023-06-17 | j77 | j106 | k.c | hdpe |  |  | 200 | [8 empty] | 61.5
26 | 2023-06-18 | j77 | j106 | k.c | hdpe |  |  | 260 | [8 empty] | 8.4
27 | 2023-06-19 | j77 | j106 | k.c | hdpe |  |  | 30 | [8 empty] | 157
28 | 2023-06-19 | j106 | j107 | k.c | hdpe | 295 | [10 empty] | 22.2
29 | 2023-06-20 | j77 | j78 | k.c | hdpe | 80 | [10 empty] | 69.8
30 | 2023-06-20 | j78 | j80 | k.c | hdpe | 30 | [10 empty] | 84.2
31 | 2023-06-20 | j80 | j105 | k.c | hdpe | 155 | [10 empty] | 28.5
32 | 2023-06-21 | j80 | j105 | k.c | hdpe | 161 | [10 empty] | 117.2
33 | 2023-06-21 | j80 | j76 | k.c | hdpe | 62 | [10 empty] | 16
34 | 2023-06-21 | j76 | j75 | k.c | hdpe |  | 80 | [9 empty] | 96.3
35 | 2023-06-22 | j67 | j75 | k.c | hdpe |  | 120 | [9 empty] | 288.8
36 | 2023-06-22 | j75 | j59 | k.c | hdpe |  | 80 | [9 empty] | 115.1
37 | 2023-06-23 | j59 | j57 | k.c | hdpe |  | 76 | [9 empty] | 34.2
38 | 2023-06-23 | j59 | j60 | k.c | hdpe | 6 | [10 empty] | 73.5
39 | 2023-06-23 | j57 | j58 | k.c | hdpe | 46 | [10 empty] | 47
40 | 2023-06-23 | j57 | j54 | k.c | hdpe |  | 74 | [9 empty] | 637
41 | 2023-06-25 | J105 | J116 | k.c | hdpe | 158 | [10 empty] | 7
42 | 2023-06-25 | J80 | J105 | k.c | hdpe | 30 | [10 empty] | 275.6
43 | 2023-06-25 | J105 | J103 | k.c | hdpe | 11 | [10 empty] | 11
44 | 2023-06-25 | J57 | J54 | k.c | hdpe |  | 26 | [9 empty] | 3
45 | 2023-09-21 | j106 | j108 | k.c | hdpe |  | 96 | [9 empty] | 8
46 | 2023-09-21 | j108 | j114 | k.c | hdpe |  | 27
47 | 2023-09-21 | j114 | j128 | k.c | hdpe |  | 75
48 | 2023-09-21 | j128 | j130 | k.c | hdpe |  | 10
49 | 2023-09-21 | j130 | j133 | k.c | hdpe |  | 58
50 | 2023-09-22 | j133 | j135 | k.c | hdpe | 11
51 | 2023-09-22 | j135 | j148 | k.c | hdpe | 51
52 | 2023-09-22 | j148 | j153 | k.c | hdpe | 56
53 | 2023-09-22 | j153 | j156 | k.c | hdpe | 16
54 | 2023-09-22 | j156 | j166 | k.c | hdpe | 19
55 | 2023-09-22 | j166 | j172 | k.c | hdpe | 52
56 | 2023-09-22 | j172 | j173 | k.c | hdpe | 57
57 | 2023-09-22 | j172 | j179 | k.c | hdpe | 76
58 | 2023-09-22 | j179 | j180 | k.c | hdpe | 66
59 | 2023-09-22 | j180 | j181 | k.c | hdpe | 28
60 | 2023-09-22 | j181 | j171 | k.c | hdpe | 70
61 | 2023-09-23 | j171 | j151 | k.c | hdpe | 267
62 | 2023-09-23 | j171 | j169 | k.c | hdpe | 122
63 | 2023-09-23 | j169 | j183 | k.c | hdpe | 217
64 | 2023-09-24 | j156 | j157 | k.c | hdpe | 84
65 | 2023-09-24 | j179 | j177 | k.c | hdpe | 20
66 | 2023-09-24 | j177 | j175 | k.c | hdpe | 45
67 | 2023-09-24 | j175 | j174 | k.c | hdpe | 23
68 | 2023-09-24 | j174 | j176 | k.c | hdpe | 34
69 | 2023-09-24 | j109 | j110 | k.c | hdpe | 66
70 | 2023-09-24 | j110 | j112 | k.c | hdpe | 24
71 | 2023-09-24 | j110 | j111 | k.c | hdpe | 10
72 | 2023-09-24 | j173 | j166 | k.c | hdpe | 74
73 | 2023-09-24 | j176 | j180 | k.c | hdpe | 55
74 | 2023-09-24 | j108 | j109 | k.c | hdpe |  | 22
75 | 2023-09-24 | j109 | j113 | k.c | hdpe |  | 17
76 | 2023-09-24 | j113 | j118 | k.c | hdpe |  | 36
77 | 2023-09-25 | j118 | j122 | k.c | hdpe |  | 38
78 | 2023-09-25 | j122 | j125 | k.c | hdpe | 55
79 | 2023-09-25 | j122 | j137 | k.c | hdpe | 104
80 | 2023-09-25 | j137 | j146 | k.c | hdpe | 392
81 | 2023-09-25 | j146 | j145 | k.c | hdpe | 15
82 | 2023-09-25 | j145 | j147 | k.c | hdpe | 113
83 | 2023-09-25 | j137 | j138 | k.c | hdpe | 17
84 | 2023-09-25 | j138 | j144 | k.c | hdpe | 122
85 | 2023-09-25 | j144 | j149 | k.c | hdpe | 83
86 | 2023-09-25 | j149 | j150 | k.c | hdpe | 70
87 | 2023-09-25 | j149 | j158 | k.c | hdpe | 92
88 | 2023-09-25 | j158 | j168 | k.c | hdpe | 42
89 | 2023-09-25 | j169 | j168 | k.c | hdpe | 29
90 | 2023-09-25 | j168 | j164 | k.c | hdpe | 34
91 | 2023-09-25 | j164 | j163 | k.c | hdpe | 24
92 | 2023-09-25 | j163 | j162 | k.c | hdpe | 97
93 | 2023-09-25 | j168 | j170 | k.c | hdpe | 35
94 | 2023-09-25 | j170 | j167 | k.c | hdpe | 61
95 | 2023-09-25 | j167 | j155 | k.c | hdpe | 57
96 | 2023-09-25 | j155 | j148 | k.c | hdpe | 90
97 | 2023-09-25 | 174 | 170 | k.c | hdpe | 40
228
Work Done Qty In ( Rmt ) : | [5 empty] | 5588 | 954 | 1202 | 0 | 0 | 228 |  |  | 7744
Restricting Exceeded Qty's to WO Qty's
Total Quantity Considered for bill ( In RMT )=
Abstract (Bill Breakup)
1 | Dia of Pipe | WO/DPR Qty's | Laying, Jointing, Backfilling - 60% |  |  |  | Gap Closing- 5% | [6 empty] | FHTC Stretch - 10%
|  |  | Laying Up to Date | Laying Qty Billed up to Date | Qty Billed Up to Previous | This Bill Qty (Laying) | WO/DPR Qty's | GAP Closing Billed Qty up to Date | GAP Closing Qty Up to Previous | This Bill Qty (GAP Closing) | Hydro Test Qty Billed up to Date | Hydro Test Qty Up to Previous | This Bill Qty (Hydro Test ) | FHTC Stretch Qty Billed up to Date | FHTC Stretch Qty Billed Up to Previous | This Bill Qty (FHTC Stretch Billed ) | Remarks
1.1 | 63 mm HDPE | 12324 | 5588 | 5588 | 2473 | 3115 |  |  |  | 0 | 10411.9 |  | 10411.9 |  |  | 0
1.2 | 75 mm HDPE | 1649 | 954 | 954 | 575 | 379 |  |  |  | 0 | 2054.4 |  | 2054.4 |  |  | 0
1.3 | 90 mm HDPE |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 1402.8 |  | 1402.8 |  |  | 0
1.4 | 110mm HDPE | 1167 | 1202 | 1202 | 1202 | 0 |  |  |  | 0 | 1819 |  | 1819 |  |  | 0
1.5 | 125mm HDPE | 590 | 0 | 0 | 0 | 0 |  |  |  | 0 | 528 |  | 528 |  |  | 0
1.6 | 140mm HDPE | 459 | 0 | 0 | 0 | 0 |  |  |  | 0 | 982 |  | 982 |  |  | 0
1.7 | 160mm HDPE | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 228 |  | 228 |  |  | 0
1.8 | 180mm HDPE |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
1.9 | 200mm HDPE |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
Sub Total = |  | 16189 | 7744 | 7744 | 4250 | 3494 | [5 empty] | 0 | 17426.1 | 0 | 0 | 0
Sub-Contractor Site Engineer (Sr.Eng/ AM-SMX ) (Dy.M-PMX ) AGM Project Incharge

## Reconsilation Statement AB
POWER MECH PROJECTS.LIMITED
RURAL WATER SUPPLY PROJECT UNDER JJM, UP - PRAYAGRAJ
Reconciliation Statement - Issued Vs Certification Qty.
#REF! | [11 empty] | #REF!
Sl NO | Description | Units | Atrasand & Parasupur |  | Saray Jamuvari |  | Total |  | Balance Qty | Avilable at Site |  | Remarks
|  |  | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty | Issued Qty | Consumed Qty |  |  | SAP Entry |  |  | Balance In Sap
1 | HDPE Pipe :-
| 63mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2800 | #REF! | 2600 | #REF! | 14300 | 11711.2 | 2588.8 |  | 5358.2 | 6353 |  | 6353 | done | 5987
| 75 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3300 | #REF! | 2100 | #REF! | 6636 | 5075.5 | 1560.5 |  | 4537.3 | 538.2 |  | 538.2 |  | 750
| 90 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 2400 | #REF! | 600 | #REF! | 3900 | 3334.6 | 265.4 |  | 2759.6 | 575 |  | 575 |  |  |  | 4900
| 110 mm dia HDPE Pipe-PN6 Class PE100 | Rmt | 3050 | #REF! | 1475 | #REF! | 5950 | 5950 | 0 |  | 4758.1 | 1191.9 |  | 1191.9 |  | 600 |  | 900
| 125 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | #REF! |  | #REF! |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 1100
| 140 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | #REF! | 1800 | #REF! | 3480 | 2465.7 | 1014.3 |  | 2465.7 | 0 |  | 0
| 160 mm dia HDPE Pipe-PN6 Class PE100 | Rmt |  | #REF! | 600 | #REF! | 1020 | 886.7 | 133.3 |  | 886.7 | 0 |  | 0
| 250DI K-7 | Rmt | 840 | #REF! |  | #REF! | 840 | 740 | 100 |  |  | 740 |  | 740 |  | 300
| Total Qty In ( Rmt ) = | [5 empty] | 36126 | 30163.7 | 5662.3
2 | Specials :-
Equal Tee
| 63mm | No's | 19 | 1 | 8 |  | 27 | 1 | 26 |  | 1 | 0 |  | 0 |  | 20 | 13
| 75mm | No's | 10 | 1 |  |  | 10 | 1 | 9 |  | 1 | 0 |  | 0
| 90mm | No's | 7 | 3 | 1 |  | 8 | 3 | 5 |  | 3 | 0 |  | 0 |  | 2 | 2
| Total Qty In ( No's ) = | [5 empty] | 45 | 5 | 40
Branch TEE
| 75 mm X 63 mm | No's | 10 | 7 | 4 | 3 | 14 | 14 | 0 |  | 14 | 0 |  | 0 |  | 2 | 1
| 90 mm X 63 mm | No's | 18 | 3 |  |  | 18 | 3 | 15 |  | 3 | 0 |  | 0
| 90 mm X 75 mm | No's | 15 |  |  |  | 15 | 0 | 15 |  |  | 0 |  | 0
| 110 mm X 63 mm | No's | 12 | 11 | 2 |  | 15 | 11 | 4 |  | 11 | 0 | J-7, J-13, J-32,J-2 | 0 |  | 1 | 1
| 110 mm X 75 mm | No's | 2 | 1 | 8 | 3 | 12 | 4 | 8 |  | 4 | 0 |  | 0 |  | 1 | 1
| 110mm X 90 mm | No's | 6 | 4 |  |  | 6 | 6 | 0 |  | 6 | 0 | J-68 | 0
| 140mm X 63 mm | No's |  |  | 3 | 1 | 3 | 1 | 2 |  | 1 | 0 | J-38 | 0
| 140mm X 75 mm | No's |  |  | 3 | 1 | 3 | 1 | 2 |  | 1 | 0 | J-67 | 0
| 140mm X 90 mm | No's |  |  | 2 | 1 | 2 | 1 | 1 |  |  | 1 |  | 1
| 160mm X 63 mm | No's |  |  | 2 |  | 2 | 0 | 2 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 88 | 41 | 47
4-Way Tee
| 63mm | No's | 1 |  |  |  | 1 | 0 | 1 | [6 empty] | 20 | 13
| Total Qty In ( No's ) = | [5 empty] | 1 | 0 | 1
Reducers
| 75mm X 63 mm | No's | 21 | 3 | 5 | 1 | 26 | 10 | 16 |  | 10 | 0 | J-12 | 0 |  | 3 | 3
| 90mm X 63 mm | No's | 4 | 2 | 2 |  | 16 | 3 | 13 |  | 3 | 0 | J-7 | 0 |  | 2 | 2
| 90mm X 75 mm | No's | 14 |  |  |  | 24 | 0 | 24 |  |  | 0 |  | 0 |  | 2 | 2
| 110 mm X 75 mm | No's | 2 |  |  |  | 2 | 0 | 2 |  |  | 0 | J-83,J-101 | 0 |  | 1
| 110 mm X 63 mm | No's |  |  |  |  | 5 | 0 | 5 |  |  | 0 |  | 0
| 110 mm X 90 mm | No's |  |  | 1 |  | 11 | 0 | 11 |  |  | 0 | J-130 | 0
| 140mm X 75 mm | No's |  |  | 6 | 1 | 6 | 1 | 5 |  | 1 | 0 |  | 0
| 160mm X 90 mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 160mm X 140mm | No's |  |  |  |  | 0 | 0 | 0 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 90 | 14 | 76
| Bends | [5 empty] | 0 | 0
| 90mm ( 45 Deg ) | [5 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
| 140mm ( 45 Deg ) | [5 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
| Total Qty In ( No's ) = | [5 empty] | 0 | 0 | 0
| End Caps | [10 empty] | 0 |  | 0
| 63mm | No's | 27 |  |  |  | 47 | 0 | 47 |  |  | 0 |  | 0 |  | 10 | 1
| Total Qty In ( No's ) = | [5 empty] | 47 | 0 | 47
2 | FHTC
1 | G.I PIPE | MTRS |  |  |  |  | 145 | 52 | 93
2 | MDPE PIPE 20MM COIL-500MTRS | MTRS |  |  |  |  | 500 | 325 | 175
3 | PPCLamps saddle-63*1/2" | nos |  |  |  |  | 110 | 26 | 84
4 | PPCLamps saddle-75*1/2" | nos |  |  |  |  | 10 | 10 | 0
5 | PPCLamps saddle-90*1/2" | nos |  |  |  |  | 10 | 6 | 4
6 | PPCLamps saddle-110*1/2" | nos |  |  |  |  | 10 | 10 | 0
7 | PPCLamps saddle-125*1/2" | nos |  |  |  |  | 0 |  | 0
8 | PPCLamps saddle-140*1/2" | nos |  |  |  |  | 0 |  | 0
9 | PPCLamps saddle-160*1/2" | nos |  |  |  |  | 0 |  | 0
10 | PPCLamps saddle-200*1/2" | nos |  |  |  |  | 0 |  | 0
11 | pp comp fm theard adapter-20mm*1/2" | nos |  |  |  |  | 95 | 52 | 43
12 | pp comp fm theard elb off taken-20mm*1/2" | nos |  |  |  |  | 52 | 52 | 0
13 | threaded fcv-1/2"(15nb) | nos |  |  |  |  | 80 | 52 | 28
14 | GI elbow | nos |  |  |  |  | 340 | 104 | 236
15 | GI socket | nos |  |  |  |  | 195 | 52 | 143
16 | saddle g.i pipe-105mm(clamps) | nos |  |  |  |  | 130 |  | 130
17 | 15mm nipple-0.3mm | nos |  |  |  |  | 195 | 52 | 143
18 | 15mm nipple-0.5mm | nos |  |  |  |  | 195 | 52 | 143
19 | bib cock ptmt(taps) | nos |  |  |  |  | 165 | 52 | 113
20 | teflon tape | nos |  |  |  |  | 20 |  | 20
21 | GI nails | nos |  |  |  |  | 220 |  | 220
Prepared by Checked By Stores AM PMX Project Incharge