## GEHRAULI
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI | [11 empty] | Block: MANGRAURA GP: GEHRAULI
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date 17-3-2023 | [5 empty] | Date of Testing …………………………………. | 2023-03-17 |  |  |  |  | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing …………………………………. | [5 empty] | Date | [5 empty] | Date of Testing ………………………………….
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 126.3 | J2 | J51 | 522 | 6KG/CM2 | 17-03-2023(09:30AM) | 17-03-2023(12:30PM) | 3:00 |  |  | 1 | HDPE | 140 | j33 | j72 | 227.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 63 | j29(1) | j29(2) | 362 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 63 | j9 | j20 | 96.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 1 | HDPE | 63 | J99 | J59 | 43.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 1 | HDPE | 63 | J144 | J148 | 45.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | HDPE | 126.3 | J51 | J33 | 423 | 6KG/CM2 | 17-03-2023(09:30AM) | 17-03-2023(12:30PM) | 3:00 |  |  | 2 | HDPE | 140 | j72 | j74 | 68 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 63 | j155 | j115 | 305.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 63 | j9 | j20 | 10.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 2 | HDPE | 63 | J99 | J59 | 17 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 2 | HDPE | 63 | J148 | J145 | 101.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | [11 empty] | 3 | HDPE | 140 | j74 | j94 | 34.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | j166 | j162 | 133.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 63 | j20 | j26 | 56 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 3 | HDPE | 63 | J103 | J70 | 25.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 3 | HDPE | 63 | J145 | J53 | 31.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 4 | HDPE | 125 | j72 | j88 | 88 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 63 | j162 | j155 | 211.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 63 | j26 | j28 | 20 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 4 | HDPE | 63 | J103 | J70 | 4.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 4 | HDPE | 63 | J145 | J40 | 121.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
Name: | [11 empty] | 5 | HDPE | 125 | j88 | j84 | 94.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 63 | j162 | j155 | 7.5 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 63 | j26 | j21 | 12.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 5 | HDPE | 63 | J70 | J141 | 109.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 5 | HDPE | 63 | J40 | J22 | 34 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
Signature: |  | already paid | [9 empty] | 6 | HDPE | 63 | j122 | j104 | 733.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | j155 | j44 | 106.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | j21 | j54 | 93 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 6 | HDPE | 63 | J112 | J70 | 24 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 6 | HDPE | 63 | J22 | J125 | 22.8 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 7 | HDPE | 63 | j122 | j39 | 116 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | j44 | j124 | 132.8 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | j54 | j159 | 100.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 7 | HDPE | 63 | J136 | J105 | 32 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 7 | HDPE | 63 | J22 | J20 | 55.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 8 | HDPE | 63 | j122 | j39 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 63 | j124 | j30 | 61.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 63 | j54 | j159 | 12.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 8 | HDPE | 63 | J135 | J131 | 35.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 8 | HDPE | 63 | J21 | J138 | 38.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 9 | HDPE | 63 | j104 | j64 | 33.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | j124 | j128 | 31.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 63 | j159 | j123 | 21.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 9 | HDPE | 63 | J84 | J60 | 2.3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 9 | HDPE | 63 | J138 | J153 | 36.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 10 | HDPE | 63 | j64 | j151 | 65.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 63 | j128 | j45 | 61.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | j123 | j82 | 78 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 10 | HDPE | 63 | J84 | J60 | 232.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 10 | HDPE | 63 | J114 | J138 | 19.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 11 | HDPE | 63 | j151 | j158 | 49 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 63 | j128 | j81 | 100.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | j149 | j163 | 28 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 11 | HDPE | 63 | J84 | J60 | 131.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 11 | HDPE | 63 | J148 | J125 | 71.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 12 | HDPE | 63 | j151 | j13 | 168.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 63 | j56 | j10 | 112.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | j163 | j140 | 27.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 12 | HDPE | 110 | J84 | J101 | 67.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 12 | HDPE | 63 | J159 | J139 | 61.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 13 | HDPE | 63 | j151 | j13 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 63 | j44 | j27 | 74.6 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 63 | j163 | j140 | 33.7 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 13 | HDPE | 63 | J101 | J134 | 30.4 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 13 | HDPE | 63 | J118 | J90 | 55.3 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 14 | HDPE | 63 | j13 | j18 | 40.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | j27 | j15 | 51.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 63 | j140 | j123 | 39 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 14 | HDPE | 110 | J101 | J111 | 519.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 14 | HDPE | 63 | J102 | J46 | 38.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 15 | HDPE | 63 | j13 | j16 | 46.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 63 | j162 | j146 | 170.9 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 63 | j140 | j89 | 86 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 15 | HDPE | 63 | J111 | J108 | 38.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | 15 | HDPE | 63 | J165 | J167 | 275 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 16 | HDPE | 63 | j16 | j64 | 68 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | j146 | j64 | 123 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 63 | j89 | j41 | 56.8 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 16 | HDPE | 63 | J108 | J117 | 82.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | 17 | HDPE | 63 | j16 | j64 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 63 | j164 | j133 | 81 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 63 | j89 | j41 | 18.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 17 | HDPE | 63 | J117 | J36 | 56.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | Name:
[12 empty] | 18 | HDPE | 63 | j16 | j11 | 104.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 63 | j133 | j167 | 177 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 63 | j89 | j94 | 61.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 18 | HDPE | 63 | J117 | J120 | 87.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO |  | Signature:
[12 empty] | 19 | HDPE | 63 | j104 | j42 | 72.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 63 | j146 | j142 | 71.7 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 63 | j74 | j113 | 38.9 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 19 | HDPE | 63 | J120 | J129 | 14.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 20 | HDPE | 63 | j104 | j42 | 26.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 63 | j142 | j137 | 126.5 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | j113 | j163a | 90 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 20 | HDPE | 63 | J120 | J67 | 27 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 21 | HDPE | 63 | j167 | j166 | 86 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | j142 | j82 | 269.4 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | j113 | j163a | 8.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 21 | HDPE | 63 | J90 | J69 | 3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 22 | HDPE | 63 | j167 | j166 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 63 | j133 | j143 | 90 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 63 | j163a | j163 | 21.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 22 | HDPE | 63 | J90 | J69 | 22 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 23 | HDPE | 63 | j166 | j126 | 335 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | j164 | j160 | 72.1 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 63 | j113 | j86 | 102.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 23 | HDPE | 63 | J90 | J90A | 3.3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 24 | HDPE | 63 | j126 | j34 | 142.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 63 | j160 | j154 | 77.2 | 6KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | j86 | j92 | 18.1 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 24 | HDPE | 63 | J90A | J132 | 121 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 25 | HDPE | 63 | j34 | j24 | 27.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 25 | HDPE | 63 | j98 | j86 | 13.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 25 | HDPE | 63 | J132A | J132B | 20.6 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 26 | HDPE | 63 | j34 | j24 | 3.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | Name: | [11 empty] | 26 | HDPE | 63 | j90 | j98 | 29 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 26 | HDPE | 63 | J132 | J149 | 26.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 27 | HDPE | 63 | j126 | j55 | 53.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | Signature: | [11 empty] | 27 | HDPE | 63 | j2(b) | j5 | 44 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 27 | HDPE | 63 | J149 | J163 | 29 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 28 | HDPE | 63 | j55 | j115 | 52.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 28 | HDPE | 63 | j5 | j4 | 77 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 28 | HDPE | 63 | J149 | J107 | 45.7 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 29 | HDPE | 63 | j115 | j29 | 67.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 29 | HDPE | 63 | j5 | j5(1) | 8.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 29 | HDPE | 63 | J149 | J107 | 9.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 30 | HDPE | 63 | j29 | j55 | 74 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 30 | HDPE | 63 | j5(1) | j8 | 35.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 30 | HDPE | 63 | J98 | J87 | 3 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | 31 | HDPE | 63 | j34 | j29(1) | 100 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO | [13 empty] | 31 | HDPE | 63 | j5 | j2 | 37.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 31 | HDPE | 63 | J98 | J87 | 35.2 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[14 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. | [14 empty] | 32 | HDPE | 160 | j2(a) | j2(b) | 192 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 32 | HDPE | 140 | J94 | J78 | 133.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Name: | [23 empty] | 33 | HDPE | 63 | j76 | j100 | 55.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 33 | HDPE | 125 | J78 | J76A | 100 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[12 empty] | Signature: | [23 empty] | 34 | HDPE | 63 | j76 | j100 | 3.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 34 | HDPE | 110 | J76A | J76 | 49 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 35 | HDPE | 63 | j73 | j71 | 60.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 35 | HDPE | 90 | J76 | J93 | 86 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 36 | HDPE | 63 | j73 | j57 | 81.5 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 36 | HDPE | 110 | J33 | J65 | 216.9 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 37 | HDPE | 63 | j57 | j79 | 37.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 37 | HDPE | 63 | J65 | J63 | 27.8 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 38 | HDPE | 63 | j57 | j47 | 47.6 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 38 | HDPE | 90 | J65 | J118 | 136.6 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 39 | HDPE | 63 | j108 | j73 | 147 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 39 | HDPE | 63 | J118 | J160 | 202.5 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 40 | HDPE | 90 | J93 | j122 | 214 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | 40 | HDPE | 63 | J82 | J144 | 56.9 | 5KG/CM2 | 3.2 | 1 | 4.2 | NO
[36 empty] | 41 | HDPE | 63 | J129 | J66 | 373.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[36 empty] | 42 | HDPE | 63 | J129 | J66 | 3 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | Name:
[36 empty] | 43 | HDPE | 63 | J129 | J135 | 27.4 | 5.5KG/CM2 | 3 | 1 | 4 | NO |  | Signature:
[36 empty] | 44 | HDPE | 63 | J135 | J136 | 12 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 45 | HDPE | 63 | J136 | J103 | 34 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 46 | HDPE | 63 | J103 | J99 | 23.2 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[36 empty] | 47 | HDPE | 63 | J99 | J150 | 40.3 | 5.5KG/CM2 | 3 | 1 | 4 | NO
[38 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Signature:

## attarsand pr
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [9 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [9 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Contractor :- |  | Power Mech Project Ltd.
Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [11 empty] | Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
Date | 2023-06-22 |  |  |  |  | Date of Testing | 2023-06-22 |  |  |  |  | Date | 2023-06-24 |  |  |  |  | Date of Testing |  | 2023-06-24 |  |  |  | Date | [5 empty] | Date of Testing
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [9 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 160 | j574 | j610 | 364.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 1 | HDPE | 110 | J738 | J733 | 180 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 90 | J262 | J554 | 63.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
2 | HDPE | 63 | j610 | j667 | 27.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 2 | HDPE | 160 | J616 | J552 | 56.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | J554 | J428 | 97.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
3 | HDPE | 160 | j610 | j450 | 431.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 3 | HDPE | 63 | J552 | J578 | 33 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 90 | J428 | J549 | 27.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
4 | HDPE | 160 | j450 | j616 | 45.1 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 4 | HDPE | 160 | J552 | J433 | 90.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | J428 | J517 | 182.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
5 | HDPE | 110 | j616 | j630 | 66.2 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 5 | HDPE | 75 | J433 | J475 | 107 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 110 | J594 | J504 | 165 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
6 | HDPE | 63 | j630 | j259 | 286.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 6 | HDPE | 63 | J475 | J658 | 128 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 110 | J504 | J490 | 30.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
7 | HDPE | 110 | j630 | j411 | 265 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 7 | HDPE | 63 | J475A | J658A | 69 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 90 | J504 | J503 | 47.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
8 | HDPE | 63 | j411 | j295 | 34 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 8 | HDPE | 75 | J475 | J532 | 12.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 110 | J503 | J247 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
9 | HDPE | 75 | j411 | j322 | 102.4 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 9 | HDPE | 63 | J532 | J758 | 56 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
10 | HDPE | 63 | j322 | j153 | 21.7 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 10 | HDPE | 75 | J532 | J527 | 77.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Name: |  | SHASHIRANJAN
11 | HDPE | 75 | j322 | j328 | 748.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 11 | HDPE | 75 | J527 | J494 | 53.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Designation: |  | ENGINEER
12 | HDPE | 160 | j626 | j574 | 185.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 12 | HDPE | 75 | J527 | J461 | 41.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Signature:
13 | HDPE | 110 | j574 | j339 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 13 | HDPE | 75 | J461 | J710 | 7.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Date:
14 | HDPE | 75 | j339a | j624 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 14 | HDPE | 63 | J710 | J727 | 32.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
15 | HDPE | 110 | j339 | j568 | 52 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 15 | HDPE | 75 | J710 | J304 | 113.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
16 | HDPE | 63 | j568 | j184 | 96 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 16 | HDPE | 63 | J304 | J309 | 68 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
17 | HDPE | 110 | j568 | j619 | 58.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 17 | HDPE | 140 | J368 | J433 | 238.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
18 | HDPE | 75 | j619 | j611 | 83 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 18 | HDPE | 75 | J461 | J561 | 73.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
19 | HDPE | 63 | j611 | j587 | 78 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 19 | HDPE | 75 | J561 | J583 |  | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
20 | HDPE | 75 | j611 | j663 | 90 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 20 | HDPE | 75 | J583 | J680 |  | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
21 | HDPE | 63 | j663 | j653 | 53 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 21 | HDPE | 63 | J580 | J676 | 65 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
22 | HDPE | 75 | j663 | j666 | 77 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 22 | HDPE | 75 | J680 | J643 | 29 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
23 | HDPE | 75 | j666 | j624 | 35 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 23 | HDPE | 63 | J643 | J357 | 62 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
24 | HDPE | 63 | j666 | j642a | 88.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 24 | HDPE | 75 | J643 | J570 | 45.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
25 | HDPE | 63 | j642a | j647 | 45.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 25 | HDPE | 63 | J570 | J440 | 36.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
26 | HDPE | 63 | j681 | j631 | 60 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 26 | HDPE | 63 | J570 | J536 | 50 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
27 | HDPE | 110 | j619 | j556 | 80 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 27 | HDPE | 160 | J751 | 659 | 649.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 5796
28 | HDPE | 63 | j556 | j651 | 64.3 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 28 | HDPE | 160 | J659 | J307 | 175.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 4927.5
29 | HDPE | 110 | j556 | j573 | 37.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 29 | HDPE | 160 | J751 | J660 | 97 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  |  |  | 653.4
30 | HDPE | 63 | j573 | j458 | 63.9 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 30 | HDPE | 63 | J660 | J349 | 90 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
31 | HDPE | 110 | j573 | j599a | 27 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 31 | HDPE | 160 | J660 | J698 | 183 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
32 | HDPE | 63 | j599a | j599b | 32 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 32 | HDPE | 140 | J690 | J143 | 57 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
33 | HDPE | 110 | j599a | j599a | 26 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 33 | HDPE | 63 | J143 | J306 | 86.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
34 | HDPE | 63 | j599 | j9 | 33 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 34 | HDPE | 140 | J143 | J203 | 96.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
35 | HDPE | 110 | j599 | j738 | 33.8 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 35 | HDPE | 63 | J203 | J459 | 21.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
36 | HDPE | 90 | j738 | j757 | 44.6 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 36 | HDPE | 140 | J203 | J227 | 13 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
37 | HDPE | 90 | j757 | j754 | 133 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 37 | HDPE | 63 | J227 | J227A | 113.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
38 | HDPE | 9 | j757 | j269 | 180 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 38 | HDPE | 140 | J227 | J310 | 65.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
39 | HDPE | 75 | j269 | j316 | 46.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 39 | HDPE | 140 | J310 | J368 | 27 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
40 | HDPE | 75 | j299 | j316 | 81 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 40 | HDPE | 63 | J368 | J368A | 57.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
41 | HDPE | 75 | j299 | j362 | 76 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 41 | HDPE | 110 | J689 | J465 | 57 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
42 | HDPE | 90 | j299 | j318 | 12 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 42 | HDPE | 110 | J465 | J682 | 64 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
43 | HDPE | 63 | j318 | j323 | 32.5 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 43 | HDPE | 110 | J465 | J682 | 85 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
44 | HDPE | 63 | j318 | j380 | 67 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 44 | HDPE | 110 | J742 | J695 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
45 | HDPE | 90 | j318 | j733 | 102 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 45 | HDPE | 110 | J210 | J181 | 30 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
46 | HDPE | 75 | j733 | j717 | 199 | 5KG/CM2 | 3.3 | 1 | 4.3 | NO |  | 46 | HDPE | 110 | J695 | J594 | 375 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 47 | HDPE | 110 | J594 | J517 | 65 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Name: |  | SHASHIRANJAN | [9 empty] | 48 | HDPE | 110 | J517 | J684 | 204 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Designation: |  | ENGINEER | [9 empty] | 49 | HDPE | 110 | J684 | J703 | 454 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Signature: | [11 empty] | 50 | HDPE | 63 | J751 | J716 | 252 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
Date: | [11 empty] | 51 | HDPE | 90 | J684 | J454 | 60.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 52 | HDPE | 63 | J454 | J219 | 32.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 53 | HDPE | 63 | J219 | J191 | 21.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 54 | HDPE | 63 | J219 | J628 | 40 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 55 | HDPE | 90 | J454 | J549 | 72.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 56 | HDPE | 63 | J219A | J219B | 52 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 57 | HDPE | 63 | J549 | J246 | 146.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 58 | HDPE | 63 | J246A | J246B | 61 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[12 empty] | 59 | HDPE | 63 | J246A | J262 | 181 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO
[14 empty] | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[12 empty] | Name: |  | SHASHIRANJAN
[12 empty] | Designation: |  | ENGINEER
Signature:
Date:

## attarasand khayathi
| HYDROSTATIC TEST FOR PRESSURE PIPES | [12 empty] | HYDROSTATIC TEST FOR PRESSURE PIPES
HYDROSTATIC TEST FOR PRESSURE PIPES
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [10 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [10 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
TPI :- |  | Medhaj Techno Concept Pvt . Ltd. | [10 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [10 empty] | Contractor :- |  | Power Mech Project Ltd. | [9 empty] | Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh
Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR | [12 empty] | Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR | [11 empty] | Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh
Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [6 empty] | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO …………………….. | [5 empty] | TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
[25 empty] | Contractor :- |  | Power Mech Project Ltd.
Date | [5 empty] | Date of Testing | [6 empty] | Date | [5 empty] | Date of Testing | [5 empty] | Block: MANGRAURA, G.P-ATTARASAND AND PARASPUR
SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark |  | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark | Dail Log Ref. …………………. | [5 empty] | Tested as per CPHEEO ……………………..
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [10 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
1 | HDPE | 90 | J650 | J633 | 8.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 1 | HDPE | 63 | J638 | J266 | 41.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | Date | [5 empty] | Date of Testing
2 | HDPE | 90 | J633 | J711 | 126.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 2 | HDPE | 110 | J589 | J638 | 79.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | SL. No. | Material of Pipe | OD (MM) | Start Node | End Node | Length | Applied test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
3 | HDPE | 90 | J711 | J457 | 78.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 3 | HDPE | 110 | J638 | J489 | 50.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO | [8 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs
4 | HDPE | 75 | J395 | J270 | 87.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 4 | HDPE | 75 | J489 | J597 | 58.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 1 | HDPE | 110 | J714 | J718 | 195.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
5 | HDPE | 63 | J270 | J286 | 83.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 5 | HDPE | 63 | J597 | J605 | 13.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 2 | HDPE | 90 | J718 | J218 | 36.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
6 | HDPE | 90 | J711 | J719 | 26.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 6 | HDPE | 75 | J597 | J543 | 43.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 3 | HDPE | 63 | J218 | J448 | 26.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
7 | HDPE | 90 | J719 | J652 | 59.7 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 7 | HDPE | 63 | J543 | J606 | 142.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 4 | HDPE | 90 | J218 | J394 | 46.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
8 | HDPE | 90 | J652 | J612 | 22.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 8 | HDPE | 75 | J543 | J547 | 127.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 5 | HDPE | 90 | J462 | J394 | 46.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
9 | HDPE | 90 | J612 | J526 | 16.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 9 | HDPE | 63 | J588 | J547 | 133 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 6 | HDPE | 63 | J462 | J376 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
10 | HDPE | 90 | J526 | J538 | 13.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 10 | HDPE | 90 | J564 | J588 | 97.9 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 7 | HDPE | 63 | J524 | J382 | 120.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
11 | HDPE | 90 | J538 | J546 | 72.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 11 | HDPE | 75 | J547 | J564 | 53.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 8 | HDPE | 110 | J382 | J469 | 212.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
12 | HDPE | 90 | J546 | J614 | 89.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 12 | HDPE | 75 | J588 | J432 | 162.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 9 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
13 | HDPE | 63 | J300 | J652 | 22.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 13 | HDPE | 90 | J564 | J614 | 578.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 10 | HDPE | 63 | J338 | J410 | 94.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
14 | HDPE | 63 | J159 | J423 | 150.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 14 | HDPE | 110 | J614 | J418 | 232.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 11 | HDPE | 63 | J338 | J171 | 24.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
15 | HDPE | 63 | J509 | J596 | 57.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 15 | HDPE | 110 | J418 | J372 | 72.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 12 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
16 | HDPE | 63 | J596 | J405 | 75.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 16 | HDPE | 110 | J372 | J311 | 11.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 13 | HDPE | 75 | J469 | J463 | 75.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
17 | HDPE | 63 | J696 | J507 | 21.5 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 17 | HDPE | 110 | J311 | J287 | 21.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 14 | HDPE | 75 | J463 | J467 | 46.2 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
18 | HDPE | 63 | J501 | J151 | 49.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 18 | HDPE | 75 | J311 | J131 | 295.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 15 | HDPE | 75 | J467 | J478 | 49.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
19 | HDPE | 63 | J563 | J491 | 35.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 19 | HDPE | 110 | J287 | J589 | 272.6 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 16 | HDPE | 75 | J478 | J383 | 14.8 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
20 | HDPE | 63 | J427 | J73 | 139.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 20 | HDPE | 90 | J693 | J603 | 10.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 17 | HDPE | 75 | J383 | J382 | 81.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
21 | HDPE | 63 | J216 | J264 | 38.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 21 | HDPE | 90 | J603 | J313 | 182.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 18 | HDPE | 75 | J383 | J243 | 47.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
22 | HDPE | 63 | J264 | J420 | 23.4 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 22 | HDPE | 90 | J313 | J341 | 18.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 19 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
23 | HDPE | 75 | J171 | J277 | 54.2 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 23 | HDPE | 90 | J424 | J194 | 68.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 20 | HDPE | 63 | J201 | J544 | 137.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
24 | HDPE | 75 | J735 | J696 | 57.1 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 24 | HDPE | 63 | J194 | J680 | 30.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 21 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
25 | HDPE | 75 | J194 | J211 | 78.9 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 25 | HDPE | 110 | J194 | J395 | 98.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 22 | HDPE | 75 | J166 | J201 | 73.9 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
26 | HDPE | 75 | J211 | J128 | 39.8 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 26 | HDPE | 110 | J395 | J457 | 14.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 23 | HDPE | 75 | J166 | J131 | 93.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
27 | HDPE | 75 | J128 | J121 | 34.3 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 27 | HDPE | 90 | J457 | J496 | 98.5 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 24 | HDPE | 63 | J131 | J589 | 103.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
28 | HDPE | 75 | J121 | J106 | 32.6 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 28 | HDPE | 90 | J496 | J557 | 16.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 25 | HDPE | 63 | J462 | J374 | 83.6 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
29 | HDPE | 250 | J750 | J746 | 740 | 5.5KG/CM2 | 3.3 | 1 | 4.3 | NO |  |  | 29 | HDPE | 90 | J557 | J508 | 38.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 26 | HDPE | 63 | J479 | J462 | 17.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
| POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  |  | 30 | HDPE | 90 | J508 | J325 | 58.7 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 27 | HDPE | 110 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Name: | [12 empty] | 31 | HDPE | 90 | J325 | J699 | 57.3 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 28 | HDPE | 63 | J358 | J439 | 13.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Designation: |  | K.ANWESH KUMAR REDDY | [10 empty] | 32 | HDPE | 63 | J508 | J650 | 70.2 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 29 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Signature: |  | S.E ENGINEER | [10 empty] | 33 | HDPE | 90 | J650 | J453 | 72.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 30 | HDPE | 63 | J547 | J588 | 10.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
Date: | [12 empty] | 34 | HDPE | 90 | J672 | J529 | 65.4 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 31 | HDPE | 75 | J358 | J201 | 108.7 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[13 empty] | 35 | HDPE | 90 | J453 | J529 | 6.1 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 32 | HDPE | 75 | J469 | J338 | 44.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
|  | 63 | 75 | 90 | 250 | [7 empty] | 36 | HDPE | 75 | J529 |  | 292.8 | 5.5KG/CM2 | 3.5 | 1 | 4.5 | NO |  | 33 | HDPE | 90 | J696 | J646 | 97.5 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
|  | 695.8 | 384.1 | 513.8 | 740 | [8 empty] | POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P. |  |  | 34 | HDPE | 110 | J576 | J707 | 168.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[13 empty] | Name: | [11 empty] | 35 | HDPE | 63 | J171 | J167 | 111.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[13 empty] | Designation: |  | K.ANWESH KUMAR REDDY | [9 empty] | 36 | HDPE | 63 | J567 | J358 | 170.3 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[13 empty] | Signature: |  | S.E ENGINEER | [9 empty] | 37 | HDPE | 63 | J484 | J166 | 169.4 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
| HYDROSTATIC TEST FOR PRESSURE PIPES | [11 empty] | Date: | [11 empty] | 38 | HDPE | 63 | J194 | J680 | 30.1 | 6KG/CM2 | 3.2 | 1 | 4.2 | NO
[26 empty] | POWER MECH |  |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
[17 empty] | 63 | 75 | 90 | 110 |  |  |  |  | Name:
[17 empty] | 430.4 | 1033.6 | 1368.4 | 851.9 |  |  |  |  | Designation: |  | K.ANWESH KUMAR REDDY
Project:- |  | Rural water supply project Under JJM , Pratapgarh , Utter Pradesh | [22 empty] | Signature: |  | S.E ENGINEER
Client : - |  | State Water & Sanitation Mission Govt of Uttar Pradesh | [22 empty] | Date:
TPI :- |  | Medhaj Techno Concept Pvt . Ltd.
Contractor :- |  | Power Mech Project Ltd. | [24 empty] | 63 | 75 | 90 | 110
Block: MANGRAURA, G.P-ATTARSAND AND PARASPUR | [26 empty] | 1646.7 | 788.2 | 226.8 | 745.7
Dail Log Ref. …………………. | 2023-02-11 |  |  |  |  | Tested as per CPHEEO …………………….. | 2023-02-11 | [9 empty] | 63 | 75 | 90 | 110 | 250
[15 empty] | HYDRO |  | 3083.9 | 2760.9 | 2109 | 3011.5 | 740
Date11-2-2023 | [5 empty] | Date of Testing …………………………………. | 2023-02-11
SL. No. | Material of Pipe | ID (MM) | Start Node | End Node | Length | Appliede test pressure (kg/cm'2) | Time in Hrs |  |  | Observation | Remark
[7 empty] | Pressure rising time (Hrs) | Pressure Released time (Hrs) | Total Duration Hrs | [5 empty] | JMR |  | 3115 | 2768.2 | 2223.3 | 3011.5 | 740
1 | HDPE | 110 | J164 | J430 | 642 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
2 | HDPE | 110 | j430 | j567 | 216 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS | [7 empty] | 31.1 | 7.3 | 114.3 | 0 | 0
3 | HDPE | 110 | j567 | j544 | 107 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
4 | HDPE | 110 | j544 | j484 | 43.8 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
5 | HDPE | 110 | j484 | j489 | 14.1 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
6 | HDPE | 110 | j489 | j638 | 48 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
7 | HDPE | 110 | j638 | j589 | 42 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
8 | HDPE | 110 | j583 | j287 | 271 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
9 | HDPE | 110 | j287 | j311 | 20 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
10 | HDPE | 110 | j311 | j372 | 10 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
11 | HDPE | 63 | j567 | j358 | 168 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
12 | HDPE | 63 | j358 | j479 | 13 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
13 | HDPE | 63 | j544 | j201 | 130 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
14 | HDPE | 75 | j358 | j201 | 106 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
15 | HDPE | 75 | j201 | j166 | 73 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
16 | HDPE | 75 | j166 | j131 | 93 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
17 | HDPE | 75 | j131 | j311 | 283 | 5.5 | 11-02-2023(3:10)pm | 11-02-2023(6:10)pm | 3HRS
|  | POWER MECH |  |  |  | MEDHAJ |  |  | JAL NIGAM U.P.
Name:
Designation: |  | ALREADY BILL COMPLETED SIR
Signature:
Date:
|  |  |  | 63 | 75 | 110
|  |  |  | 311 | 555 | 1413.9
SR.NO | NAME | AADHAR NUMBER | PHONE NUMBER | MDPE PIPE | HDPE | START NODE | END NODE | s.no | description |  | units | 20660 | 20661 | 20662 | 20653 | 3813 | CONSUMED | BALANCE | TOTAL
1 | JAMUNA | 940253791176 | 8052246339 | 5 | 63 | J163 | J103 | 1 | G.I PIPE |  | MTRS | 30 | 15 | 100 |  |  | 52 | 93 | 145
2 | UMA PRAKASH | 651669258347 | 7379497850 | 5 | 63 | J163 | J103 | 2 | MDPE PIPE 20MM COIL-500MTRS |  | MTRS |  |  |  |  | 500 | 325 | 175 | 500
3 | RAM JAWAN | 958969999566 | 7800605950 | 5 | 63 | J163 | J103 | 3 | PPCLamps saddle-63*1/2" |  | nos |  |  |  | 90 | 20 | 26 | 84 | 110
4 | SURIBI | 919974595478 | 8354919254 | 7 | 63 | J163 | J103 | 4 | PPCLamps saddle-75*1/2" |  | nos |  |  |  |  | 10 | 10 | 0 | 10 |  | 10 | 6 | 10
5 | MADURI | 812635107926 | 9621559650 | 7 | 63 | J163 | J134 | 5 | PPCLamps saddle-90*1/2" |  | nos |  |  |  |  | 10 | 6 | 4 | 10
6 | RAM VALI | 740066163470 | 9670206036 | 5 | 63 | J163 | J134 | 6 | PPCLamps saddle-110*1/2" |  | nos |  |  |  |  | 10 | 10 | 0 | 10
7 | BAGHU YADAV | 511374774276 | 9670206036 | 7 | 63 | J163 | J134 | 7 | PPCLamps saddle-125*1/2" |  | nos | [7 empty] | 0
8 | SON KUMAR | 916490465213 | 8511731720 | 5 | 63 | J159 | J201 | 8 | PPCLamps saddle-140*1/2" |  | nos | [7 empty] | 0
9 | SAM TIWARI | 753683774896 | 9918703950 | 6 | 63 | J159 | J201 | 9 | PPCLamps saddle-160*1/2" |  | nos | [7 empty] | 0
10 | GAYATHRI DEVI | 347121308211 | 9594195325 | 5 | 63 | J159 | J201 | 10 | PPCLamps saddle-200*1/2" |  | nos | [7 empty] | 0
11 | TANDARA BERA SHIIMHA | 957458789465 |  | 5 | 63 | J159 | J201 | 11 | pp comp fm theard adapter-20mm*1/2" |  | nos |  | 15 |  | 30 | 50 | 52 | 43 | 95
12 | AFLAL | 573187004221 |  | 5 | 63 | J159 | J201 | 12 | pp comp fm theard elb off taken-20mm*1/2" |  | nos |  |  |  |  | 52 | 52 | 0 | 52
13 | FANLAL | 293638410994 |  | 5 | 63 | J159 | J201 | 13 | threaded fcv-1/2"(15nb) |  | nos |  |  |  | 30 | 50 | 52 | 28 | 80
14 | SIVAKANTH | 712145381832 |  | 5 | 63 | J275 | J269 | 14 | GI elbow |  | nos | 60 | 30 | 200 |  | 50 | 104 | 236 | 340
15 | SIVA KUMARI | 644805671515 | 7607026007 | 5 | 63 | J275 | J269 | 15 | GI socket |  | nos | 30 | 15 | 100 |  | 50 | 52 | 143 | 195
16 | YAMAYANAND YADSAV |  |  | 6 |  |  |  | 16 | saddle g.i pipe-105mm(clamps) |  | nos | 30 |  |  |  | 100 |  | 130 | 130
17 | DEVAMATI | 593139922449 | 8601732896 | 5 | 63 | J275 | J269 | 17 | 15mm nipple-0.3mm |  | nos | 30 | 15 | 100 |  | 50 | 52 | 143 | 195
18 | SUMITRA | 686418465551 | 9336369931 | 8 | 63 | J276 | J263 | 18 | 15mm nipple-0.5mm |  | nos | 30 | 15 | 100 |  | 50 | 52 | 143 | 195
19 | SHALI DEVI | 216854312481 |  | 7 | 110 | J19 | J27 | 19 | bib cock ptmt(taps) |  | nos |  | 15 | 100 |  | 50 | 52 | 113 | 165
20 | EFANA KUMARPHAL | 209737519600 |  | 9 | 110 | J19 | J27 | 20 | teflon tape |  | nos |  |  | 20 |  |  |  | 20 | 20
21 | DHARAM | 364034285803 |  | 5 | 110 | J19 | J27 | 21 | g.inails |  | nos | 120 |  |  |  | 100 |  |  | 220
22 | UBA DEVI | 387472011259 |  | 6 | 110 | J19 | J27
23 | RAM KUMAR PATH |  |  | 8
24 | SANGEETHA | 959480286558 |  | 7 | 63 | J275 | J269
25 | BHRUJ LAL | 736506891862 |  | 5 | 63 | J40 | J16
26 | RAM MILAN | 596852998499 |  | 6 | 63 | J40 | J16
27 | NATH NADTH | 521089037651 |  | 7 | 63 | J80 | J76
28 | AFTHINA | 522756481453 |  | 8 | 63 | J80 | J76
29 | MITHRA DEV YADAV | 378036851544 |  | 5 | 63 | J80 | J76
30 | RAM BAS VARMA | 293658226109 | 9105362179 | 6 | 63 | J80 | J76
31 | LAL MATHI | 718390198364 |  | 6 | 63 | J84 | J16
32 | RIKI SITA | 577905564520 | 8097764299 | 6 | 63 | J76 | J93
33 | SAMUNA PRASAD | 940253791176 | 8052246339 | 5 | 75 | J45 | J16
34 | OM PRAKESH | 651669258347 | 7379497850 | 8 | 75 | J45 | J16
35 | RAM JATHAN | 958969999566 | 7800605950 | 5 | 75 | J45 | J16
36 | SUSHIL | 919974595472 | 8354919254 | 5 | 75 | J45 | J16
37 | MADHURI | 812635107926 | 9621559650 | 7 | 75 | J45 | J16
38 | RAGHU NATH | 882907194434 | 9601065957 | 5 | 75 | J45 | J16
39 | VEERENDRA PRATAP | 383870701511 | 9918848531 | 6 | 75 | J45 | J20
40 | PRABHU RAM LALA | 513397242000 | 7526074878 | 4 | 75 | J45 | J20
41 | BAL RAM | 348780942346 | 9918848531 | 8 | 75 | J45 | J20
42 | PULAM DEVI | 261029437158 |  | 5 | 90 | J46 | J40
43 | KANTH LALA | 964375061210 | 7398167717 | 5 | 90 | J46 | J40
44 | RANI DENI | 244300127431 | 8874991073 | 6 | 90 | J46 | J40
45 | SALAN LAL | 954408909312 | 9721174391 | 8 | 90 | J14 | J34
46 | KEVAL DEVATH | 679778061734 | 7390031641 | 7 | 90 | J14 | J34
47 | GIRIJ TIWARI | 940053859769 | 9651025325 | 5 | 90 | J14 | J34
48 | RAM SHANKAR | 746712739410 | 9450401256 | 9 | 110 | J19 | J10
49 | MAMI TIWARI | 608632754926 | 9335501265 | 5 | 110 | J19 | J10
50 | ROSHANI TIWARI | 322727353442 |  | 4 | 75 | J45 | J20
51 | MAJUDATHI | 361800062225 |  | 7 | 110 | J19 | J27
52 | SAWMI NATH | 969393125842 | 9665077340 | 5 | 111 | J19 | J27
53 | SUGIL TIWARI | 334651125119 | 8953148385 | 9 | 112 | J19 | J27
54 | BHABITHA | 254701796741 | 7338650632 | 5 | 113 | J19 | J27
[5 empty] | 63 | 75 | 90 | 110
[5 empty] | 26 | 10 | 6 | 10

## heera pillar build con
Attarsand and paraspur heera pillar
SR.NO | start node | end node | DIA OF PIPE (mm) | mdpePIPE (meter) | OWNER NAME | AADHAR CARD NO | MOBILE NO | s.no | description | [5 empty] | units | ISSUED QTY |  | 19302 | 19305 | 19306 | 19301 | 19304 | 19308 | 19303 | 19309 | 19310 | 19311 | 19312 | 19313 | 19314 | 19315 | 19316 | 19317 | 19318 | 19319 | 19320 | Consumed | Balanced | TOTAL | 1st bill
1 | j402 | j314 | 63 | 6 | MUMTAS ALI | 722576725675 | 9721042868 | 1 | G.I PIPE | [5 empty] | MTRS | 1 |  |  |  | 50 |  |  | 100 | 70 |  |  | 100 |  |  | 100 |  |  |  | 100 |  |  | 321 | 199 | 520 | 133 | 321 | 188
2 | j646 | j713 | 90 | 7 | SALAUDDIN | 794846188118 | 9161714624 | 2 | MDPE PIPE 20MM COIL-500MTRS | [5 empty] | MTRS | 5 |  |  | 500 |  |  |  |  | 500 | 500 | 500 | 500 |  |  | 500 |  |  |  | 500 |  | 500 |  | 4000 | 4000 |  |  | 0
3 | j646 | j713 | 90 | 5 | VAHASUDDIN | 389201597589 | 9935337025 | 3 | PPCLamps saddle-63*1/2" | [5 empty] | nos | 1 |  | 20 | 25 |  | 50 | 30 | 80 |  |  | 50 |  |  |  | 20 |  |  |  | 20 |  |  | 195 | 100 | 295 | 103 |  | 92
4 | j646 | j713 | 90 | 4 | SALIM KHAN | 26837498259 | 7235982361 | 4 | PPCLamps saddle-75*1/2" | [5 empty] | nos | [12 empty] | 25 |  | 40 |  |  |  | 20 |  |  | 22 | 63 | 85 |  |  | 22
5 | j646 | j713 | 90 | 6 | MOHDIJAMALUABLEEN | 231427235294 | 7506151814 | 5 | PPCLamps saddle-90*1/2" | [5 empty] | nos |  |  | 30 |  |  | 10 |  | 20 |  |  | 50 |  |  |  | 40 |  |  |  | 50 |  |  | 101 | 99 | 200 | 30 |  | 71
6 | j646 | j713 | 90 | 8 | KHALIL KHAN | 555126212522 | 6387092155 | 6 | PPCLamps saddle-110*1/2" | [5 empty] | nos |  |  | 10 | [13 empty] | 15 |  | 10 |  |  |  | 35 | 35 |  |  | 0
7 | j646 | j713 | 90 | 5 | FAJAL KHAN | 337331277605 | 6390737925 | 7 | PPCLamps saddle-125*1/2" | [5 empty] | nos | [20 empty] | 10 |  | 10 | 10 |  |  | 0
8 | j646 | j713 | 90 | 8 | AFSANA BEGAN | 992909161205 | 9140209730 | 8 | PPCLamps saddle-140*1/2" | [5 empty] | nos | [20 empty] | 15 | 3 | 12 | 15 |  |  | 3
9 | j181 | j678 | 90 | 9 | REHANA | 953929669688 | 7388667882 | 9 | PPCLamps saddle-160*1/2" | [5 empty] | nos |  |  | 10 | [14 empty] | 50 |  |  |  |  | 60 | 60 |  |  | 0
10 | j422 | j401 | 90 | 10 | HAJIM KHAN | 596693783813 | 9005830682 | 10 | PPCLamps saddle-200*1/2" | [5 empty] | nos | [22 empty] | 0 | 0 |  |  | 0
11 | j212 | j135 | 63 | 6 | REHANA BANA | 457220875703 | 8953719154 | 11 | pp comp fm theard adapter-20mm*1/2" | [5 empty] | nos | 1 |  | 70 | 25 |  | 50 | 30 | 100 |  |  | 100 | 100 |  |  | 100 |  |  |  | 100 |  |  | 321 | 354 | 675 | 133 |  | 188
12 | j212 | j135 | 63 | 4 | MAHMMADEJAJ | 450420739898 | 7380414240 | 12 | pp comp fm theard elb off taken-20mm*1/2" | [5 empty] | nos | 1 |  | 70 | 25 |  | 50 |  | 100 |  |  |  | 100 |  |  | 100 |  |  |  | 100 |  |  | 321 | 224 | 545 | 133 |  | 188
13 | j141 | j253 | 90 | 6 | AKBAR KHAN | 959165671715 | 8756352423 | 13 | threaded fcv-1/2"(15nb) | [5 empty] | nos | 1 |  | 70 | 25 |  | 50 |  | 100 |  |  | 100 | 100 |  |  | 100 |  |  |  | 100 |  |  | 321 | 324 | 645 | 133 |  | 188
14 | j141 | j253 | 90 | 8 | MUSFAR | 647760265514 | 8999987445 | 14 | GI elbow | [5 empty] | nos | 2 |  | 70 | 50 |  |  |  | 200 |  |  | 100 |  | 50 |  | 200 |  |  |  | 200 |  |  | 642 | 228 | 870 | 133 |  | 509
15 | j141 | j253 | 90 | 9 | MAASARI | 368660403516 | 8382086012 | 15 | GI socket | [5 empty] | nos | 1 |  | 70 | 25 |  |  |  | 100 |  |  | 200 |  | 25 |  |  | 100 |  |  |  | 100 |  | 321 | 299 | 620 | 133 |  | 188
16 | j352 | j438 | 90 | 7 | lalti | 439931270121 | 9670632425 | 16 | saddle g.i pipe-105mm(clamps) | [5 empty] | nos | 2 | [21 empty] | 0 | 0 |  |  | 0
17 | j402 | j314 | 63 | 5 | Asagari bano | 784016710301 | 7388197097 | 17 | 15mm nipple-0.3mm | [5 empty] | nos | 1 |  |  | 25 |  |  |  |  | 70 | 100 | 100 | 100 |  |  | 100 |  |  |  |  | 100 |  | 321 | 274 | 595 | 133 |  | 188
18 | j402 | j314 | 63 | 2 | MOHD RAJA KHAN | 683771213913 | 9956892974 | 18 | 15mm nipple-0.5mm | [5 empty] | nos | 1 | [7 empty] | 70 | 100 | 100 |  |  |  |  | 100 |  |  |  | 100 |  | 321 | 149 | 470 | 133 |  | 188
19 | j402 | j314 | 63 | 3 | ANWAR | 209947531879 | 9935113787 | 19 | bib cock ptmt(taps) | [5 empty] | nos | 1 |  | 70 | [6 empty] | 100 |  |  |  | 150 |  | 100 |  |  |  | 150 | 50 | 321 | 299 | 620 | 133 |  | 188
20 | j402 | j314 | 63 | 6 | SANGITA | 277651671836 | 8422083820 | 20 | teflon tape | [5 empty] | nos | 1 | [7 empty] | 15 |  |  |  | 20 |  |  | 100 |  | 20 |  | 25 |  |  | 180 | 180 |  |  | 0
21 | j402 | j525 | 63 | 4 | ASIF KHAN | 740256309024 | 8127377686 | 21 | g.inails | [5 empty] | nos | 4 | [21 empty] | 0 | 0
22 | j402 | j525 | 63 | 5 | MOHD AKRAM | 488277053764 | 9175797662
23 | j402 | j525 | 63 | 5 | MO MUSLIM | 970083893375 | 7459076743
24 | j356 | j343 | 63 | 6 | ABIB KHAN | 841085072006 | 8127977686
25 | j356 | j343 | 63 | 3 | SALMA BEGAM | 844902584581 | 9935714424 | 63 | 75 | [5 empty] | 90 | 110 | 160 |  |  |  | 63 | 75 | 90 | 110 | 160 | 2nd bill
26 | j356 | j343 | 63 | 4 | BADSHAH KHAN | 922815701676 | 9793584439 | 79 | 0 | [5 empty] | 53 | 0 | 1 | 133 |  |  | 92 | 22 | 71 | 0 | 3 | 188
27 | j343 | j352 | 63 | 5 | KAYOO KHAN | 783788241288 | 9594651027
28 | j343 | j352 | 63 | 18 | GUFRAN KHAN | 805429228997 | 7897163219 | 63 | 75 | [5 empty] | 90 | 110 | 160
29 | j401 | j656 | 63 | 18 | KAMSAN NISHA | 390568234092 | 7897163219 | 13 | 22 | 13 | 13 | 13 | 13 | 13 | 18 | 0 | 2 | 55
30 | j401 | j656 | 63 | 11 | AYASHA BANO | 893359139588 | 8421947557
31 | j401 | j656 | 63 | 11 | AKBARI | 531382486247 | 9559746755
32 | j404 | j289 | 90 | 8 | SABIHA BANU | 807806827011 | 9559746755
33 | j404 | j289 | 90 | 5 | SAHNAJ | 479704002586 | 9519903703
34 | j404 | j289 | 90 | 15 | NOORJAHAN | 778210117038 | 7897008268
35 | j404 | j289 | 90 | 20 | SHABARAUN NISHA | 406064121887 | 9848766889
36 | j404 | j289 | 90 | 31 | KAUSHAR JAHAN | 720667877817 | 7318400368
37 | j404 | j289 | 90 | 30 | SHAHIN KHAN | 551065697192 | 7058958033
38 | j404 | j289 | 90 | 28 | JAMIL BEGAM | 681285169374 | 9695715582
39 | j404 | j289 | 90 | 14 | MUKTAR AHMED | 965547503729 | 9892388510
40 | j438 | j363 | 90 | 7 | JAMRATUL NISHA | 472336019483 | 7318053904
41 | j308 | j272 | 63 | 11 | GUDDAM DEVI | 832064611656 | 9565647823
42 | j308 | j272 | 63 | 11 | LALTI DEVI | 834816784422 | 7387680390
43 | j308 | j272 | 63 | 4 | RAM AVODH | 744307223774 | 7235975799
44 | j308 | j272 | 63 | 3 | RAVI RAJAK | 651701288660 | 9044039879
45 | j485 | j646 | 90 | 5 | LALTI | 838447951529 | 9695737921
46 | j485 | j646 | 90 | 5 | RAMESH | 984734808070 | 7458092990
47 | j485 | j646 | 90 | 3 | RAM CHANDRA VISHV KARMA | 214070222085 | 9670227383
48 | j485 | j646 | 90 | 4 | ANARKALI | 808268395284 | 8860816611
49 | j646 | j713 | 90 | 3 | RAMKISHAN | 899693248073 | 6387632767
50 | j646 | j713 | 90 | 5 | RAM AVADH | 685905425629 | 9956643653
51 | j646 | j713 | 90 | 6 | MOMIN | 951099067751 | 9935109975
52 | j654 | j181 | 90 | 4 | RAVIYA | 545981825609 | 9935736727
53 | j654 | j181 | 90 | 3 | RAZIYA BEGUM | 920994123409 | 9793140217
54 | j654 | j181 | 90 | 6 | AKBARI | 914747309441 | 9695722237
55 | j654 | j181 | 90 | 4 | JAVED KHAN | 725912675333 | 7388296199
56 | j401 | j654 | 90 | 5 | JAN MOHHAMAD | 271125110957 | 9793752731
57 | j401 | j654 | 90 | 5 | MOHAN LAL | 217870815621 | 8318968295
58 | j150 | j141 | 90 | 4 | JAGNNATH | 517629980253 | 7054539873
59 | j150 | j141 | 90 | 2 | SANTOSH KUMAR | 797298481310 | 8346962345
60 | j253 | j408 | 63 | 2 | GUDDI | 836843633574 | 9005520253
61 | j253 | j408 | 63 | 3 | LALGIBASE NUKANAUJIYA | 900507939877 | 9617024355
62 | j253 | j408 | 63 | 6 | SADDAM KHAN | 523247926382 | 9594286070
63 | j251 | j282 | 160 | 15 | MEERA DEVI | 480859512615 | 7081820926
64 | j282 | j350 | 63 | 4 | MEVALAL | 630810638564 | 8528512295
65 | j282 | j350 | 63 | 4 | YASHODA DEVI | 814490633029 | 8009582919
66 | j282 | j350 | 63 | 5 | MAHENDRA KUMAR | 965170048984 | 8528512295
67 | j351 | j321 | 63 | 3 | PRADEEP KUMAR | 200148576792 | 8928512295
68 | j525 | j518 | 63 | 5 | WAKIL AHMAD | 309156005860 | 8953112674
69 | j150 | j141 | 90 | 5 | MANDiR | nill | nill
70 | j289 | j320 | 90 | 4 | MOIDRISH | 846975509072 | 7998475211
71 | j104 | j168 | 63 | 5 | TEERATH RAJ | 594787646358 | 8257526584
72 | j104 | j168 | 63 | 7 | UDAY RAJ | 710359978738 | 9793017335
73 | j104 | j168 | 63 | 2 | ANISHUL NISHA | 543122505368 | 9321200172
74 | j104 | j168 | 63 | 7 | HALEEMA | 261410368524 | 7021913139
75 | j104 | j168 | 63 | 5 | JAGANNATH YADAV | 988959880665 | 8601749300
76 | j248 | j315 | 90 | 5 | RABEESUL | 442805195546 | 9956864119
77 | j248 | j315 | 90 | 10 | RIZWAM | 592971357320 | 8882916693
78 | j275 | j116 | 90 | 10 | ARMAN | 649101969819 | 8883617632
79 | j245 | j347 | 63 | 5 | MOHD JAHUR | 699101969819 | 8879764474
80 | j245 | j347 | 63 | 6 | SANITHA DEVI | 362554762093 | 8528560219
81 | j245 | j347 | 63 | 4 | BABULAL | 435471987514 | 8874091943
82 | j245 | j347 | 63 | 5 | RAM PRASAD | 673618095860 | 7897170064
83 | j337 | j531 | 63 | 3 | RAJESH | 776073790967 | 7388792741
84 | j337 | j531 | 63 | 5 | MAJIDA BANO | 776073790967 | 7388792741
85 | j315 | j156 | 90 | 3 | MOHD VARIS | 504945363609 | 7304089123
86 | j315 | j156 | 90 | 3 | HADISUL NISHA | 349108189042 | 9005500168
87 | j315 | j156 | 90 | 4 | RUKSANA | 421171351719 | 9085438050
88 | j315 | j156 | 90 | 4 | BADRUN NISHA | 202605520636 | 9919469862
89 | j294 | j295 | 63 | 3 | SHANTI | 702925777313 | 7225418219
90 | j294 | j295 | 63 | 4 | SUDHIRAM | 683674145661 | 7054832600
91 | j294 | j295 | 63 | 5 | RAMAJAR | 900499945046 | 8948815097
92 | j294 | j295 | 63 | 5 | PRADEEP KUMAR | 714767561430 | 7068182402
93 | j315 | j156 | 63 | 5 | BABULAL | 374395105626 | 7068182402
94 | j233 | j296 | 90 | 7 | SHANMUND | 894459168084 | 7317399326
95 | j233 | j296 | 90 | 6 | RUKSANA BANO | 887547647458 | 7317399326
96 | j275 | j116 | 90 | 7 | IMTIYAJ | 889082949529 | 7378989434
97 | j275 | j116 | 90 | 7 | MAD NADDIM | 917566765494 | 7316989327
98 | j315 | j156 | 63 | 5 | NEETA | 222662417174 | 9987240776
99 | j275 | j198 | 63 | 6 | SIKANDER | 842298132783 | 9948972537
100 | j275 | j198 | 63 | 7 | TEJRAM | 740182524578 | 7897192759
101 | j275 | j198 | 63 | 5 | GEETA DEVI | 771196846645 | 7369563012
102 | j233 | j185 | 63 | 5 | GUDDU HARI JAM | 866255425629 | 7880483881
103 | j233 | j185 | 63 | 4 | RAJ PATI SINGH | 346709460858 | 9005500134
104 | j198 | j231 | 63 | 10 | SANTOSH PRATAP SINGH | 274665956670 | 8707312251
105 | j705 | j416 | 63 | 4 | VIJAY PRATAP SINGH | 332038153446 | 8840582517
106 | j705 | j416 | 63 | 4 | ARAVIND PRATAP SINGH | 230803791182 | 9918311693
107 | j422 | j401 | 90 | 4 | RAJA RAM | 780218770448 | 8953901355
108 | j249 | j646 | 90 | 6 | MAHESH KUMAR | 565041484702 | 8115198106
109 | j249 | j646 | 90 | 5 | MOHD SHARIF | 231196633624 | 7800490687
110 | j212 | j135 | 63 | 2 | DIL SHAD ALI | 641445128859 | 8174026284
111 | j212 | j135 | 63 | 2 | MOSHAMSHAD | 589396271125 | 8737898948
112 | j212 | j135 | 63 | 5 | ANVAR ALI | 832676315198 | 6376353522
113 | j212 | j135 | 63 | 3 | ASIYA | 880079481344 | 9956968146
114 | j212 | j135 | 63 | 4 | ARUN PRATAP SINGH | 721374850678 | 9793558288
115 | j212 | j135 | 63 | 3 | RAJESH KUMAR | 363845931238 | 9170593435
116 | j212 | j135 | 63 | 4 | REETA | 2083479222236 | 8948124060
117 | j212 | j135 | 63 | 4 | RAM PIYARE VERMA | 881346142693 | 9119949667
118 | j212 | j135 | 63 | 3 | BHAGIRATHI VERMA | 478860713970 | 9936216057
119 | j212 | j135 | 63 | 2 | RAM MILAN | 672418087954 | 89219936350
120 | j212 | j135 | 63 | 4 | RAM RATI | 868678935334 | 8303928845
121 | j104 | j168 | 63 | 5 | DILIP KUMAR VERMA | 222626397572 | 6393787035
122 | j104 | j168 | 63 | 4 | SUNITHA | 943457739688 | 8607317292
123 | j104 | j168 | 63 | 6 | ASHOK KUMAR | 631646178267 | 9936498405
124 | j104 | j168 | 63 | 3 | PRAMOD KUMAR VERMA | 445141612936 | 7275432457
125 | j104 | j168 | 63 | 4 | BHANMATI | 853791914135 | 7081949420
126 | j212 | j135 | 63 | 3 | RAMPAL VERMA | 783456495859 | 9569019561
127 | j212 | j135 | 63 | 3 | PUSHPA VERMA | 991305188466 | 8601050969
128 | j212 | j135 | 63 | 4 | MEERA DEVI | 7482966688267 | 9918869827
129 | j212 | j135 | 63 | 3 | SANJAY | 255893615179 | 7851899427
130 | j212 | j135 | 63 | 2 | SHOBHNATH VERMA | 389983256412 | 8840970540
131 | j134 | j379 | 63 | 3 | MIRA | 493577987274 | 8874123379
132 | j134 | j379 | 63 | 3 | RAMDEV | 601598941795 | 9648148928
133 | j134 | j379 | 63 | 4 | RAHISUL BANO | 762393062881 | 8080393232
811
Sakra
1 | j106 | j74 | 160 | 2 | lalati dev | 981914945198 | 9919527419
2 | j44 | j14 | 75 | 4 | arada prasad | 481656210881 | 9918488176
3 | j44 | j130 | 75 | 6 | jairam | 542112388745 | 9721253980
4 | j44 | j130 | 75 | 7 | malikaram | 722191312618 | 9794604099
5 | j44 | j130 | 75 | 7 | shakuntal | 582565931540 | 9793857468
6 | j106 | j74 | 160 | 4 | seema | 348560608071 | 9670240813
7 | j14 | j34 | 63 | 2 | devi saran tiwari | 377012289253 | 9670240813
8 | j14 | j34 | 63 | 5 | kusun | 877629008850 | 9665797546
9 | j14 | j34 | 63 | 2 | ashwani tiwari | 497459522093 | 7275023359
10 | j97 | j107 | 90 | 6 | durpanthi devi | 514739905811 | 9428856024
11 | j97 | j107 | 90 | 2 | santosh kumar | 274446995215 | 9411095964
12 | j140 | j118 | 75 | 5 | suraj tiwari | 473525717545 | 8948343297
13 | j140 | j118 | 75 | 5 | kumkum tiwari | 664308910437 | 9919146419
14 | j145 | j223 | 75 | 4 | shubham tiwari | 929501533941 | 9598780426
15 | j14 | j37 | 63 | 7 | anita tiwari | 434617667600 | 7428115823
16 | j14 | j37 | 63 | 14 | kalawati devi | 433206465493 | 8948987457
17 | j113 | j139 | 90 | 3 | bajaranj bahadurpal | 444126186457 | 9621539654
18 | j145 | j223 | 75 | 3 | ram prasad | 695758514402 | 6355309751
19 | j145 | j223 | 75 | 8 | kalesh kumar tiwari | 980150043719 | 8400262528
20 | j148 | j54 | 75 | 4 | rajesh tiwari | 574560038644 | 9792265759
21 | j48 | j199 | 90 | 6 | vijay kumar tiwari | 201669961392 | 7800707505
22 | j148 | j54 | 75 | 5 | babloo | 637762038407 | 7307778613
23 | j148 | j54 | 75 | 2 | baliram saroj | 857487185806 | 7379363596
24 | j148 | j54 | 75 | 4 | sherbahadur saroj | 6032803823 | 9792922289
25 | j143 | j140 | 90 | 9 | manoj kumar | 209683493085 | 9892488403
26 | j143 | j140 | 90 | 6 | ram dular saroj | 596450091930 | 8948525637
27 | j143 | j140 | 90 | 6 | ram lakhan | 642099324339 | 9919094888
28 | j143 | j140 | 90 | 8 | jagpatta | 924282964317 | 9569106833
29 | j143 | j140 | 90 | 8 | jai prakash | 266878134943 | 9335328523
30 | j143 | j140 | 90 | 8 | vikram | 720534436313 | 8081171663
31 | j143 | j140 | 90 | 7 | vijay kumar | 386416484257 | 8737838711
32 | j107 | j143 | 90 | 10 | sangeetha | 411160850574 | 7081639216
33 | j107 | j143 | 90 | 5 | hari ram | 356250131798 | 8948297972
34 | j107 | j143 | 90 | 4 | anara devi | 253311190514 | 9918987124
35 | j110 | j226 | 63 | 3 | ram vati devi | 462695184848 | 8291722950
36 | j110 | j217 | 63 | 5 | tej bahadur yadav | 597330839648 | 8416915575
37 | j110 | j217 | 63 | 3 | nanhaku | 759159386472 | 9956463210
38 | j143 | j140 | 90 | 4 | gaya prasad | 744407882871 | 8604231900
39 | j27 | j84 | 63 | 5 | meera devi | 973433657175 | 7624800774
40 | j27 | j84 | 63 | 5 | chhote lal | 362824915830 | 7408158667
41 | j27 | j84 | 63 | 5 | meera devi | 973433657175 | 7275186721
42 | j223 | j103 | 75 | 6 | prem sheela | 551899462671 | 9621201311
43 | j143 | j140 | 90 | 4 | vaishali | 789414087763 | 912548950
44 | j143 | j140 | 90 | 9 | kiran | 977089865826 | 9919808702
45 | j65 | j113 | 90 | 6 | sarita | 541153734920 | 7843983946
46 | j54 | j112 | 63 | 6 | sakshi yadav | 810889149162 | 8052115593
47 | j54 | j116 | 63 | 9 | abhishek verma | 724019164691 | 7408158667
48 | j223 | j103 | 75 | 5 | sunita devi | 932272886969 | 7607442015
49 | j103 | j140 | 75 | 5 | manoj yadav | 995222576307 | 847836314
50 | j103 | j140 | 75 | 7 | arun kumar | 646052957711 | 9328297213
51 | j157 | j117 | 75 | 8 | deep-ak | 243958911887 | 8756272934
52 | j157 | j117 | 75 | 6 | prasad yadav | 941654851835 | 9514414900
53 | j157 | j117 | 75 | 6 | brijesh kumar | 810455787316 | 9793107743
54 | j122 | j65 | 75 | 7 | nirmala devi | 472931646149 | 8360346873
55 | j122 | j65 | 75 | 9 | surekha devi | 741268458412 | 7388719883
311

## PURBHIKA AND RAIGARH
PUREBHIKA AND RAIGARH | [7 empty] | REMARKS
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) AS PER SITE | CUMMULATIVE
1 | J64 | J31 |  |  | 63 | 117.5 | 117.5
2 | J22 | J64 |  |  | 63 | 178.5 | 296
3 | J31 | J53 |  |  | 63 | 188.3 | 484.3
4 | J53 | J53 |  |  | 63 | 8 | 492.3
5 | J64 | J60 |  |  | 63 | 2.1 | 494.4
6 | J60 | J54 |  |  | 63 | 120 | 614.4
7 | J54 | J59 |  |  | 63 | 125.9 | 740.3 |  |  |  | BRICK ROAD | INTERLOACKING | B.T ROAD
8 | J59 | J13 |  |  | 63 | 120.5 | 860.8 |  |  |  | 93 | 39.8 | 6
9 | J60 | J66 | BRICK ROAD | 0.36 | 63 | 93 | 953.8 |  |  |  | 53.4 | 33.2 | 4
10 | J66 | J65 |  |  | 63 | 49.9 | 1003.7 |  |  |  | 64.8 | 33.2 | 5
11 | J65 | J61 |  |  | 63 | 37.4 | 1041.1 |  |  |  | 287.5 | 120.4 | 7
12 | J65 | J73 |  |  | 63 | 53 | 1094.1 |  |  |  | 88.9 | 117.1 | 6.2
13 | J73 | J63 |  |  | 63 | 23.8 | 1117.9 |  |  |  | 203 | 17.4 | 6.4
14 | J63 | J61 |  |  | 63 | 59.9 | 1177.8 |  |  |  | 29.9 | 44.9
15 | J61 | J40 |  |  | 63 | 36.7 | 1214.5 |  |  |  | 100.3 | 40
16 | J40 | J3 |  |  | 63 | 55.9 | 1270.4 |  |  |  | 27 | 34
17 | J323 | J331 |  |  | 63 | 41.9 | 1312.3 |  |  |  | 77.1 | 21.3
18 | J235 | J222 |  |  | 63 | 11 | 1323.3 |  |  |  | 82
19 | J295 | J259 |  |  | 63 | 44.1 | 1367.4 |  |  |  | 66.4
20 | J259 | J291 |  |  | 63 | 33.4 | 1400.8 |  |  |  | 24.2
21 | J295 | J266 |  |  | 63 | 52.2 | 1453 |  |  |  | 122.6
22 | J266 | J259 |  |  | 63 | 63.1 | 1516.1 |  |  |  | 81
23 | J310 | J300 |  |  | 63 | 69.4 | 1585.5 |  |  |  | 33.8
24 | J223 | J289 |  |  | 63 | 122.3 | 1707.8 |  |  |  | 29.8
25 | J289 | J242 |  |  | 63 | 107.1 | 1814.9 |  |  |  | 89.3
26 | J242 | J180 | BRICK ROAD | 0.36 | 63 | 53.4 | 1868.3 |  |  |  | 18
27 | J180 | J148 |  |  | 63 | 63.4 | 1931.7 |  |  |  | 31
28 | J242 | J167 | BRICK ROAD | 0.36 | 63 | 64.8 | 1996.5 |  |  |  | 82.4
29 | J167 | J212 |  |  | 63 | 21 | 2017.5 |  |  |  | 4.3
30 | J212 | J262 |  |  | 63 | 15.7 | 2033.2 |  |  | TOTAL | 1689.7 | 501.3 | 34.6
31 | J212 | J252 |  |  | 63 | 12 | 2045.2
32 | J171 | J235 | INTERLOCKING | 0.36 | 63 | 39.8 | 2085
33 | J167 | J160 |  |  | 63 | 89.2 | 2174.2
34 | J160 | J141 |  |  | 63 | 40.4 | 2214.6
35 | J160 | J196 |  |  | 63 | 45.7 | 2260.3
36 | J356 | J271 |  |  | 63 | 158.9 | 2419.2
37 | J218 | J208 | INTERLOCKING | 0.36 | 63 | 33.2 | 2452.4
38 | J271 | J292 |  |  | 63 | 115.4 | 2567.8
39 | J271 | J265 |  |  | 63 | 100.5 | 2668.3
40 | J357 | J332 |  |  | 63 | 143.4 | 2811.7
41 | J332 | J308 |  |  | 63 | 156.9 | 2968.6
42 | J356 | J357 |  |  | 63 | 55.2 | 3023.8
43 | J208 | J171 | INTERLOCKING | 0.36 | 63 | 33.2 | 3057
44 | J314 | J268 |  |  | 63 | 41.3 | 3098.3
45 | J268 | J283 |  |  | 63 | 7.8 | 3106.1
46 | J116 | J281 |  |  | 63 | 229.8 | 3335.9
47 | J306 | J305 | BRICK ROAD | 0.36 | 63 | 287.5 | 3623.4
48 | J306 | J340 |  |  | 63 | 561.1 | 4184.5
49 | J340 | J335 | BRICK ROAD | 0.36 | 63 | 88.9 | 4273.4
50 | J340 | J311 | BRICK ROAD | 0.36 | 63 | 203 | 4476.4
51 | J305 | J319 |  |  | 63 | 60 | 4536.4
52 | J305 | J315 |  |  | 63 | 130.3 | 4666.7
53 | J315 | J333 |  |  | 63 | 87.6 | 4754.3
54 | J315 | J326 |  |  | 63 | 26.8 | 4781.1
55 | J326 | J317 |  |  | 63 | 25 | 4806.1
56 | J326 | J349 |  |  | 63 | 149 | 4955.1
57 | J349 | J366 |  |  | 63 | 38.5 | 4993.6
58 | J360 | J328 |  |  | 63 | 91 | 5084.6
59 | J318 | J321 |  |  | 63 | 41 | 5125.6
60 | J321 | J341 |  |  | 63 | 43.6 | 5169.2
61 | J318 | J328 |  |  | 63 | 48.3 | 5217.5
62 | J328 | J358 |  |  | 63 | 87 | 5304.5
63 | J348 | J345 |  |  | 63 | 105 | 5409.5
64 | J345 | J327 |  |  | 63 | 22 | 5431.5
65 | J345 | J342 |  |  | 63 | 41.5 | 5473
66 | J348 | J353 |  |  | 63 | 34.8 | 5507.8
67 | J348 | J353 |  |  | 63 | 212.3 | 5720.1
68 | J348 | J359 |  |  | 63 | 20.8 | 5740.9
69 | J359 | J367 |  |  | 63 | 119.9 | 5860.8
70 | J367 | J354 |  |  | 63 | 44.9 | 5905.7
71 | J354 | J334 |  |  | 63 | 96.3 | 6002
72 | J344 | J371 |  |  | 63 | 224.8 | 6226.8
73 | J371 | J369 |  |  | 63 | 11 | 6237.8
74 | J354 | J347 |  |  | 63 | 89.3 | 6327.1
75 | J347 | J370 | BRICK ROAD | 0.36 | 63 | 29.9 | 6357
76 | J370 | J365 | BRICK ROAD | 0.36 | 63 | 100.3 | 6457.3
77 | J76 | J96 |  |  | 63 | 78.3 | 6535.6
78 | J112 | J116 |  |  | 63 | 85.9 | 6621.5
79 | J145 | J107 |  |  | 63 | 29 | 6650.5
80 | J107 | J131 |  |  | 63 | 35.7 | 6686.2
81 | J116 | J142 |  |  | 63 | 41.5 | 6727.7
82 | J142 | J119 |  |  | 63 | 40.5 | 6768.2
83 | J40 | J32 |  |  | 63 | 20 | 6788.2
84 | J32 | J1 |  |  | 63 | 106 | 6894.2
85 | J32 | J27 |  |  | 63 | 144.3 | 7038.5
86 | J27 | J28 |  |  | 63 | 52.8 | 7091.3
87 | J27 | J41 |  |  | 63 | 12.5 | 7103.8
88 | J41 | J10 |  |  | 63 | 116.8 | 7220.6
89 | J27 | J62 |  |  | 63 | 11.5 | 7232.1
90 | J62 | J67 |  |  | 63 | 41.5 | 7273.6
91 | J67 | J46 |  |  | 63 | 23.4 | 7297
92 | J67 | J33 |  |  | 63 | 37 | 7334
93 | J33 | J11 |  |  | 63 | 22 | 7356
94 | J33 | J15 |  |  | 63 | 24 | 7380
95 | J15 | J45 |  |  | 63 | 30.4 | 7410.4
96 | J45 | J50 |  |  | 63 | 67.4 | 7477.8
97 | J50 | J51 |  |  | 63 | 34.1 | 7511.9
98 | J11 | J50 |  |  | 63 | 137.1 | 7649
99 | J45 | J52 |  |  | 63 | 77 | 7726
100 | J295 | J23 |  |  | 63 | 12 | 7738
101 | J23 | J37 |  |  | 63 | 21 | 7759
102 | J29 | J7 |  |  | 63 | 37 | 7796
103 | J7 | J24 |  |  | 63 | 59.8 | 7855.8
104 | J24 | J68 |  |  | 63 | 105 | 7960.8
105 | J25 | J21 |  |  | 63 | 32 | 7992.8
106 | J25 | J47 |  |  | 63 | 55 | 8047.8
107 | J37 | J36 |  |  | 63 | 60.2 | 8108
108 | J36 | J39 |  |  | 63 | 31.4 | 8139.4
109 | J39 | J43 |  |  | 63 | 25 | 8164.4
110 | J47 | J55 |  |  | 63 | 67 | 8231.4
111 | J55 | J16 |  |  | 63 | 17 | 8248.4
112 | J55 | J57 |  |  | 63 | 45 | 8293.4
113 | J57 | J38 |  |  | 63 | 194.2 | 8487.6
114 | J39 | J47 |  |  | 63 | 9.6 | 8497.2
115 | J38 | J8 |  |  | 63 | 62.4 | 8559.6
116 | J289 | J239 |  |  | 63 | 37.5 | 8597.1
117 | J239 | J294 |  |  | 63 | 11.3 | 8608.4
118 | J239 | J301 |  |  | 63 | 27.8 | 8636.2
119 | J301 | J264 |  |  | 63 | 26 | 8662.2
120 | J264 | J273 |  |  | 63 | 64.7 | 8726.9
121 | J273 | J308 |  |  | 63 | 66 | 8792.9
122 | J285 | J280 |  |  | 63 | 80.9 | 8873.8
123 | J280 | J286 |  |  | 63 | 36 | 8909.8
124 | J286 | J277 | BRICK ROAD | 0.36 | 63 | 27 | 8936.8
125 | J277 | J273 | BRICK ROAD | 0.36 | 63 | 77.1 | 9013.9
126 | J293 | J277 | BRICK ROAD | 0.36 | 63 | 82 | 9095.9
127 | J196 | J303 | INTERLOCKING | 0.36 | 63 | 120.4 | 9216.3
128 | J303 | J320 |  |  | 63 | 114.1 | 9330.4
129 | J303 | J285 | INTERLOCKING | 0.36 | 63 | 117.1 | 9447.5
130 | J299 | J293 | INTERLOCKING | 0.36 | 63 | 17.4 | 9464.9
131 | J299 | J298 |  |  | 63 | 84.4 | 9549.3
132 | J293 | J332 | INTERLOCKING | 0.36 | 63 | 44.9 | 9594.2
133 | J298 | J302 |  |  | 63 | 43.2 | 9637.4
134 | J302 | J288 |  |  | 63 | 62.9 | 9700.3
135 | J288 | J256 |  |  | 63 | 23 | 9723.3
136 | J288 | J314 |  |  | 63 | 167.6 | 9890.9
137 | J288 | J269 |  |  | 63 | 135.7 | 10026.6
138 | J356 | J271 |  |  | 63 | 158.9 | 10185.5
139 | J271 | J292 |  |  | 63 | 115.4 | 10300.9
140 | J271 | J265 |  |  | 63 | 100.5 | 10401.4
141 | J357 | J347 |  |  | 63 | 29.8 | 10431.2
142 | J332 | J308 |  |  | 63 | 156.9 | 10588.1
143 | J356 | J357 |  |  | 63 | 55 | 10643.1
144 | J314 | J268 |  |  | 63 | 41 | 10684.1
145 | J268 | J283 |  |  | 63 | 7.8 | 10691.9
146 | J283 | J233 |  |  | 63 | 58.5 | 10750.4
147 | J233 | J192 |  |  | 63 | 28.2 | 10778.6
148 | J283 | J198 |  |  | 63 | 149.8 | 10928.4
149 | J198 | J215 |  |  | 63 | 69 | 10997.4
150 | J215 | J196 |  |  | 63 | 16.3 | 11013.7
151 | J154 | J103 |  |  | 63 | 65 | 11078.7
152 | J103 | J150 |  |  | 63 | 128.4 | 11207.1
153 | J150 | 279 |  |  | 63 | 181.7 | 11388.8
154 | J150 | 279 | B.T ROAD | 0.36 | 63 | 6 | 11394.8
155 | J279 | J224 |  |  | 63 | 198.9 | 11593.7
156 | J279 | J274 |  |  | 63 | 305.7 | 11899.4
157 | J274 | J211 |  |  | 63 | 133.4 | 12032.8
158 | J274 | J263 |  |  | 63 | 195.1 | 12227.9
159 | J263 | J246 |  |  | 63 | 28.6 | 12256.5
160 | J246 | J227 |  |  | 63 | 145.1 | 12401.6
161 | J246 | J227 | B.T ROAD | 0.36 | 63 | 4 | 12405.6
162 | J150 | J110 |  |  | 63 | 251.7 | 12657.3
163 | J110 | J82 |  |  | 63 | 101.6 | 12758.9
164 | J82 | J103 |  |  | 63 | 106.6 | 12865.5
165 | J95 | J93 |  |  | 63 | 8.2 | 12873.7
166 | J93 | J108 |  |  | 63 | 131 | 13004.7
167 | J98 | J133 |  |  | 63 | 93 | 13097.7
168 | J58 | J90 |  |  | 63 | 452.4 | 13550.1
169 | J90 | J79 |  |  | 63 | 72.3 | 13622.4
170 | J90 | J102 |  |  | 63 | 108.5 | 13730.9
171 | J121 | J108 |  |  | 63 | 56 | 13786.9
172 | J121 | J78 |  |  | 63 | 119.3 | 13906.2
173 | J78 | J77 |  |  | 63 | 64.4 | 13970.6
174 | J78 | J88 |  |  | 63 | 91.3 | 14061.9
175 | J88 | J92 |  |  | 63 | 53.3 | 14115.2
176 | J92 | J100 |  |  | 63 | 60.9 | 14176.1
177 | J92 | 87 |  |  | 63 | 47 | 14223.1
178 | J87 | J106 |  |  | 63 | 88 | 14311.1
179 | J87 | J93 |  |  | 63 | 18 | 14329.1
180 | J88 | J94 |  |  | 63 | 98 | 14427.1
181 | J94 | J144 |  |  | 63 | 64 | 14491.1
182 | J82 | J108 |  |  | 63 | 24.5 | 14515.6
183 | J144 | J140 |  |  | 63 | 70.6 | 14586.2
184 | J140 | J152 |  |  | 63 | 111.4 | 14697.6
185 | J88 | J140 |  |  | 63 | 117 | 14814.6
186 | J144 | J110 |  |  | 63 | 31.3 | 14845.9
187 | j81 | j146 |  |  | 63 | 80.5 | 14926.4
188 | j101 | j146 |  |  | 63 | 141.9 | 15068.3
189 | j146 | j200 |  |  | 63 | 18 | 15086.3
190 | j200 | j187 |  |  | 63 | 25.7 | 15112
191 | j187 | j91 |  |  | 63 | 10 | 15122
192 | j187 | j195 |  |  | 63 | 10 | 15132
193 | j195 | j164 |  |  | 63 | 46.7 | 15178.7
194 | j164 | j177 |  |  | 63 | 13.5 | 15192.2
195 | j164 | j158 |  |  | 63 | 9.5 | 15201.7
196 | j147 | j161 |  |  | 63 | 34.4 | 15236.1
197 | j161 | j166 | brick road | 0.36 | 63 | 66.4 | 15302.5
198 | j166 | j151 |  |  | 63 | 46.7 | 15349.2
199 | j166 | j174 | brick road | 0.36 | 63 | 24.2 | 15373.4
200 | j174 | j135 |  |  | 63 | 20 | 15393.4
201 | j174 | j221 | brick road | 0.36 | 63 | 122.6 | 15516
202 | j135 | j139 |  |  | 63 | 68 | 15584
203 | j179 | j169 |  |  | 63 | 273.3 | 15857.3
204 | j138 | j124 |  |  | 63 | 54.7 | 15912
205 | j124 | j136 |  |  | 63 | 80 | 15992
206 | j124 | j127 |  |  | 63 | 112.3 | 16104.3
207 | j127 | j118 |  |  | 63 | 39.6 | 16143.9
208 | j118 | j111 |  |  | 63 | 41.5 | 16185.4
209 | j127 | j117 |  |  | 63 | 104.2 | 16289.6 |  |  | 401.2
210 | j117 | j97 |  |  | 63 | 40.2 | 16329.8 |  |  | 20443
211 | j117 | j134 |  |  | 63 | 42 | 16371.8
212 | j179 | j137 |  |  | 63 | 80.7 | 16452.5 |  |  | 26021
213 | j137 | j169 |  |  | 63 | 133.6 | 16586.1
214 | j137 | j128 |  |  | 63 | 172.3 | 16758.4
215 | j128 | j184 |  |  | 63 | 30.6 | 16789
216 | j128 | j182 |  |  | 63 | 40.6 | 16829.6
217 | j168 | j225 |  |  | 63 | 33.2 | 16862.8
218 | j225 | j190 |  |  | 63 | 23.2 | 16886
219 | j190 | j257 |  |  | 63 | 16.9 | 16902.9
220 | j199 | j129 |  |  | 63 | 91.4 | 16994.3
221 | j129 | j200 |  |  | 63 | 46.1 | 17040.4
222 | j227 | j239 |  |  | 63 | 228.9 | 17269.3
223 | j238 | j201 |  |  | 63 | 59.4 | 17328.7
224 | j238 | j247 |  |  | 63 | 251 | 17579.7
225 | j247 | j257 | b.t road | 0.36 | 63 | 5 | 17584.7
226 | j247 | j257 |  |  | 63 | 104.1 | 17688.8
227 | j257 | j272 |  |  | 63 | 6 | 17694.8
228 | j257 | j272 |  |  | 63 | 33 | 17727.8
229 | j272 | j237 |  |  | 63 | 43.4 | 17771.2
230 | j237 | j236 |  |  | 63 | 29.3 | 17800.5
231 | j236 | j216 |  |  | 63 | 13.5 | 17814
232 | j237 | j172 |  |  | 63 | 80 | 17894
233 | j216 | j172 |  |  | 63 | 47.6 | 17941.6
234 | j216 | j255 |  |  | 63 | 51.6 | 17993.2
235 | j255 | j244 |  |  | 63 | 24.9 | 18018.1
236 | j244 | j245 |  |  | 63 | 29.1 | 18047.2
237 | j250 | j236 |  |  | 63 | 62.9 | 18110.1
238 | j272 | j256 |  |  | 63 | 38.3 | 18148.4
239 | j256 | j250 |  |  | 63 | 41 | 18189.4
240 | j250 | j181 |  |  | 63 | 57.9 | 18247.3
241 | j181 | j202 |  |  | 63 | 109 | 18356.3
242 | j181 | j153 |  |  | 63 | 44 | 18400.3
243 | j153 | j162 |  |  | 63 | 86.4 | 18486.7
244 | j247 | j253 |  |  | 63 | 37.1 | 18523.8
245 | j253 | j248 |  |  | 63 | 94.7 | 18618.5
246 | j253 | j248 | INTERLOCKING | 0.36 | 63 | 40 | 18658.5
247 | j248 | j270 | INTERLOCKING | 0.36 | 63 | 34 | 18692.5
248 | J270 | J278 | INTERLOCKING | 0.36 | 63 | 21.3 | 18713.8
249 | J338 | J307 |  |  | 63 | 22.8 | 18736.6
250 | J307 | J276 |  |  | 63 | 29.4 | 18766
251 | J307 | J304 |  |  | 63 | 39.9 | 18805.9
252 | J248 | J226 | BRICK ROAD | 0.36 | 63 | 81 | 18886.9
253 | J226 | J203 |  |  | 63 | 45.8 | 18932.7
254 | J203 | J287 |  |  | 63 | 125.3 | 19058
255 | J203 | J189 |  |  | 63 | 22 | 19080
256 | J207 | J230 |  |  | 63 | 16 | 19096
257 | J287 | J322 |  |  | 63 | 52.6 | 19148.6
258 | J322 | J304 |  |  | 63 | 18.9 | 19167.5
259 | J304 | J234 |  |  | 63 | 129.2 | 19296.7
260 | J234 | J228 |  |  | 63 | 34.6 | 19331.3
261 | J321 | J341 |  |  | 63 | 87.3 | 19418.6
262 | J365 | J362 |  |  | 63 | 77.8 | 19496.4
263 | J182 |  |  |  | 63 | 56.6 | 19553
264 | J33 | J11 | BRICK ROAD | 0.36 | 63 | 33.8 | 19586.8
265 | J42 | J52 |  |  | 63 | 95.6 | 19682.4
266 | J37 | J36 |  |  | 63 | 10 | 19692.4
267 | J76 | J72 |  |  | 63 | 18.7 | 19711.1
268 | J326 | J349 |  |  | 63 | 56.6 | 19767.7
269 | J76 | J72 |  |  | 63 | 25 | 19792.7
270 | J318 | J328 |  |  | 63 | 86.3 | 19879
271 | J354 | J347 | BRICK ROAD | 0.36 | 63 | 29.8 | 19908.8
272 | J370 | J311 |  |  | 63 | 278.4 | 20187.2
273 | J100 | J92 |  |  | 63 | 47.3 | 20234.5
274 | J293 | J332 |  |  | 63 | 27.5 | 20262
275 | J342 | J343 |  |  | 63 | 121.1 | 20383.1
276 | J90 | J79 |  |  | 63 | 29.6 | 20412.7
277 | J347 | J371 | BRICK ROAD | 0.36 | 63 | 89.3 | 20502
278 | J74 | J98 |  |  | 63 | 19.1 | 20521.1
279 | J281 | J297a |  |  | 63 | 307.5 | 20828.6 | EXTRA LINE |  |  |  | 325.7
280 | J281 | J297 |  |  | 63 | 147.6 | 20976.2
281 | J297 | J290 |  |  | 63 | 51.5 | 21027.7
282 | J297 | J292 | B.T ROAD | 0.36 | 63 | 7 | 21034.7
283 | j227 | j149 |  |  | 75 | 132.3 | 21167
284 | J297 | J292 |  |  | 75 | 67.6 | 21234.6
285 | J22 | J52 |  |  | 75 | 111.4 | 21346
286 | J319 | J323 |  |  | 75 | 28.6 | 21374.6
287 | J323 | J295 |  |  | 75 | 135.9 | 21510.5
288 | J319 | J339 |  |  | 75 | 91 | 21601.5
289 | J339 | J343 | BRICK ROAD | 0.37 | 75 | 18 | 21619.5
290 | J343 | J333 | BRICK ROAD | 0.37 | 75 | 31 | 21650.5
291 | J333 | J358 | BRICK ROAD | 0.37 | 75 | 82.4 | 21732.9
292 | J358 | J366 |  |  | 75 | 43.6 | 21776.5
293 | J366 | J348 |  |  | 75 | 105.8 | 21882.3 |  |  | 551.6
294 | J58 | J38 |  |  | 75 | 151.2 | 22033.5
295 | J38 | J95 |  |  | 75 | 551.6 | 22585.1
296 | J52 | J69 |  |  | 75 | 135.8 | 22720.9
297 | J133 | J121 |  |  | 75 | 45.7 | 22766.6
298 | J196 | J154 |  |  | 90 | 269.1 | 23035.7
299 | j179 | j199 |  |  | 90 | 60.6 | 23096.3
300 | j199 | j221 |  |  | 90 | 226 | 23322.3
301 | j221 | j227 | b.t road | 0.39 | 90 | 6.2 | 23328.5
302 | j221 | j227 |  |  | 90 | 216.1 | 23544.6
303 | j101 | j179 |  |  | 90 | 35.5 | 23580.1 |  | j227 | j221 | kc road | HDPE |  | 190
304 | j101 | j179 | brick road | 0.39 | 90 | 4.3 | 23584.4 |  | j221 | j179 | kc road | HDPE |  | 280
305 | J368 | J266 |  |  | 90 | 188 | 23772.4 |  | j112 | j145 | kc road | HDPE |  | 45
306 | J310 | J223 |  |  | 90 | 154.6 | 23927 |  | j145 | j223 | kc road | HDPE |  | 90
307 | J223 | J145 |  |  | 90 | 95.6 | 24022.6 |  | j223 | j310 | kc road | HDPE |  | 151
308 | J99 | J104 |  |  | 90 | 25 | 24047.6 |  | j368 | j266 | kc road | HDPE |  | 174
309 | J104 | J154 |  |  | 90 | 170 | 24217.6 |  | j99 | j104 |  | HDPE |  | 28
310 | J112 | J145 |  |  | 90 | 25 | 24242.6 |  | j104 | j154 |  | HDPE |  | 169
311 | J368 | J310 |  |  | 90 | 28.7 | 24271.3
312 | J72 | J81 |  |  | 110 | 134.4 | 24405.7 |  | j196 | j215 |  | HDPE |  | 21
313 | J81 | J101 |  |  | 110 | 50.4 | 24456.1 |  | j215 | j198 |  | HDPE |  | 69
314 | J70 | J68 |  |  | 110 | 120.1 | 24576.2 |  | j198 | j283 |  | HDPE |  | 152
315 | J68 | J58 |  |  | 110 | 32.9 | 24609.1 |  | J154 | J196 |  | HDPE |  | 246
316 | J199 | J123 |  |  | 110 | 186.9 | 24796 |  | j23 | j35 | KC ROAD | HDPE |  | 60
317 | J123 | J148 |  |  | 110 | 79.8 | 24875.8
318 | J148 | J112 |  |  | 110 | 160.1 | 25035.9
319 | J35 | J29 |  |  | 110 | 56.7 | 25092.6
320 | J133 | J93 |  |  | 125 | 128.9 | 25221.5
321 | J72 | J74 |  |  | 125 | 65.7 | 25287.2
322 | J74 | J98 |  |  | 125 | 73.2 | 25360.4
323 | J95 | J99 |  |  | 125 | 64.9 | 25425.3
324 | J35 | J14 |  |  | 140 | 95 | 25520.3
325 | J14 | 22 |  |  | 140 | 58.6 | 25578.9
326 | J69 | J76 |  |  | 140 | 415 | 25993.9
327 | J76 | J72 |  |  | 140 | 155 | 26148.9 |  |  | 119
328 | J69 | J70 | B.T ROAD | 0.44 | 140 | 6.4 | 26155.3
329 | J70 | J35 |  |  | 140 | 110 | 26265.3
330 | j14 | OHT |  |  | 160 | 26 | 26291.3
331 | j281 | j368 |  |  | 63 | 250 | 26541.3
63 | 75 | 90 | 110 | 125 | 140 | 160 | [6 empty] | 18921
21034.7 | 1731.9 | 1504.7 | 821.3 | 332.7 | 840 | 0 | 26265.3 | [5 empty] | 1820
23628 | 1864 | 1675 | 939 | 396 | 845 | 26 | 29373 | [5 empty] | 1615
877
396
|  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | [6 empty] | 838
|  |  | 63 | 23628 | 14700 | 21034.7
|  |  | 75 | 1864 | 1550 | 1731.9
|  |  | 90 | 1675 | 2000 | 1504.7
|  |  | 110 | 939 | 900 | 821.3
|  |  | 125 | 396 | 396 | 332.7
|  |  | 140 | 845 | 840 | 840
|  |  | 160 | 26 | 0

## MANGRAURA
MANGRAURA
Sl.No | Start Node | End Node | Type of Road | WIDTH OF DISMATLING | Dia of pipe | Pipe Length (M) |  | CUMMULATIVE
1 | J191 | J180 |  |  | 63 | 56.1 |  | 56.1
2 | J191 | J180 | C .C ROAD |  | 63 | 3.5 |  | 59.6
3 | J180 | J201 |  |  | 63 | 34.6 |  | 94.2
4 | J180 | J199 |  |  | 63 | 136 |  | 230.2
5 | J199 | J205 |  |  | 63 | 88.6 |  | 318.8
6 | J205 | J213 |  |  | 63 | 149 |  | 467.8
7 | J205 | J184 |  |  | 63 | 203.3 |  | 671.1 |  | 270
8 | J199 | J131 |  |  | 63 | 607 |  | 1278.1
9 | J191 | J198 |  |  | 63 | 27 |  | 1305.1
10 | J198 | J202 |  |  | 63 | 28 |  | 1333.1
11 | J202 | J182 |  |  | 63 | 63 |  | 1396.1
12 | J182 | J145 |  |  | 63 | 27 |  | 1423.1
13 | J145 | J165 |  |  | 63 | 28 |  | 1451.1
14 | J165 | J155 |  |  | 63 | 18 |  | 1469.1
15 | J155 | J156 |  |  | 63 | 46.2 |  | 1515.3
16 | J156 | J142 |  |  | 63 | 28 |  | 1543.3
17 | J142 | J106 |  |  | 63 | 53.6 |  | 1596.9
18 | J106 | J173 |  |  | 63 | 257.3 |  | 1854.2
19 | J143 | J121 |  |  | 63 | 17.5 |  | 1871.7
20 | J121 | J120 |  |  | 63 | 48.1 |  | 1919.8
21 | J120 | J123 |  |  | 63 | 23 |  | 1942.8
22 | J120 | J114 |  |  | 63 | 15 |  | 1957.8
23 | J114 | J116 |  |  | 63 | 19.3 |  | 1977.1
24 | J123 | J154 |  |  | 63 | 33.8 |  | 2010.9
25 | J143 | J89 |  |  | 63 | 110.9 |  | 2121.8
26 | J89 | J195 |  |  | 63 | 74 |  | 2195.8
27 | J121 | J129 |  |  | 63 | 26.8 |  | 2222.6
28 | J129 | J107 |  |  | 63 | 65.7 |  | 2288.3
29 | J123 | J104 |  |  | 63 | 40.3 |  | 2328.6
30 | J104 | J112 |  |  | 63 | 36.4 |  | 2365
31 | J112 | J135 |  |  | 63 | 98.9 |  | 2463.9
32 | J99 | J93 |  |  | 63 | 16 |  | 2479.9
33 | J93 | J100 |  |  | 63 | 12.5 |  | 2492.4
34 | J100 | J107 |  |  | 63 | 67.3 |  | 2559.7
35 | J107 | J109 |  |  | 63 | 40.1 |  | 2599.8
36 | J109 | J125 |  |  | 63 | 8.2 |  | 2608
37 | J125 | J84 |  |  | 63 | 32.8 |  | 2640.8
38 | J84 | J5 |  |  | 63 | 27.2 |  | 2668
39 | J5 | J16 |  |  | 63 | 19.5 |  | 2687.5
40 | J5 | J1 |  |  | 63 | 51 |  | 2738.5
41 | J195 | J152 |  |  | 63 |  |  | 2738.5
42 | J105 | J97 |  |  | 63 | 126.9 |  | 2865.4
43 | J97 | J66 |  |  | 63 | 214.7 |  | 3080.1
44 | J66 | J60 |  |  | 63 | 76 |  | 3156.1
45 | J60 | J64 |  |  | 63 | 5 |  | 3161.1
46 | J60 | J57 |  |  | 63 | 150.2 |  | 3311.3
47 | J64 | J57 |  |  | 63 | 35.2 |  | 3346.5
48 | J57 | J53 |  |  | 63 | 192 |  | 3538.5
49 | J53 | J48 |  |  | 63 | 20 |  | 3558.5
50 | J48 | J25 |  |  | 63 | 32.6 |  | 3591.1
51 | J132 | J117 |  |  | 63 | 64 |  | 3655.1
52 | J117 | J43 |  |  | 63 | 106.9 |  | 3762
53 | J43 | J85 |  |  | 63 | 140 |  | 3902
54 | J85 | J105 |  |  | 63 | 80.7 |  | 3982.7
55 | J105 | J124 |  |  | 63 | 80 |  | 4062.7
56 | J124 | J108 |  |  | 63 | 44.9 |  | 4107.6
57 | J108 | J128 |  |  | 63 | 172.2 |  | 4279.8
58 | J108 | J21 |  |  | 63 | 52 |  | 4331.8
59 | J133 | J136 |  |  | 63 | 5.8 |  | 4337.6
60 | J136 | J161 |  |  | 63 | 27.2 |  | 4364.8
61 | J161 | J175 |  |  | 63 | 16.4 |  | 4381.2
62 | J161 | J134 |  |  | 63 | 25.8 |  | 4407
63 | J134 | J157 |  |  | 63 | 23.7 |  | 4430.7
64 | J142 | J134 |  |  | 63 | 31.4 |  | 4462.1
65 | J170 | J146 |  |  | 63 | 31.6 |  | 4493.7
66 | J146 | J182 |  |  | 63 | 20.4 |  | 4514.1
67 | J170 | J183 |  |  | 63 | 68 |  | 4582.1
68 | J183 | J193 |  |  | 63 | 8.8 |  | 4590.9
69 | J193(1) | J193(1) |  |  | 63 | 20.9 |  | 4611.8
70 | J183 | J190 |  |  | 63 | 18 |  | 4629.8
71 | J190 | J160 |  |  | 63 | 24 |  | 4653.8
72 | J172 | J160 |  |  | 63 | 20.8 |  | 4674.6
73 | J172 | J146 |  |  | 63 | 16.4 |  | 4691
74 | J172 | J178 |  |  | 63 | 14.8 |  | 4705.8
75 | J178 | JJ168 |  |  | 63 | 16.6 |  | 4722.4
76 | J178 | J202 |  |  | 63 | 52.5 |  | 4774.9
77 | J160 | J115 |  |  | 63 | 91.7 |  | 4866.6
78 | J172 | J115 |  |  | 63 | 87.1 |  | 4953.7
79 | J115 | J150 |  |  | 63 | 4.2 |  | 4957.9
80 | J208 | J150(A) |  |  | 63 | 41.4 |  | 4999.3
81 | J150(A) | J150(A) |  |  | 63 | 9.4 |  | 5008.7
82 | J150(A) | J137 |  |  | 63 | 70.7 |  | 5079.4
83 | J150 | J206 |  |  | 63 | 42 |  | 5121.4
84 | J165 | J164 |  |  | 63 |  |  | 5121.4
85 | J164 | J159 |  |  | 63 | 17 |  | 5138.4
86 | J164 | J153 |  |  | 63 | 11 |  | 5149.4
87 | J153 | J218 |  |  | 63 | 49.7 |  | 5199.1
88 | J159 | J156 |  |  | 63 | 38.4 |  | 5237.5
89 | J191 | J137 |  |  | 63 | 47.6 |  | 5285.1
90 | J137 | J169 |  |  | 63 | 14 |  | 5299.1
91 | J195 | J152 |  |  | 63 | 114.8 |  | 5413.9
92 | J152 | J139 |  |  | 63 | 63.4 |  | 5477.3
93 | J139 | J126 |  |  | 63 | 38 |  | 5515.3
94 | J42 | J132 |  |  | 63 |  |  | 5515.3
95 | J132 | J82 | BRICK ROAD | 0.39 | 63 | 427.6 |  | 5942.9
96 | J82 | J80 | BRICK ROAD | 0.39 | 63 | 62 |  | 6004.9
97 | J82 | J56 | BRICK ROAD | 0.39 | 63 | 123.2 |  | 6128.1
98 | j14 | j9 |  |  | 140 | 117 |  | 6245.1
99 | j14 | j19 |  |  | 125 | 264 |  | 6509.1
100 | j19 | j52 |  |  | 63 | 305.2 |  | 6814.3
101 | j60 | j27 |  |  | 63 | 64.5 |  | 6878.8
102 | j52 | j68 |  |  | 63 | 111.8 |  | 6990.6
103 | j52 | j7 |  |  | 63 | 117.8 |  | 7108.4
104 | j68 | j72 |  |  | 63 | 233 |  | 7341.4
105 | j19 | j15 |  |  | 110 | 255 |  | 7596.4
106 | j15 | j31 |  |  | 63 | 27.4 |  | 7623.8
107 | j15 | j28 |  |  | 110 | 51.6 |  | 7675.4
108 | j28 | j45 |  |  | 63 | 61.3 |  | 7736.7
109 | j45 | j37 |  |  | 63 | 22.2 |  | 7758.9
110 | j37 | j39 |  |  | 63 | 13.6 |  | 7772.5
111 | j20 | j36 |  |  | 110 | 18 |  | 7790.5
112 | j36 | j60 |  |  | 110 | 59.8 |  | 7850.3
113 | j60 | j64 |  |  | 63 | 153.9 |  | 8004.2
114 | j64 | j40 |  |  | 63 | 65.4 |  | 8069.6
115 | j64 | j57 |  |  | 63 | 33 |  | 8102.6
116 | j57 | j71 |  |  | 63 | 91 |  | 8193.6
117 | j57 | j53 |  |  | 63 | 130 |  | 8323.6
118 | j53 | j48 |  |  | 63 | 25 |  | 8348.6
119 | j48 | j25 |  |  | 63 | 29.9 |  | 8378.5
120 | j25 | j42 |  |  | 63 | 21.1 |  | 8399.6
121 | j9 | j192 |  |  | 90 | 303 |  | 8702.6
122 | j192 | j59 |  |  | 63 | 144.2 |  | 8846.8
123 | j192 | j100 |  |  | 63 | 43 |  | 8889.8
124 | j188 | j195 |  |  | 63 | 18.7 |  | 8908.5
125 | j192 | j118 |  |  | 90 | 74 |  | 8982.5
126 | j110 | j122 |  |  | 90 | 30.9 |  | 9013.4
127 | j122 | j203 |  |  | 90 | 240.3 |  | 9253.7
128 | J132 | J82 |  |  | 63 | 435.8 |  | 9689.5
129 | J82 | J56 |  |  | 63 | 128.4 |  | 9817.9 | 16317.3
130 | J56 | J47 |  |  | 63 | 55.4 |  | 9873.3 | 14954
131 | J82 | J80 |  |  | 63 | 68.4 |  | 9941.7 | 1363.3
132 | J80 | J65 |  |  | 63 | 30 |  | 9971.7
133 | J80 | J81 |  |  | 63 | 123.5 |  | 10095.2
134 | J65 | J50 |  |  | 63 | 30 |  | 10125.2
135 | J50 | J20 |  |  | 63 | 73.2 |  | 10198.4
136 | J200 | J208 |  |  | 63 | 54.5 |  | 10252.9
137 | J208 | J206 |  |  | 63 | 24.8 |  | 10277.7
138 | J206 | J211 |  |  | 63 | 18.2 |  | 10295.9
139 | J211 | J207 |  |  | 63 | 68 |  | 10363.9
140 | J211 | J204 |  |  | 63 | 337.8 |  | 10701.7
141 | J207 | J215 |  |  | 63 | 43.8 |  | 10745.5
142 | J215 | J189 |  |  | 63 | 47 |  | 10792.5
143 | J189 | J147 |  |  | 63 | 41 |  | 10833.5
144 | J189 | J141 |  |  | 63 | 55 |  | 10888.5
145 | J141 | J158 |  |  | 63 | 8 |  | 10896.5
146 | J158 | J177 |  |  | 63 | 18.3 |  | 10914.8
147 | J158 | J209 |  |  | 63 | 56.6 |  | 10971.4
148 | J215 | J209 |  |  | 63 | 82.9 |  | 11054.3
149 | J209 | J210 |  |  | 63 | 42.6 |  | 11096.9
150 | J209 | J185 |  |  | 63 | 142 |  | 11238.9
151 | J42 | J94 |  |  | 63 | 114 |  | 11352.9
152 | J94 | J71 |  |  | 63 | 33.6 |  | 11386.5
153 | J71 | J73 |  |  | 63 | 14.7 |  | 11401.2
154 | J73 | J33 |  |  | 63 | 44.1 |  | 11445.3
155 | J33 | J85 |  |  | 63 | 200 |  | 11645.3
156 | J85 | J105 |  |  | 63 | 81.6 |  | 11726.9
157 | J85 | J43 |  |  | 63 | 138.5 |  | 11865.4
158 | J43 | J91 |  |  | 63 | 52 |  | 11917.4
159 | J91 | J117 |  |  | 63 | 56 |  | 11973.4
160 | J117 | J132 |  |  | 63 | 112 |  | 12085.4
161 | J105 | J124 |  |  | 63 | 74.7 |  | 12160.1
162 | J124 | J108 |  |  | 63 | 50.9 |  | 12211
163 | J108 | J128 |  |  | 63 | 175 |  | 12386
164 | J128 | J21 |  |  | 63 | 60.5 |  | 12446.5
165 | J128 | J92 |  |  | 63 | 233.4 |  | 12679.9
166 | J108 | J148 |  |  | 63 | 82.6 |  | 12762.5
167 | J148 | J26 |  |  | 63 | 394.2 |  | 13156.7
168 | J60 | J41 |  |  | 63 | 63.9 |  | 13220.6
169 | J41 | J69 |  |  | 63 | 144.4 |  | 13365
170 | J69 | J78 |  |  | 63 | 58.7 |  | 13423.7
171 | J69 | J22 |  |  | 63 | 35.2 |  | 13458.9
172 | J22 | 12 |  |  | 63 | 9.2 |  | 13468.1
173 | J22 | J17 |  |  | 63 | 7.9 |  | 13476
174 | J41 | J74 |  |  | 63 | 193.4 |  | 13669.4
175 | J74 | J87 |  |  | 63 | 183.9 |  | 13853.3
176 | J87 | J86 |  |  | 63 | 55 |  | 13908.3
177 | J86 | J32 |  |  | 63 | 63.5 |  | 13971.8
178 | J96 | J95 |  |  | 63 | 82.2 |  | 14054
179 | J95 | J98 |  |  | 63 | 117.7 |  | 14171.7
180 | J98 | J102 |  |  | 63 | 42 |  | 14213.7
181 | J74 | J51 |  |  | 63 | 118 |  | 14331.7
182 | J60 | J66 |  |  | 63 | 73.2 |  | 14404.9
183 | J66 | J62 |  |  | 63 | 124.5 |  | 14529.4
184 | J62 | J97 |  |  | 63 | 97.6 |  | 14627
185 | J97 | J105 |  |  | 63 | 130 |  | 14757
186 | J14 | OHT |  |  | 140 | 24 |  | 14781
| 63 | 75 | 90 | 110 | 125 | 140
| 13343.4 | 0 | 648.2 | 384.4 | 264 | 141 |  | 14781
| 16542 | 72 | 716 | 781 | 258 | 139 | 139 | 18508
[11 empty] | J66 | J51 | 63 | 299.3
[11 empty] | J51 | J88 | 63 | 31
| Block |  | Mangraura | [7 empty] | JJ88 | J8 | 63 | 124.9
| GP |  | mangraura | [7 empty] | J8 | J18 | 63 | 40
| Agency Name/ Work Order No |  | Unity Infra | [5 empty] | 14926 |  | J8 | J35 | 63 | 53.2
| 63MM | [7 empty] | 10 |  | J97 | J63 | 63 | 83.8
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks |  |  |  |  | J63 | J35 | 63 | 187.6
| 1 | 2023-01-23 | 4200 |  |  | 2972 |  |  |  |  | J63 | J96 | 63 | 54.6
| 2 | 2023-02-07 | 900 |  |  | 2975 |  |  |  |  | J35 | J96 | 63 | 259.9
| 3 | 2023-02-12 | 4200 |  |  | 2978 |  |  |  |  | J96 | J148 | 63 | 151.1
| 4 | 2023-03-14 | 300 |  |  | 2982 |  |  |  |  | J51 | J8 | 63 | 259.9
| 5 | 2023-03-15 | 1200 |  |  | 2983
| 6 | 2023-03-23 | 600 |  |  | 2987
| 7 | 2023-03-29 | 600 |  |  | 2992
| 8 | 2023-04-03 | 600
| 9 | 2023-04-09 | 600 |  |  | 2997
|  | TOTAL | 13200
75MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
1
2
3
|  | TOTAL | 0
90MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-02-07 | 300 |  |  | 2975
| 2 | 2023-03-21 | 200 |  |  | 2986
| 3 | 2023-03-24 | 200 |  |  | 2989
|  | TOTAL | 700
110MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-02-07 | 600 |  |  | 2975
| 2 | 2023-02-12 | 100 |  |  | 2978
| 3 | 2023-04-06 | 100 |  |  | 2996
4
5
6
7
8
|  | TOTAL | 800
125MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-03-15 | 264 |  |  | 2983
|  | TOTAL | 264
140MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-03-15 | 132 |  |  | 2983
|  | TOTAL | 132

## MALAAK
Block |  | Mangraura
GP |  | MALAAK
Total Length (M) |  | 20705
FHTC (No's)
Agency Name |  | SHUKLA CVONSTRUCTION
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
1 | 2023-05-28 | J130 | J107 |  |  |  |  | 320 |  |  |  |  | 320
2 | 2023-05-28 | J153 | J126 |  |  |  |  | 99 |  |  |  |  | 419
3 | 2023-05-28 | J126 | J136 |  |  |  |  | 218 |  |  |  |  | 637
4 | 2023-05-28 | J136 | J192 |  |  | 150 | [6 empty] | 787
5 | 2023-05-29 | j130 | j124 | [5 empty] | 325 |  |  |  | 1112
6 | 2023-05-31 | j168 | j181 |  |  | 80 | [6 empty] | 1192
7 | 2023-05-31 | j181 | j132 |  |  | 135 | [6 empty] | 1327
8 | 2023-05-31 | j164 | j112 |  |  | 60 | [6 empty] | 1387
9 | 2023-05-31 | j164 | j168 |  |  | 107 | [6 empty] | 1494
10 | 2023-06-01 | j64 | j177 |  |  | 200 | [6 empty] | 1694
11 | 2023-06-01 | j106 | j138 |  |  | 26 | [6 empty] | 1720
12 | 2023-06-01 | j99 | j88 |  |  | 95 | [6 empty] | 1815
13 | 2023-06-04 | j99 | j208 |  |  | 78 | [6 empty] | 1893
14 | 2023-06-04 | j99 | j152 |  |  | 100 | [6 empty] | 1993
15 | 2023-06-04 | j152 | j167 |  |  | 43 | [6 empty] | 2036
16 | 2023-06-04 | j152 | j106 |  |  | 106 | [6 empty] | 2142
17 | 2023-06-04 | jj98 | j40 |  |  | 62 | [6 empty] | 2204
18 | 2023-06-04 | j187 | j98 |  |  | 68 | [6 empty] | 2272
19 | 2023-06-04 | j40 | j74 |  |  | 61 | [6 empty] | 2333
20 | 2023-06-04 | j40 | j190 |  |  | 60 | [6 empty] | 2393
21 | 2023-06-04 | j190 | j74 |  |  | 110 | [6 empty] | 2503
22 | 2023-06-05 | J167A | J167A |  |  | 70 | [6 empty] | 2573
23 | 2023-06-05 | J192 | J200 |  |  | 85 | [6 empty] | 2658
24 | 2023-06-05 | J200 | J99 |  |  | 78 | [6 empty] | 2736
25 | 2023-06-05 | J187 | J179 |  |  | 70 | [6 empty] | 2806
26 | 2023-06-05 | J69 | J98 |  |  | 24 | [6 empty] | 2830
27 | 2023-06-06 | j168 | j164 |  |  | 107 | [6 empty] | 2937
28 | 2023-06-06 | j136 | j159 |  |  | 135 | [6 empty] | 3072
29 | 2023-06-09 | j20 | j2 |  |  | 114 | [6 empty] | 3186
30 | 2023-06-09 | j2 | j24 |  |  | 163 | [6 empty] | 3349
31 | 2023-06-09 | j2 | j1 |  |  | 55 | [6 empty] | 3404
32 | 2023-06-10 | j20 | j29 |  |  | 104 | [6 empty] | 3508
33 | 2023-06-10 | j2 | j22 |  |  | 68 | [6 empty] | 3576
34 | 2023-06-10 | j29 | j53 |  |  | 77 | [6 empty] | 3653
35 | 2023-06-10 | j40 | j19 |  |  | 204 | [6 empty] | 3857
36 | 2023-06-11 | j101 | j28 |  |  | 95 | [6 empty] | 3952
37 | 2023-06-11 | j29 | j20 |  |  | 104 | [6 empty] | 4056
38 | 2023-06-12 | j130 | j37 |  |  |  | 240 | [5 empty] | 4296
39 | 2023-06-12 | j120 | j27 |  |  | 270 | [6 empty] | 4566
40 | 2023-06-13 | j37 | j19 |  |  | 103 | [6 empty] | 4669
41 | 2023-06-13 | j19 | j31 |  |  | 45 | [6 empty] | 4714
42 | 2023-06-13 | j37 | j70 |  |  | 106 | [6 empty] | 4820
43 | 2023-06-13 | j71 | j123 |  |  | 66 | [6 empty] | 4886
44 | 2023-06-13 | j101 | j60 |  |  | 80 | [6 empty] | 4966
45 | 2023-06-14 | j53 | j29 |  |  | 77 | [6 empty] | 5043
46 | 2023-06-14 | j29 | j20 |  |  | 104 | [6 empty] | 5147
47 | 2023-06-14 | j20 | j2 |  |  | 114 | [6 empty] | 5261
48 | 2023-06-14 | j2 | j1 |  |  | 55 | [6 empty] | 5316
49 | 2023-06-15 | J31 | J26 |  |  | 19 | [6 empty] | 5335
50 | 2023-06-15 | J26 | J34 |  |  | 23 | [6 empty] | 5358
51 | 2023-06-15 | J34 | J42 |  |  | 33 | [6 empty] | 5391
52 | 2023-06-15 | J34 | J39 |  |  | 17 | [6 empty] | 5408
53 | 2023-06-15 | J70 | J71 |  |  | 40 | [6 empty] | 5448
54 | 2023-06-15 | J123 | J128 |  |  | 29 | [6 empty] | 5477
55 | 2023-06-15 | J72 | J53 |  |  | 42 | [6 empty] | 5519
56 | 2023-06-17 | j30 | j36 |  |  | 54 | [6 empty] | 5573
57 | 2023-06-17 | j30 | j47 |  |  | 34 | [6 empty] | 5607
58 | 2023-06-17 | j47 | j62 |  |  | 11 | [6 empty] | 5618
59 | 2023-06-17 | j62 | j21 |  |  | 58 | [6 empty] | 5676
60 | 2023-06-17 | j47 | j48 |  |  | 51 | [6 empty] | 5727
61 | 2023-06-17 | j48 | j95 |  |  | 53 | [6 empty] | 5780
62 | 2023-06-17 | j48 | j57 |  |  | 34 | [6 empty] | 5814
63 | 2023-06-17 | j57 | 67 |  |  | 14 | [6 empty] | 5828
64 | 2023-06-17 | j57 | j77 |  |  | 72 | [6 empty] | 5900
65 | 2023-06-17 | j27 | j112 |  |  | 113 | [6 empty] | 6013
66 | 2023-06-17 | j11 | j10 |  |  | 13 | [6 empty] | 6026
67 | 2023-06-18 | j27 | j32 |  |  | 45 | [6 empty] | 6071
68 | 2023-06-18 | j32 | j61 |  |  | 74 | [6 empty] | 6145
69 | 2023-06-18 | j61 | j68 |  |  | 105 | [6 empty] | 6250
70 | 2023-06-18 | j68 | j82 |  |  | 6 | [6 empty] | 6256
71 | 2023-06-18 | j61 | j68 |  |  | 80 | [6 empty] | 6336
72 | 2023-06-18 | j96 | j82 |  |  | 54 | [6 empty] | 6390
73 | 2023-06-19 | j228 | j230 |  |  | 150 | [6 empty] | 6540
74 | 2023-06-19 | j230 | j231 |  |  | 59 | [6 empty] | 6599
75 | 2023-06-19 | j230 | j89 |  |  | 67 | [6 empty] | 6666
76 | 2023-06-19 | j89 | j231 |  |  | 79 | [6 empty] | 6745 |  |  |  | 7058
77 | 2023-06-22 | j231 | j186 |  |  | 40 | [6 empty] | 6785
78 | 2023-06-22 | j186 | j114 |  |  | 28 | [6 empty] | 6813
79 | 2023-06-22 | j114 | j145 |  |  | 37 | [6 empty] | 6850
80 | 2023-06-22 | j145 | j174 |  |  | 26 | [6 empty] | 6876
81 | 2023-06-22 | j174 | j226 |  |  | 26 | [6 empty] | 6902
82 | 2023-06-22 | j186 | j226 |  |  | 80 | [6 empty] | 6982
83 | 2023-06-22 | j145 | j140 |  |  | 48 | [6 empty] | 7030
84 | 2023-06-22 | j226 | j233 |  |  | 28 | [6 empty] | 7058
85 | 2023-06-23 | J114 | J111 |  |  | 85 | [6 empty] | 7143
86 | 2023-06-23 | J111 | J161 |  |  | 166 | [6 empty] | 7309
87 | 2023-06-23 | J233 | J161 |  |  | 56 | [6 empty] | 7365
88 | 2023-06-23 | J161 | J210 |  |  | 28 | [6 empty] | 7393
89 | 2023-06-23 | J210 | J202 |  |  | 12 | [6 empty] | 7405
90 | 2023-06-23 | J210 | J219 |  |  | 60 | [6 empty] | 7465
91 | 2023-06-23 | J242 | J243 |  |  | 112 | [6 empty] | 7577
92 | 2023-06-24 | J125 | J169 |  |  | 86 | [6 empty] | 7663
93 | 2023-06-24 | J169 | J160 |  |  | 89 | [6 empty] | 7752
94 | 2023-06-24 | J160 | J156 |  |  | 22 | [6 empty] | 7774
95 | 2023-06-24 | J160 | J153 |  |  | 5 | [6 empty] | 7779
96 | 2023-06-24 | J153 | J155 |  |  | 14 | [6 empty] | 7793
97 | 2023-06-24 | J155 | J129 |  |  | 56 | [6 empty] | 7849
98 | 2023-06-24 | J243 | J196 |  |  | 170 | [6 empty] | 8019
99 | 2023-06-24 | J11 | J14 |  |  | 35 | [6 empty] | 8054
100 | 2023-07-05 | j113 | j142 |  |  | 95 | [6 empty] | 8149
101 | 2023-07-05 | j142 | j135 |  |  | 60 | [6 empty] | 8209
102 | 2023-07-05 | j163 | j228 |  |  | 240 | [6 empty] | 8449
103 | 2023-07-07 | j125 | j135 |  |  | 137 | [6 empty] | 8586
104 | 2023-07-07 | j131 | j170 |  |  | 39 | [6 empty] | 8625
105 | 2023-07-07 | j142 | j127 |  |  | 41 | [6 empty] | 8666
106 | 2023-07-08 | j86 | j87 |  |  | 54 | [6 empty] | 8720
107 | 2023-07-08 | j90 | j118 |  |  | 116 | [6 empty] | 8836
108 | 2023-07-09 | j80 | j104 |  |  |  |  | 88 |  |  |  |  | 8924
109 | 2023-07-10 | j172 | j175 |  |  | 239 | [6 empty] | 9163
110 | 2023-07-10 | j104 | j148 |  |  | 104 | [6 empty] | 9267
111 | 2023-07-10 | j100 | j163 |  |  | 163 | [6 empty] | 9430
112 | 2023-07-11 | j91 | j124 | [6 empty] | 320 |  |  | 9750
113 | 2023-07-12 | j91 | j124 | [6 empty] | 100 |  |  | 9850
114 | 2023-07-12 | j229 | j231 |  |  | 101 | [6 empty] | 9951
115 | 2023-07-12 | j229 | j232 |  |  | 96 | [6 empty] | 10047
116 | 2023-07-13 | j91 | j92 | [7 empty] | 204 |  | 10251
117 | 2023-07-14 | j201 | j185 |  |  | 35 | [6 empty] | 10286
118 | 2023-07-14 | j185 | j191 |  |  | 41 | [6 empty] | 10327
119 | 2023-07-14 | j92 | j91 | [7 empty] | 96 |  | 10423
120 | 2023-07-15 | j92 | j91 | [7 empty] | 178 |  | 10601
121 | 2023-07-16 | J139 | J147 |  |  | 53 | [6 empty] | 10654
122 | 2023-07-16 | J147 | J119 |  |  | 20 | [6 empty] | 10674
123 | 2023-07-16 | J147 | J122 |  |  | 38 | [6 empty] | 10712
124 | 2023-07-16 | J116 | J122 |  |  | 200 | [6 empty] | 10912
125 | 2023-07-16 | J97 | J118 | [6 empty] | 60 |  |  | 10972
126 | 2023-07-17 | J97 | J118 | [6 empty] | 59 |  |  | 11031
127 | 2023-07-17 | J116 | J139 | [5 empty] | 111 |  |  |  | 11142
128 | 2023-07-18 | J139 | J212 |  |  |  | 219 | [5 empty] | 11361
129 | 2023-07-19 | J212 | J213 |  |  | 84 | [6 empty] | 11445
130 | 2023-07-19 | J213 | J211 |  |  | 50 | [6 empty] | 11495
131 | 2023-07-19 | J211 | J232 |  |  | 122 | [6 empty] | 11617
132 | 2023-07-19 | J232 | J229 |  |  | 96 | [6 empty] | 11713
133 | 2023-07-19 | J229 | J234 |  |  | 144 | [6 empty] | 11857
134 | 2023-07-20 | J55 | J92 | [8 empty] | 122 | 11979
135 | 2023-07-20 | J92 | J97 | [8 empty] | 13 | 11992
136 | 2023-07-20 | J55 | J43 |  |  | 89 | [6 empty] | 12081
137 | 2023-07-20 | J43 | J41 |  |  | 28 | [6 empty] | 12109
138 | 2023-07-21 | J55 | J65 |  |  | 63 | [6 empty] | 12172
139 | 2023-07-21 | J55A | J54B |  |  | 17 | [6 empty] | 12189
140 | 2023-07-22 | j113 | j196 |  |  |  | 119 | [5 empty] | 12308
141 | 2023-07-23 | j97 | j80 | [7 empty] | 88 |  | 12396
142 | 2023-07-23 | j213 | j217 |  |  | 106 | [6 empty] | 12502
143 | 2023-07-24 | J80 | J79 |  |  |  | 22 | [5 empty] | 12524
144 | 2023-07-24 | J79 | J103 |  |  | 27 | [6 empty] | 12551
145 | 2023-07-24 | J79 | J110 |  |  | 130 | [6 empty] | 12681
146 | 2023-07-24 | J81 | J81A |  |  | 30 | [6 empty] | 12711
147 | 2023-07-24 | j134 | j108 |  |  | 95 | [6 empty] | 12806
148 | 2023-07-25 | j108 | j133 |  |  | 52 | [6 empty] | 12858
149 | 2023-07-25 | j133 | j94 |  |  | 130 | [6 empty] | 12988
150 | 2023-07-25 | j94 | j636 |  |  | 57 | [6 empty] | 13045 |  |  |  |  | 6902
151 | 2023-07-25 | j63 | j9 |  |  | 117 | [6 empty] | 13162
152 | 2023-07-25 | j110 | j141 |  |  | 53 | [6 empty] | 13215
153 | 2023-07-25 | j141 | j141a |  |  | 150 | [6 empty] | 13365
[6 empty] | 10364 | 600 | 725 | 436 | 539 | 566 | 135 | 13365
[6 empty] | 17139 | 813 | 1002 | 483 | 539 | 566 | 163 | 20705
13736
| Block |  | Mangraura
| GP |  | MALAK
| Agency Name/ Work Order No |  | SHUKLA CONSTRUCTION
63MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent |  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
| 1 | 2023-06-08 | 4300 |  |  | 1098 |  |  | 63 | 17139 | 14000 | 10364 | 3636
| 2 | 2023-05-29 | 2450 |  |  | 1090 |  |  | 75 | 813 | 600 | 600 | 0
| 3 | 2023-05-28 | 600 |  |  | 1088 |  |  | 90 | 1002 | 1050 | 725 | 325
| 4 | 2023-06-21 | 3200 |  |  | 7903 |  |  | 110 | 483 | 525 | 436 | 89
| 5 | 2023-07-07 | 1950 |  |  | 7906 |  |  | 125 | 539 | 540 | 539 | 1
| 6 | 2023-07-26 | 1500 |  |  | 7916 |  |  | 140 | 566 | 576 | 566 | 10
[9 empty] | 160 | 163 | 168 | 135 | 33
|  | TOTAL | 14000
75MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-29 | 300 |  |  | 1090
| 2 | 2023-07-07 | 300 |  |  | 7906
3
3
|  | TOTAL | 600
90MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-06-08 | 300 |  |  | 1098
| 2 | 2023-05-28 | 750 |  |  | 1088
|  | TOTAL | 1050
110MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-29 | 375 |  |  | 1090
| 2 | 2023-07-07 | 150 |  |  | 7906
3
4
5
6
7
8
|  | TOTAL | 525
125MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-06-03 | 540 |  |  | 1093
|  | TOTAL | 540
140MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-06-03 | 576 |  |  | 1093
|  | TOTAL | 576
160MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-06-03 | 168 |  |  | 1093
|  | TOTAL | 168

## LAULI POKHATAKHAM
Block |  | Mangraura
GP |  | LAULI POKHATAKHAM
Total Length (M) |  | 25451
FHTC (No's)
Agency Name |  | Shukla construction
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) |  |  |  |  | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 140mm
1 | 2023-05-05 | j249 | j126 | K.C ROAD | HDPE | 280 |  |  |  |  | 280 | L.H.S | 1.5 | NIKHIL
2 | 2023-05-06 | j249 | j126 | K.C ROAD | HDPE | 152 |  |  |  |  | 432 | L.H.S | 1.5 | NIKHIL
3 | 2023-05-06 | J126 | J108 | K.C ROAD | HDPE | 200 |  |  |  |  | 632 | L.H.S | 1.5 | NIKHIL
4 | 2023-05-07 | J126 | J108 | K.C ROAD | HDPE | 65 |  |  |  |  | 697 | L.H.S | 1.5 | NIKHIL
5 | 2023-05-07 | j108 | j115 | K.C ROAD | HDPE | 93 |  |  |  |  | 790 | L.H.S | 1.5 | NIKHIL |  |  | 12074
6 | 2023-05-07 | j115 | j140 | K.C ROAD | HDPE | 35 |  |  |  |  | 825 | L.H.S | 1.5 | NIKHIL
7 | 2023-05-07 | j140 | j132 | K.C ROAD | HDPE | 200 |  |  |  |  | 1025 | L.H.S | 1.5 | NIKHIL
8 | 2023-05-08 | j140 | j132 | K.C ROAD | HDPE | 150 |  |  |  |  | 1175 | L.H.S | 1.5 | NIKHIL
9 | 2023-05-09 | j140 | j132 | K.C ROAD | HDPE | 60 |  |  |  |  | 1235 | L.H.S | 1.5 | NIKHIL
10 | 2023-05-09 | j118 | j242 | K.C ROAD | HDPE | 200 |  |  |  |  | 1435 | L.H.S | 1.5 | NIKHIL
11 | 2023-05-11 | j90 | j80 | K.C ROAD | HDPE | 106 |  |  |  |  | 1541 | L.H.S | 1.5 | NIKHIL
12 | 2023-05-11 | j80 | j81 | K.C ROAD | HDPE | 38 |  |  |  |  | 1579 | L.H.S | 1.5 | NIKHIL
13 | 2023-05-11 | j81 | j117 | K.C ROAD | HDPE | 195 |  |  |  |  | 1774 | L.H.S | 1.5 | NIKHIL
14 | 2023-05-12 | j43 | j23 | K.C ROAD | HDPE | 109 |  |  |  |  | 1883 | L.H.S | 1.5 | NIKHIL
15 | 2023-05-12 | j23 | j28 | K.C ROAD | HDPE | 164 |  |  |  |  | 2047 | L.H.S | 1.5 | NIKHIL
16 | 2023-05-12 | j28 | j74 | K.C ROAD | HDPE | 41 |  |  |  |  | 2088 | L.H.S | 1.5 | NIKHIL
17 | 2023-05-13 | j81 | j53 | K.C ROAD | HDPE | 150 |  |  |  |  | 2238 | L.H.S | 1.5 | NIKHIL
18 | 2023-05-13 | j43 | j23 | K.C ROAD | HDPE | 100 |  |  |  |  | 2338 | L.H.S | 1.5 | NIKHIL
19 | 2023-05-13 | j74 | j51 | K.C ROAD | HDPE | 65 |  |  |  |  | 2403 | L.H.S | 1.5 | NIKHIL
20 | 2023-05-13 | j51 | j34 | K.C ROAD | HDPE | 35 |  |  |  |  | 2438 | L.H.S | 1.5 | NIKHIL
21 | 2023-05-14 | j294 | j288 | K.C ROAD | HDPE | 140 |  |  |  |  | 2578 | L.H.S | 2 | NIKHIL
22 | 2023-05-14 | j288 | j289 | K.C ROAD | HDPE | 125 |  |  |  |  | 2703 | L.H.S | 2 | NIKHIL
23 | 2023-05-14 | j34 | j1 | K.C ROAD | HDPE | 50 |  |  |  |  | 2753 | L.H.S | 2 | NIKHIL
24 | 2023-05-15 | j289 | j265 | K.C ROAD | HDPE | 345 |  |  |  |  | 3098 | L.H.S | 2 | NIKHIL
25 | 2023-05-16 | j265 | j175 | K.C ROAD | HDPE |  |  | 261 |  |  | 3359 | L.H.S | 2 | NIKHIL
26 | 2023-05-17 | j28 | j74 | K.C ROAD | HDPE | 150 |  |  |  |  | 3509 | L.H.S | 2 | NIKHIL
27 | 2023-05-18 | J267 | J190 | K.C ROAD | HDPE |  |  | 320 |  |  | 3829 | L.H.S | 2 | NIKHIL
28 | 2023-05-19 | J267 | J190 | K.C ROAD | HDPE |  |  | 176 |  |  | 4005 | L.H.S | 2 | NIKHIL
29 | 2023-05-19 | j175 | j267 | K.C ROAD | HDPE |  |  |  | 300 |  | 4305 | L.H.S | 2 | NIKHIL
30 | 2023-05-21 | J267 | J253 | K.C ROAD | HDPE |  |  | 300 |  |  | 4605 | L.H.S | 2 | NIKHIL
31 | 2023-05-21 | J253 | J295 | K.C ROAD | HDPE | 50 |  |  |  |  | 4655 | L.H.S | 2 | NIKHIL
32 | 2023-05-22 | J132 | J83 | K.C ROAD | HDPE | 147 |  |  |  |  | 4802 | L.H.S | 2 | NIKHIL
33 | 2023-05-22 | J253 | J295 | K.C ROAD | HDPE | 238 |  |  |  |  | 5040 | L.H.S | 2 | NIKHIL
34 | 2023-05-24 | J190 | J231 | K.C ROAD | HDPE | 67 |  |  |  |  | 5107 | L.H.S | 2 | NIKHIL
35 | 2023-05-24 | J231 | J173 | K.C ROAD | HDPE | 428 |  |  |  |  | 5535 | L.H.S | 2 | NIKHIL
36 | 2023-05-24 | J295 | J198 | K.C ROAD | HDPE | 209 |  |  |  |  | 5744 | L.H.S | 2 | NIKHIL
37 | 2023-05-24 | J196 | J152 | K.C ROAD | HDPE | 150 |  |  |  |  | 5894 | L.H.S | 2 | NIKHIL
38 | 2023-05-24 | J253 | J166 | K.C ROAD | HDPE | 426 |  |  |  |  | 6320 | L.H.S | 2 | NIKHIL
39 | 2023-05-24 | J166 | J199 | K.C ROAD | HDPE | 75 |  |  |  |  | 6395 | L.H.S | 2 | NIKHIL
40 | 2023-05-25 | J292 | J262 | K.C ROAD | HDPE | 180 |  |  |  |  | 6575 | L.H.S | 2 | NIKHIL
41 | 2023-05-25 | J262 | J269 | K.C ROAD | HDPE | 76 |  |  |  |  | 6651 | L.H.S | 2 | NIKHIL
42 | 2023-05-25 | J292 | J290 | K.C ROAD | HDPE | 152 |  |  |  |  | 6803 | L.H.S | 2 | NIKHIL
43 | 2023-05-25 | J290 | J295 | K.C ROAD | HDPE | 252 |  |  |  |  | 7055 | L.H.S | 2 | NIKHIL
44 | 2023-05-25 | J25 | J106 | K.C ROAD | HDPE | 65 |  |  |  |  | 7120 | L.H.S | 2 | NIKHIL
45 | 2023-05-25 | J83 | J47 | K.C ROAD | HDPE | 217 |  |  |  |  | 7337 | L.H.S | 1.5 | NIKHIL
46 | 2023-05-25 | J47 | J5 | K.C ROAD | HDPE | 121 |  |  |  |  | 7458 | L.H.S | 1.5 | NIKHIL
47 | 2023-05-25 | J83 | J43 | K.C ROAD | HDPE | 329 |  |  |  |  | 7787 | L.H.S | 2 | NIKHIL
48 | 2023-05-25 | J106 | J73 | K.C ROAD | HDPE | 392 |  |  |  |  | 8179 | L.H.S | 2 | NIKHIL
49 | 2023-05-26 | J73 | J43 | K.C ROAD | HDPE | 270 |  |  |  |  | 8449 | L.H.S | 2 | NIKHIL
50 | 2023-05-26 | J106 | J73 | K.C ROAD | HDPE | 392 |  |  |  |  | 8841 | L.H.S | 2 | NIKHIL
51 | 2023-05-27 | J83 | J132 | K.C ROAD | HDPE | 147 |  |  |  |  | 8988 | L.H.S | 2 | NIKHIL
52 | 2023-05-27 | J132 | J138 | K.C ROAD | HDPE | 257 |  |  |  |  | 9245 | L.H.S | 2 | NIKHIL
53 | 2023-05-28 | J138 | J127 | K.C ROAD | HDPE | 206 |  |  |  |  | 9451 | L.H.S | 2 | NIKHIL
54 | 2023-05-28 | J127 | J104 | K.C ROAD | HDPE | 270 |  |  |  |  | 9721 | L.H.S | 2 | NIKHIL
55 | 2023-06-04 | j183 | j151 | K.C ROAD | HDPE | 170 |  |  |  |  | 9891 | L.H.S | 2 | NIKHIL
56 | 2023-06-04 | j151 | j243 | K.C ROAD | HDPE | 71 |  |  |  |  | 9962 | L.H.S | 2 | NIKHIL
57 | 2023-06-04 | j243 | j208 | K.C ROAD | HDPE | 115 |  |  |  |  | 10077 | L.H.S | 2 | NIKHIL
58 | 2023-06-04 | j208 | j225 | K.C ROAD | HDPE | 25 |  |  |  |  | 10102 | L.H.S | 2 | NIKHIL
59 | 2023-06-04 | j225 | j212 | K.C ROAD | HDPE | 88 |  |  |  |  | 10190 | L.H.S | 2 | NIKHIL
60 | 2023-06-04 | j212 | j206 | K.C ROAD | HDPE | 66 |  |  |  |  | 10256 | L.H.S | 2 | NIKHIL
61 | 2023-06-09 | j212 | j230 | K.C ROAD | HDPE | 15 |  |  |  |  | 10271 | L.H.S | 1 | NIKHIL
62 | 2023-06-09 | j230 | j206 | K.C ROAD | HDPE | 66 |  |  |  |  | 10337 | L.H.S | 1 | NIKHIL
63 | 2023-06-09 | j206 | j168 | K.C ROAD | HDPE | 306 |  |  |  |  | 10643 | L.H.S | 1 | NIKHIL
64 | 2023-06-09 | j168 | j165 | K.C ROAD | HDPE | 136 |  |  |  |  | 10779 | L.H.S | 1 | NIKHIL
65 | 2023-06-09 | j165 | j202 | K.C ROAD | HDPE | 23 |  |  |  |  | 10802 | L.H.S | 1 | NIKHIL
66 | 2023-06-09 | j202 | j237 | K.C ROAD | HDPE | 52 |  |  |  |  | 10854 | L.H.S | 1 | NIKHIL
67 | 2023-06-09 | j202 | j233 | K.C ROAD | HDPE | 259 |  |  |  |  | 11113 | L.H.S | 1 | NIKHIL
68 | 2023-06-10 | j262 | j221 | K.C ROAD | HDPE | 44 |  |  |  |  | 11157 | L.H.S | 1 | NIKHIL
69 | 2023-06-10 | j221 | j274 | K.C ROAD | HDPE | 105 |  |  |  |  | 11262 | L.H.S | 1 | NIKHIL
70 | 2023-06-10 | j215 | j252 | K.C ROAD | HDPE | 26 |  |  |  |  | 11288 | L.H.S | 1 | NIKHIL
71 | 2023-06-10 | j252 | j228 | K.C ROAD | HDPE | 25 |  |  |  |  | 11313 | L.H.S | 1 | NIKHIL
72 | 2023-06-10 | j214 | j254 | K.C ROAD | HDPE | 40 |  |  |  |  | 11353 | L.H.S | 1 | NIKHIL
73 | 2023-06-10 | j254 | j189 | K.C ROAD | HDPE | 61 |  |  |  |  | 11414 | L.H.S | 1 | NIKHIL
74 | 2023-06-10 | j254 | j260 | K.C ROAD | HDPE | 20 |  |  |  |  | 11434 | L.H.S | 1 | NIKHIL
75 | 2023-06-11 | j259 | j264 | K.C ROAD | HDPE | 77 |  |  |  |  | 11511 | L.H.S | 1 | NIKHIL
76 | 2023-06-11 | j262 | j246 | K.C ROAD | HDPE | 96 |  |  |  |  | 11607 | L.H.S | 1 | NIKHIL
77 | 2023-06-11 | j252 | j254 | K.C ROAD | HDPE | 54 |  |  |  |  | 11661 | L.H.S | 1 | NIKHIL
78 | 2023-06-11 | j264 | j256 | K.C ROAD | HDPE | 100 |  |  |  |  | 11761 | L.H.S | 2 | NIKHIL
79 | 2023-06-12 | j229 | j114 | K.C ROAD | HDPE | 100 |  |  |  |  | 11861 | L.H.S | 2 | NIKHIL
80 | 2023-06-13 | j204 | j197 | K.C ROAD | HDPE | 100 |  |  |  |  | 11961 | L.H.S | 2 | NIKHIL
81 | 2023-06-13 | j190 | j204 | K.C ROAD | HDPE | 30 |  |  |  |  | 11991 | L.H.S | 2 | NIKHIL
82 | 2023-06-14 | j183 | 247 | K.C ROAD | HDPE | 41 |  |  |  |  | 12032 | L.H.S | 2 | NIKHIL
83 | 2023-06-14 | j151 | j183 | K.C ROAD | HDPE | 170 |  |  |  |  | 12202 | L.H.S | 2 | NIKHIL
84 | 2023-06-14 | j243 | j151 | K.C ROAD | HDPE | 71 |  |  |  |  | 12273 | L.H.S | 2 | NIKHIL
85 | 2023-06-14 | j208 | j243 | K.C ROAD | HDPE | 115 |  |  |  |  | 12388 | L.H.S | 2 | NIKHIL
86 | 2023-06-14 | j200 | j222 | K.C ROAD | HDPE | 43 |  |  |  |  | 12431 | L.H.S | 2 | NIKHIL
87 | 2023-06-15 | J225 | J194 | K.C ROAD | HDPE | 181 |  |  |  |  | 12612
88 | 2023-06-15 | J272 | J268 | K.C ROAD | HDPE | 98 |  |  |  |  | 12710
89 | 2023-06-15 | J208 | J199 | K.C ROAD | HDPE | 63 |  |  |  |  | 12773
90 | 2023-06-15 | J208 | J243 | K.C ROAD | HDPE | 110 |  |  |  |  | 12883
91 | 2023-06-16 | j194 | j180 | K.C ROAD | HDPE | 38 |  |  |  |  | 12921
92 | 2023-06-16 | j237 | j227 | K.C ROAD | HDPE | 41 |  |  |  |  | 12962
93 | 2023-06-16 | j168 | j178 | K.C ROAD | HDPE | 51 |  |  |  |  | 13013
94 | 2023-06-16 | j212 | j217 | K.C ROAD | HDPE | 45 |  |  |  |  | 13058
95 | 2023-06-16 | j199 | j201 | K.C ROAD | HDPE | 31 |  |  |  |  | 13089
96 | 2023-06-16 | j186 | j179 | K.C ROAD | HDPE | 32 |  |  |  |  | 13121
97 | 2023-06-16 | j179 | j200 | K.C ROAD | HDPE | 12 |  |  |  |  | 13133
98 | 2023-06-16 | j268 | j279 | K.C ROAD | HDPE | 30 |  |  |  |  | 13163
99 | 2023-06-16 | j180 | j191 | K.C ROAD | HDPE | 21 |  |  |  |  | 13184
100 | 2023-06-16 | j191 | j186 | K.C ROAD | HDPE | 26 |  |  |  |  | 13210
101 | 2023-06-16 | j186 | j195 | K.C ROAD | HDPE | 42 |  |  |  |  | 13252
102 | 2023-06-17 | j195 | j210 | K.C ROAD | HDPE | 32 |  |  |  |  | 13284
103 | 2023-06-17 | j210 | j236 | K.C ROAD | HDPE | 50 |  |  |  |  | 13334
104 | 2023-06-17 | j236 | j224 | K.C ROAD | HDPE | 25 |  |  |  |  | 13359
105 | 2023-06-17 | j224 | j240 | K.C ROAD | HDPE | 13 |  |  |  |  | 13372
106 | 2023-06-17 | j240 | j244 | K.C ROAD | HDPE | 21 |  |  |  |  | 13393
107 | 2023-06-17 | j244 | j245 | K.C ROAD | HDPE | 21 |  |  |  |  | 13414
108 | 2023-06-17 | j245 | j272 | K.C ROAD | HDPE | 15 |  |  |  |  | 13429
109 | 2023-06-19 | j33 | j20 | K.C ROAD | HDPE | 13 |  |  |  |  | 13442
110 | 2023-06-19 | j21 | j33 | K.C ROAD | HDPE | 37 |  |  |  |  | 13479
111 | 2023-06-19 | j21 | j26 | K.C ROAD | HDPE | 76 |  |  |  |  | 13555
112 | 2023-06-19 | j19 | j21 | K.C ROAD | HDPE | 90 |  |  |  |  | 13645
113 | 2023-06-19 | j19 | j31 | K.C ROAD | HDPE | 35 |  |  |  |  | 13680
114 | 2023-06-19 | j31 | j15 | K.C ROAD | HDPE | 54 |  |  |  |  | 13734
115 | 2023-06-19 | j15 | j11 | K.C ROAD | HDPE | 120 |  |  |  |  | 13854
116 | 2023-06-19 | j11 | j9 | K.C ROAD | HDPE | 32 |  |  |  |  | 13886
117 | 2023-06-20 | j15 | j2 | K.C ROAD | HDPE | 55 |  |  |  |  | 13941
118 | 2023-06-20 | j19 | j46 | K.C ROAD | HDPE | 70 |  |  |  |  | 14011
119 | 2023-06-20 | j46 | j18 | K.C ROAD | HDPE | 49 |  |  |  |  | 14060 | [5 empty] | 6710
120 | 2023-06-20 | j18 | j6 | K.C ROAD | HDPE | 78 |  |  |  |  | 14138
121 | 2023-06-20 | j46 | j44 | K.C ROAD | HDPE | 84 |  |  |  |  | 14222
122 | 2023-06-20 | j18 | j8 | K.C ROAD | HDPE | 40 |  |  |  |  | 14262
123 | 2023-06-24 | J43 | J23 | K.C ROAD | HDPE | 109 |  |  |  |  | 14371
124 | 2023-06-24 | J23 | J28 | K.C ROAD | HDPE | 164 |  |  |  |  | 14535
125 | 2023-06-24 | J28 | J74 | K.C ROAD | HDPE | 141 |  |  |  |  | 14676
126 | 2023-06-24 | J74 | J51 | K.C ROAD | HDPE | 67 |  |  |  |  | 14743
127 | 2023-06-24 | J51 | J34 | K.C ROAD | HDPE | 37 |  |  |  |  | 14780
128 | 2023-06-24 | J34 | J45 | K.C ROAD | HDPE | 52 |  |  |  |  | 14832
129 | 2023-06-24 | J45 | J13 | K.C ROAD | HDPE | 23 |  |  |  |  | 14855
130 | 2023-07-06 | j196 | j152 | K.C ROAD | HDPE | 210 |  |  |  |  | 15065
131 | 2023-07-07 | j196 | j152 | K.C ROAD | HDPE | 50 |  |  |  |  | 15115
132 | 2023-07-08 | j295 | j170 | K.C ROAD | HDPE | 70 |  |  |  |  | 15185
133 | 2023-07-09 | j119 | j133 | K.C ROAD | HDPE | 75 |  |  |  |  | 15260
134 | 2023-07-10 | j119 | j82 | K.C ROAD | HDPE | 200 |  |  |  |  | 15460
135 | 2023-07-13 | j108 | j100 | K.C ROAD | HDPE | 70 |  |  |  |  | 15530
136 | 2023-07-13 | j100 | j95 | K.C ROAD | HDPE | 17 |  |  |  |  | 15547
137 | 2023-07-13 | j95 | j92 | K.C ROAD | HDPE | 105 |  |  |  |  | 15652
138 | 2023-07-13 | j115 | j111 | K.C ROAD | HDPE | 55 |  |  |  |  | 15707
139 | 2023-07-13 | j111 | j122 | K.C ROAD | HDPE | 54 |  |  |  |  | 15761
140 | 2023-07-22 | j43 | j24 | K.C ROAD | HDPE |  |  |  | 86 |  | 15847
141 | 2023-07-22 | j24 | j17 | K.C ROAD | HDPE |  |  |  |  | 26 | 15873
142 | 2023-07-22 | j24 | j42 | K.C ROAD | HDPE |  |  |  |  | 92 | 15965 |  |  |  |  | 1641
143 | 2023-07-22 | j42 | j55 | K.C ROAD | HDPE |  |  |  |  | 31 | 15996 |  |  |  |  | 5108
144 | 2023-07-22 | j55 | j56 | K.C ROAD | HDPE |  |  |  |  | 22 | 16018
145 | 2023-07-22 | j56 | j41 | K.C ROAD | HDPE |  |  |  |  | 95 | 16113
146 | 2023-07-22 | j41 | j67 | K.C ROAD | HDPE |  |  |  |  | 84 | 16197
147 | 2023-07-22 | j67 | j90 | K.C ROAD | HDPE |  |  |  | 88 |  | 16285
148 | 2023-07-22 | j90 | j96 | K.C ROAD | HDPE |  |  |  | 40 |  | 16325
149 | 2023-07-22 | j96 | j175 | K.C ROAD | HDPE |  |  |  | 171 |  | 16496
[6 empty] | 14404 | 0 | 1057 | 685 | 350 | 16496
[6 empty] | 23136 | 198 | 1057 | 691 | 369 | 25451
| Block |  | Mangraura
| GP |  | LAULI POKATHKAM
| Agency Name/ Work Order No |  | SHUKLA CONSTRUCTION
63MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent |  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
| 1 | 2023-05-03 | 3000 |  |  | 1079 |  |  | 63 | 23136 | 14800 | 14404 | 396
| 2 | 2023-05-14 | 400 |  |  | 1085 |  |  | 75 | 198 | 400 | 0 | 400
| 3 | 2023-05-19 | 3100 |  |  | 1086 |  |  | 90 | 1057 | 1100 | 1057 | 43
| 4 | 2023-05-24 | 6000 |  |  | 1087 |  |  | 110 | 691 | 700 | 685 | 15
| 5 | 2023-06-21 | 2300 |  |  | 7902 |  |  | 140 | 369 | 372 | 350 | 22
|  | TOTAL | 14800
75MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-19 | 400 |  |  | 1086
2
3
3
|  | TOTAL | 400
90MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-14 | 800 |  |  | 1085
| 2 | 2023-05-19 | 300 |  |  | 1086
|  | TOTAL | 1100
110MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-14 | 400 |  |  | 1085
| 2 | 2023-06-21 | 300 |  |  | 7902
3
4
5
6
7
8
|  | TOTAL | 700
140MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-06-03 | 372 |  |  | 10+2
|  | TOTAL | 372

## barasarai
Block |  | Mangraura
GP |  | Barasarai
Total Length (M) |  | 23048
FHTC (No's)
Agency Name |  | AGS construction
Sl.No | Date | Start Node | End Node | Type of Road | DI/HDPE | Pipe Length (M) | [6 empty] | Cumulative Length (M) | LHS/RHS | Distance from Road C/L | Site Engineer Sign | Remarks
[6 empty] | 63mm | 75mm | 90mm | 110mm | 125mm | 140mm | 160mm
1 | 2023-04-28 | j43 | j46 | KC ROAD | HDPE | 200 | [6 empty] | 200
2 | 2023-04-29 | j43 | j46 | KC ROAD | HDPE | 100 | [6 empty] | 300
3 | 2023-04-29 | j154 | j172 | KC ROAD | HDPE | 200 | [6 empty] | 500
4 | 2023-05-01 | j154 | j172 | KC ROAD | HDPE | 273 | [6 empty] | 773
5 | 2023-05-06 | J14 | J15 | KC ROAD | HDPE | 209 | [6 empty] | 982
6 | 2023-05-07 | J13 | J12 | KC ROAD | HDPE | 110 | [6 empty] | 1092
7 | 2023-05-08 | j57 | j61 | KC ROAD | HDPE | 211 | [6 empty] | 1303
8 | 2023-05-18 | J63 | J62 | KC ROAD | HDPE | 130 | [6 empty] | 1433
9 | 2023-05-19 | j62 | j57 | KC ROAD | HDPE | 135 | [6 empty] | 1568
10 | 2023-05-19 | j63 | j62 | KC ROAD | HDPE | 20 | [6 empty] | 1588
11 | 2023-05-21 | J54 | J57 | KC ROAD | HDPE | 120 | [6 empty] | 1708
12 | 2023-05-21 | J54 | J61 | KC ROAD | HDPE | 30 | [6 empty] | 1738
13 | 2023-05-21 | J10 | J22 | KC ROAD | HDPE | 157 | [6 empty] | 1895
14 | 2023-05-21 | J22 | J25 | KC ROAD | HDPE | 27 | [6 empty] | 1922
15 | 2023-05-21 | J24 | J23 | KC ROAD | HDPE | 105 | [6 empty] | 2027
16 | 2023-05-21 | J22 | J21 | KC ROAD | HDPE | 24 | [6 empty] | 2051
17 | 2023-05-21 | J24 | J25 | KC ROAD | HDPE | 45 | [6 empty] | 2096
18 | 2023-05-22 | J39 | J38 | KC ROAD | HDPE | 105 | [6 empty] | 2201
19 | 2023-05-22 | J25 | J39 | KC ROAD | HDPE | 22 | [6 empty] | 2223
20 | 2023-05-22 | J25 | J40 | KC ROAD | HDPE | 70 | [6 empty] | 2293
21 | 2023-05-24 | J53 | J45 | KC ROAD | HDPE | 77 | [6 empty] | 2370
22 | 2023-05-24 | J45 | J39 | KC ROAD | HDPE | 40 | [6 empty] | 2410
23 | 2023-05-24 | J38 | J43 | KC ROAD | HDPE | 45 | [6 empty] | 2455
24 | 2023-05-24 | J38 | J37 | KC ROAD | HDPE | 25 | [6 empty] | 2480
25 | 2023-05-24 | J43 | J44 | KC ROAD | HDPE | 44 | [6 empty] | 2524
26 | 2023-05-24 | J52 | J50 | KC ROAD | HDPE | 25 | [6 empty] | 2549
27 | 2023-05-24 | J68 | J70 | KC ROAD | HDPE | 59 | [6 empty] | 2608
28 | 2023-05-24 | J70 | J75 | KC ROAD | HDPE | 60 | [6 empty] | 2668
29 | 2023-05-25 | J52 | J68 | KC ROAD | HDPE | 90 | [6 empty] | 2758
30 | 2023-05-25 | J79 | J72 | KC ROAD | HDPE |  | 238 | [5 empty] | 2996
31 | 2023-05-25 | J72 | J53 | KC ROAD | HDPE |  | 141 | [5 empty] | 3137
32 | 2023-05-25 | J71 | J75 | KC ROAD | HDPE | 117 | [6 empty] | 3254
33 | 2023-05-25 | J71 | J72 | KC ROAD | HDPE | 26 | [6 empty] | 3280
34 | 2023-05-25 | J71 | J70 | KC ROAD | HDPE | 16 | [6 empty] | 3296
35 | 2023-05-28 | J80 | J0 | KC ROAD | HDPE | 21 | [6 empty] | 3317 |  |  | EXTRA LINE
36 | 2023-05-28 | J83 | J82 | KC ROAD | HDPE | 29 | [6 empty] | 3346
37 | 2023-05-28 | J82 | J86 | KC ROAD | HDPE | 227 | [6 empty] | 3573
38 | 2023-05-28 | J40 | J53 | KC ROAD | HDPE |  | 75 | [5 empty] | 3648
39 | 2023-05-28 | J82 | J88 | KC ROAD | HDPE | 66 | [6 empty] | 3714
40 | 2023-05-28 | J86 | J81 | KC ROAD | HDPE | 30 | [6 empty] | 3744
41 | 2023-05-29 | j89 | j90 | KC ROAD | HDPE | 155 | [6 empty] | 3899
42 | 2023-05-30 | j73 | j74 | KC ROAD | HDPE | 124 | [6 empty] | 4023
43 | 2023-05-30 | j145 | j197 | KC ROAD | HDPE | 200 | [6 empty] | 4223
44 | 2023-05-31 | j36 | j32 | KC ROAD | HDPE | 114 | [6 empty] | 4337
45 | 2023-06-01 | j145 | j197 | KC ROAD | HDPE | 100 | [6 empty] | 4437
46 | 2023-06-01 | j32 | j33 | KC ROAD | HDPE | 21 | [6 empty] | 4458
47 | 2023-06-01 | j32 | j29 | KC ROAD | HDPE | 119 | [6 empty] | 4577
48 | 2023-06-02 | j110 | j114 | KC ROAD | HDPE | 181 | [6 empty] | 4758
49 | 2023-06-02 | j114 | j117 | KC ROAD | HDPE | 48 | [6 empty] | 4806
50 | 2023-06-02 | j107 | j108 | KC ROAD | HDPE | 53 | [6 empty] | 4859
51 | 2023-06-04 | J107 | J99 | KC ROAD | HDPE | 107 | [6 empty] | 4966
52 | 2023-06-04 | J99 | J105 | KC ROAD | HDPE | 73 | [6 empty] | 5039
53 | 2023-06-04 | J98 | J100 | KC ROAD | HDPE | 50 | [6 empty] | 5089
54 | 2023-06-04 | J138 | J139 | KC ROAD | HDPE | 25 | [6 empty] | 5114
55 | 2023-06-06 | j115 | j116 | KC ROAD | HDPE | 80 | [6 empty] | 5194
56 | 2023-06-07 | j91 | j98 | KC ROAD | HDPE | 80 | [6 empty] | 5274
57 | 2023-06-08 | j107 | j109 | KC ROAD | HDPE | 96 | [6 empty] | 5370
58 | 2023-06-09 | j94 | j110 | KC ROAD | HDPE | 44 | [6 empty] | 5414
59 | 2023-06-09 | j91 | j98 | KC ROAD | HDPE | 22 | [6 empty] | 5436
60 | 2023-06-09 | j112 | j111 | KC ROAD | HDPE | 21 | [6 empty] | 5457
61 | 2023-06-10 | j79 | j187 | KC ROAD | HDPE | 80 | [6 empty] | 5537
62 | 2023-06-12 | j96 | j97 | KC ROAD | HDPE | 128 | [6 empty] | 5665
63 | 2023-06-12 | j90 | j89 | KC ROAD | HDPE | 150 | [6 empty] | 5815
64 | 2023-06-13 | j197 | j145 | KC ROAD | HDPE | 62 | [6 empty] | 5877
65 | 2023-06-13 | j92 | j93 | KC ROAD | HDPE | 285 | [6 empty] | 6162
66 | 2023-06-13 | j127 | j128 | KC ROAD | HDPE | 166 | [6 empty] | 6328
67 | 2023-06-14 | j76 | j81 | KC ROAD | HDPE | 100 | [6 empty] | 6428
68 | 2023-06-14 | j154 | j151 | KC ROAD | HDPE |  |  | 89 |  |  |  |  | 6517
69 | 2023-06-14 | j151 | j145 | KC ROAD | HDPE |  |  | 50 |  |  |  |  | 6567
70 | 2023-06-15 | J211 | J212 | KC ROAD | HDPE | 60 | [6 empty] | 6627
71 | 2023-06-15 | J218 | J223 | KC ROAD | HDPE | 65 | [6 empty] | 6692
72 | 2023-06-15 | J199 | J200 | KC ROAD | HDPE | 122 | [6 empty] | 6814
73 | 2023-06-15 | J145 | J197 | KC ROAD | HDPE | 277 | [6 empty] | 7091
74 | 2023-06-16 | j226 | j233 | KC ROAD | HDPE | 80 | [6 empty] | 7171
75 | 2023-06-16 | j133 | j140 | KC ROAD | HDPE | 45 | [6 empty] | 7216
76 | 2023-06-16 | j210 | j211 | KC ROAD | HDPE | 24 | [6 empty] | 7240
77 | 2023-06-16 | j211 | j212 | KC ROAD | HDPE | 60 | [6 empty] | 7300
78 | 2023-06-17 | j215 | j216 | KC ROAD | HDPE | 28 | [6 empty] | 7328
79 | 2023-06-17 | j232 | j243 | KC ROAD | HDPE | 50 | [6 empty] | 7378
80 | 2023-06-17 | j226 | j217 | KC ROAD | HDPE | 132 | [6 empty] | 7510
81 | 2023-06-17 | j243 | j249 | KC ROAD | HDPE | 46 | [6 empty] | 7556
82 | 2023-06-17 | j249 | j250 | KC ROAD | HDPE | 65 | [6 empty] | 7621
83 | 2023-06-17 | j249 | j252 | KC ROAD | HDPE | 150 | [6 empty] | 7771
84 | 2023-06-18 | j227 | j232 | KC ROAD | HDPE | 69 | [6 empty] | 7840
85 | 2023-06-18 | j231 | j232 | KC ROAD | HDPE | 28 | [6 empty] | 7868
86 | 2023-06-18 | j231 | j233 | KC ROAD | HDPE | 34 | [6 empty] | 7902
87 | 2023-06-18 | j197 | j204 | KC ROAD | HDPE | 113 | [6 empty] | 8015
88 | 2023-06-18 | j203 | j204 | KC ROAD | HDPE | 99 | [6 empty] | 8114
89 | 2023-06-18 | j201 | j203 | KC ROAD | HDPE | 21 | [6 empty] | 8135
90 | 2023-06-18 | j206 | j209 | KC ROAD | HDPE | 51 | [6 empty] | 8186
91 | 2023-06-18 | j209 | j208 | KC ROAD | HDPE | 42 | [6 empty] | 8228
92 | 2023-06-18 | j226b | j226c | KC ROAD | HDPE | 34 | [6 empty] | 8262
93 | 2023-06-18 | j206 | j209a | KC ROAD | HDPE | 16 | [6 empty] | 8278
94 | 2023-06-19 | j198 | j201 | KC ROAD | HDPE | 44 | [6 empty] | 8322
95 | 2023-06-19 | j201 | 201a | KC ROAD | HDPE |  | 73 | [5 empty] | 8395
96 | 2023-06-19 | j201a | j201b | KC ROAD | HDPE | 26 | [6 empty] | 8421
97 | 2023-06-19 | j198 | j206 | KC ROAD | HDPE |  | 118 | [5 empty] | 8539
98 | 2023-06-19 | j249 | j252 | KC ROAD | HDPE | 30 | [6 empty] | 8569
99 | 2023-06-19 | j252 | j234 | KC ROAD | HDPE | 100 | [6 empty] | 8669
100 | 2023-06-19 | j204 | j210 | KC ROAD | HDPE |  |  | 43 |  |  |  |  | 8712
101 | 2023-06-19 | j210 | j216 | KC ROAD | HDPE |  |  | 41 |  |  |  |  | 8753
102 | 2023-06-20 | j196 | j213 | KC ROAD | HDPE |  |  | 264 |  |  |  |  | 9017
103 | 2023-06-20 | j196 | j198 | KC ROAD | HDPE |  |  | 48 |  |  |  |  | 9065
104 | 2023-06-20 | j211 | j211a | KC ROAD | HDPE | 45 | [6 empty] | 9110
105 | 2023-06-21 | j253 | j252 | KC ROAD | HDPE | 14 | [6 empty] | 9124
106 | 2023-06-21 | j254 | j256 | KC ROAD | HDPE | 78 | [6 empty] | 9202
107 | 2023-06-21 | j254 | j255 | KC ROAD | HDPE | 30 | [6 empty] | 9232
108 | 2023-06-21 | j252 | j254 | KC ROAD | HDPE | 11 | [6 empty] | 9243
109 | 2023-06-21 | j251 | j234 | KC ROAD | HDPE | 20 | [6 empty] | 9263
110 | 2023-06-21 | j210 | j211 | KC ROAD | HDPE | 24 | [6 empty] | 9287
111 | 2023-06-21 | j215 | j216 | KC ROAD | HDPE | 28 | [6 empty] | 9315
112 | 2023-06-21 | j226a | j226b | KC ROAD | HDPE | 11 | [6 empty] | 9326
113 | 2023-06-21 | j226b | j226c | KC ROAD | HDPE | 34 | [6 empty] | 9360
114 | 2023-06-22 | j213 | j217 | KC ROAD | HDPE | 83 | [6 empty] | 9443
115 | 2023-06-22 | j216 | j218 | KC ROAD | HDPE |  | 28 | [5 empty] | 9471
116 | 2023-06-22 | j218 | j200 | KC ROAD | HDPE |  | 5 | [5 empty] | 9476
117 | 2023-06-22 | j200 | j223 | KC ROAD | HDPE |  | 57 | [5 empty] | 9533
118 | 2023-06-22 | j223 | j225 | KC ROAD | HDPE |  | 10 | [5 empty] | 9543
119 | 2023-06-22 | j225 | j227 | KC ROAD | HDPE |  | 21 | [5 empty] | 9564
120 | 2023-06-22 | j223 | j224 | KC ROAD | HDPE | 19 | [6 empty] | 9583
121 | 2023-06-23 | j223(a) | j236 | KC ROAD | HDPE | 100 | [6 empty] | 9683
122 | 2023-06-25 | J76 | J81 | KC ROAD | HDPE | 43 | [6 empty] | 9726
123 | 2023-06-25 | J73 | J76 | KC ROAD | HDPE | 25 | [6 empty] | 9751
124 | 2023-06-25 | J69 | J73 | KC ROAD | HDPE | 48 | [6 empty] | 9799
125 | 2023-06-25 | J210 | J211 | B.T ROAD | HDPE | 3 | [6 empty] | 9802
126 | 2023-06-25 | J216 | J215 | B.T ROAD | HDPE | 3 | [6 empty] | 9805
127 | 2023-06-25 | J214 | J223 | B.T ROAD | HDPE | 3 | [6 empty] | 9808
128 | 2023-06-25 | J223 | J224 | B.T ROAD | HDPE | 3 | [6 empty] | 9811
129 | 2023-07-07 | j192 | j196 | KC ROAD | HDPE |  |  |  | 180 |  |  |  | 9991
130 | 2023-07-09 | j187 | j192 | KC ROAD | HDPE |  |  |  | 66 |  |  |  | 10057
131 | 2023-07-09 | j186 | j187 | KC ROAD | HDPE |  |  |  | 84 |  |  |  | 10141
132 | 2023-07-09 | j144 | j186 | KC ROAD | HDPE |  |  |  | 168 |  |  |  | 10309
133 | 2023-07-09 | j186 | j188 | KC ROAD | HDPE | 63 | [6 empty] | 10372
134 | 2023-07-09 | j140 | j144 | KC ROAD | HDPE |  |  |  | 54 |  |  |  | 10426
135 | 2023-07-09 | j137 | j140 | KC ROAD | HDPE |  |  |  | 71 |  |  |  | 10497
136 | 2023-07-10 | j144 | j144(a) | KC ROAD | HDPE | 104 | [6 empty] | 10601
137 | 2023-07-10 | j144a | j141 | KC ROAD | HDPE | 50 | [6 empty] | 10651
138 | 2023-07-11 | j127 | j137 | KC ROAD | HDPE |  |  |  | 78 |  |  |  | 10729
139 | 2023-07-11 | j96 | j127 | KC ROAD | HDPE |  |  |  | 300 |  |  |  | 11029
140 | 2023-07-12 | j96 | j127 | KC ROAD | HDPE |  |  |  | 30 |  |  |  | 11059
141 | 2023-07-13 | j96 | j127 | KC ROAD | HDPE |  |  |  | 22 |  |  |  | 11081
142 | 2023-07-13 | j92 | j96 | KC ROAD | HDPE |  |  |  | 25 |  |  |  | 11106
143 | 2023-07-13 | j89 | j92 | KC ROAD | HDPE |  |  |  | 14 |  |  |  | 11120
144 | 2023-07-14 | j144a | j144b | KC ROAD | HDPE | 13 | [6 empty] | 11133
145 | 2023-07-14 | j144a | j141 | KC ROAD | HDPE | 13 | [6 empty] | 11146
146 | 2023-07-14 | j141 | j141a | KC ROAD | HDPE | 71 | [6 empty] | 11217
147 | 2023-07-14 | j141 | j141b | KC ROAD | HDPE | 45 | [6 empty] | 11262
148 | 2023-07-18 | J14 | J158 | KC ROAD | HDPE |  | 283 | [5 empty] | 11545
149 | 2023-07-19 | J158 | J159 | KC ROAD | HDPE | 65 | [6 empty] | 11610
150 | 2023-07-19 | J158 | J164 | KC ROAD | HDPE | 80 | [6 empty] | 11690
151 | 2023-07-20 | J158 | J164 | KC ROAD | HDPE | 68 | [6 empty] | 11758
152 | 2023-07-20 | J164 | J170 | KC ROAD | HDPE | 138 | [6 empty] | 11896
153 | 2023-07-20 | J170 | J174 | KC ROAD | HDPE | 49 | [6 empty] | 11945
154 | 2023-07-20 | J170 | J165 | KC ROAD | HDPE | 15 | [6 empty] | 11960
155 | 2023-07-22 | j170 | j163 | KC ROAD | HDPE | 60 | [6 empty] | 12020
156 | 2023-07-22 | j165 | j176 | KC ROAD | HDPE | 23 | [6 empty] | 12043
157 | 2023-07-22 | j166 | j161 | KC ROAD | HDPE | 58 | [6 empty] | 12101
158 | 2023-07-22 | j166 | j169 | KC ROAD | HDPE | 18 | [6 empty] | 12119
159 | 2023-07-22 | j174 | j173 | KC ROAD | HDPE | 8 | [6 empty] | 12127
160 | 2023-07-22 | j173 | j175 | KC ROAD | HDPE | 23 | [6 empty] | 12150
161 | 2023-07-22 | j175 | j177 | KC ROAD | HDPE | 30 | [6 empty] | 12180
162 | 2023-07-23 | j169 | j167 | KC ROAD | HDPE | 9 | [6 empty] | 12189
163 | 2023-07-23 | j167 | j163 | KC ROAD | HDPE | 60 | [6 empty] | 12249
164 | 2023-07-23 | j161 | j157 | KC ROAD | HDPE | 27 | [6 empty] | 12276
165 | 2023-07-23 | j157 | j155 | KC ROAD | HDPE | 10 | [6 empty] | 12286
166 | 2023-07-23 | j157 | j154 | KC ROAD | HDPE | 74 | [6 empty] | 12360
167 | 2023-07-24 | J161 | J163 | KC ROAD | HDPE | 42 | [6 empty] | 12402
168 | 2023-07-24 | J163 | J162 | KC ROAD | HDPE | 12 | [6 empty] | 12414
169 | 2023-07-25 | J145 | J151 | KC ROAD | HDPE |  | 89 | [5 empty] | 12503
170 | 2023-07-25 | J151 | J154 | KC ROAD | HDPE |  | 125 | [5 empty] | 12628
171 | 2023-07-25 | J164 | J160 | KC ROAD | HDPE |  | 61 | [5 empty] | 12689
172 | 2023-07-25 | j154 | j160 | KC ROAD | HDPE |  | 24 | [5 empty] | 12713
173 | 2023-07-25 | j177 | j179 | KC ROAD | HDPE | 41 | [6 empty] | 12754
174 | 2023-07-25 | j171 | j172 | KC ROAD | HDPE | 11 | [6 empty] | 12765
175 | 2023-07-25 | j171 | j172 | KC ROAD | HDPE | 65 | [6 empty] | 12830
176 | 2023-07-25 | j172 | j177 | KC ROAD | HDPE | 35 | [6 empty] | 12865
[6 empty] | 9890 | 1348 | 535 | 1092 | 0 | 0 | 0 | 12865
[6 empty] | 14448 | 2831 | 1614 | 2095 | 751 | 1022 | 287 | 23048
| Block |  | Mangraura
| GP |  | BARASARAI
| Agency Name/ Work Order No |  | AGS CONSTRUCTION
63MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | indent |  |  |  | DIA | TOTALSCOPE | Issue (M) | Laid (M) | Balance Against Issue (M)
| 1 | 2023-04-27 | 1950 |  |  | 2239 |  |  |  | 63 | 14448 | 10500 | 9890 | 610
| 2 | 2023-05-20 | 2450 |  |  | 503 |  |  |  | 75 | 2831 | 2000 | 1348 | 652
| 3 | 2023-05-29 | 400 |  |  | 4341 |  |  |  | 90 | 1614 | 1000 | 535 | 465
| 4 | 2023-06-04 | 2700 |  |  | 20452 |  |  |  | 110 | 2095 | 1875 | 1092 | 783
| 5 | 2023-06-17 | 3000 |  |  | 4342 |  |  |  | 125 | 751 |  |  | 0
[10 empty] | 140 | 1022 |  |  | 0
[10 empty] | 160 | 287 |  |  | 0
|  | TOTAL | 10500
75MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-05-07 | 800 |  |  | 4339
| 2 | 2023-05-20 | 1200 |  |  | 503
3
3
|  | TOTAL | 2000
90MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 1 | 2023-04-27 | 400 |  |  | 2239
| 2 | 2023-06-17 | 600 |  |  | 4342
|  | TOTAL | 1000
110MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
| 2 | 2023-06-29 | 875 |  |  | 4341
| 3 | 2023-07-10 | 1000 |  |  | 20460
4
5
6
7
8
|  | TOTAL | 1875
140MM
| Sl.No | Date | Issue (M) | Laid (M) | Balance Against Issue (M) | Remarks
1
|  | TOTAL | 0