## Sheet1
JOINT MEASUREMENT REPORT
G.P.-NARI,BLOCK -SANDWA CHANDRIKA
AGENCY -TRIPATHI PLASTIC &TUBES
MEASUREMENT OF PIPELINES
DATE OF MEASUREMENT -02/02/2023
Sr.No. | PIPE NO. | Start Node | End Node | Dia of Pipe in(mm) | Length in (m) | Road Type | Width of Dismantling (m) | Reinstatement | Remarks/Details
1 | P-125 | J-99 | J-107 | 63 | 46 | PVB | 0.6
2 | P-130 | J-107 | J-117 | 63 | 36 | PVB | 0.6
3 | P-72 | J-117 | J-139 | 75 | 45 | PVB | 0.6
4 | P-67 | J-139 | J-78 | 75 | 33 | PVB | 0.6
5 | P-73 | J-78 | J-83 | 75 | 50 | KC
6 | P-45 | J-139 | J-83 | 125 | 32 | KC
7 | P-26 | J-83 | J-91 | 125 | 41 | KC
8 | P-36 | J-91 | J-96 | 125 | 49 | KC
9 | P-17 | J-96 | J-104 | 125 | 117.1 | KC
10 | P-22 | J-100 | J-104 | 125 | 32 | KC
11 | P-30 | J-105 | J-100 | 125 | 38 | KC
12 | P-32 | J-111 | J-105 | 125 | 37 | KC
13 | P-119 | J-128 | J-111 | 63 | 58 | KC
14 | P-63 | J-78 | J-128 | 63 | 17 | KC
15 | P-94 | J-126 | J-128 | 63 | 29.3 | KC
16 | P-161 | J-131 | J-126 | 63 | 7.7 | KC
17 | P-89 | J-141 | J-131 | 63 | 20 | KC
18 | P-85 | J-141 | J-78 | 63 | 41 | PVB | 0.6
19 | P-23 | J-111 | J-133 | 125 | 48 | KC
20 | P-18 | J-133 | J-142 | 110 | 27.5 | KC
21 | P-87 | J-131 | J-142 | 63 | 57 | KC
22 | P-90 | J-142 | J-136 | 63 | 14 | KC
23 | P-206 | J-136 | J-129 | 63 | 16.8 | KC | END CAP PENDING
24 | P-100 | J-138 | J-136 | 63 | 50 | KC
25 | P-106 | J-138 | J-134 | 63 | 17.7 | KC
26 | P-59 | J-144 | J-134 | 63 | 58 | KC
27 | P-77 | J-134 | J-110 | 63 | 110 | KC
28 | P-163 | J-121 | J-110 | 63 | 53.1 | KC
29 | P-68 | J-110 | J-127 | 63 | 4 | KC
30 | P-168 | J-127 | J-119 | 63 | 17.7 | PVB | END CAP PENDING
31 | P-64 | J-117 | J-127 | 75 | 30.3 | KC
32 | P-101 | J-107 | J-82 | 63 | 51 | KC
33 | P-56 | J-45 | J-82 | 63 | 16 | KC
34 | P-86 | J-82 | J-41 | 63 | 13 | KC
35 | P-158 | J-41 | J-55 | 63 | 78 | KC
36 | P-88 | J-82 | J-41 | 63 | 35 | KC
37 | P-193 | J-93 | J-92 | 63 | 37 | KC
38 | P-98 | J-91 | J-93 | 75 | 20.5 | KC
39 | P-44 | J-77 | J-45 | 75 | 21 | KC
40 | P-217 | J-77 | J-44 | 63 | 22.7 | KC
41 | P-43 | J-47 | J-77 | 75 | 22 | KC
42 | P-175 | J-47 | J-49 | 63 | 57 | KC
43 | P-211 | J-81 | J-47 | 63 | 22 | KC
44 | P-38 | J-54 | J-47 | 110 | 27 | KC
45 | P-13 | J-54 | J-96 | 125 | 90 | KC
46 | P-9 | J-51 | J-54 | 140 | 84 | KC
47 | P-131 | J-104 | J-88 | 63 | 115.3 | KC
[5 empty] | 33.8 | BOE | 0.4
[5 empty] | 51.4 | KC
48 | P-170 | J-89 | J-88 | 63 | 55 | KC
49 | P-154 | J-88 | J-94 | 63 | 47 | KC
50 | P-214 | J-98 | J-94 | 63 | 17 | KC | END CAP PENDING
51 | P-197 | J-94 | J-109 | 63 | 36 | KC
52 | P-195 | J-135 | J-89 | 63 | 41.9 | KC | END CAP PENDING
53 | P-136 | J-100 | J-89 | 75 | 130 | KC
54 | P-19 | J-142 | J-150 | 110 | 83 | KC
55 | P-182 | J-150 | J-146 | 90 | 53 | KC
56 | P-21 | J-150 | J-144 | 110 | 111 | KC
57 | P-14 | J-144 | J-172 | 110 | 187 | KC
58 | P-40 | J-178 | J-167 | 140 | 96.2 | KC
59 | P-29 | J-174 | J-173 | 140 | 50.3 | KC
[5 empty] | 10 | BOE | 0.6
60 | P-194 | J-174 | J-154 | 63 | 32 | KC
61 | P-199 | J-173 | J-159 | 63 | 30 | KC
62 | P-25 | J-173 | J-172 | 140 | 47.7 | KC
63 | P-20 | J-167 | J-140 | 140 | 151 | KC
64 | P-10 | J-140 | J-74 | 140 | 318.6 | KC
65 | P-15 | J-140 | J-86 | 125 | 395.2 | KC
66 | P-55 | J-21 | J-07 | 63 | 46.5 | KC
[5 empty] | 204 | BOE | 0.6 | Completed.
[5 empty] | 39 | KC
67 | P-48 | J-17 | J-21 | 125 | 207.8 | KC
68 | P-8 | J-17 | J-51 | 140 | 110 | KC
69 | P-11 | J-55 | J-17 | 140 | 71 | KC
70 | P-12 | J-74 | J-55 | 140 | 60 | KC
71 | P-205 | J-132 | J-130 | 63 | 29.8 | KC
72 | P-107 | J-130 | J-85 | 63 | 523 | KC
73 | P-165 | J-85 | J-64 | 63 | 103.3 | KC
74 | P-162 | J-85 | J-71 | 63 | 101.4 | KC
75 | P-6 | J-51 | J-106 | 160 | 263.7 | KC
76 | P-190 | J-106 | J-102 | 63 | 61 | KC
77 | P-5 | J-80 | J-106 | 160 | 572 | KC
78 | P-62 | J-80 | J-67 | 75 | 3.6 | BT | Pending Road crossing
[5 empty] | 167 | BOE | 0.5 | COMPLETED
[5 empty] | 64.2 | KC
79 | P-49 | J-67 | J-39 | 90 | 38 | KC
80 | P-176 | J-23 | J-39 | 63 | 57 | KC
81 | P-47 | J-39 | J-33 | 90 | 35.1 | KC
82 | P-54 | J-04 | J-33 | 90 | 38.4 | KC
83 | P-186 | J-04 | J-34 | 63 | 48 | KC
84 | P-53 | J-32 | J-04 | 90 | 66.7 | KC
85 | P-51 | J-31 | J-32 | 90 | 37 | KC
86 | P-112 | J-33 | J-30A | 63 | 58 | KC
87 | P-112A | J-30A | J-30B | 63 | 23.8 | KC
88 | P-112B | J-30A | J-30C | 63 | 59.1 | KC
89 | P-128 | J-67 | J-68 | 63 | 51 | KC
90 | P-141 | J-68 | J-62 | 63 | 122.8 | KC
91 | P-189 | J-40 | J-62 | 63 | 81.5 | KC
92 | P-65 | J-178 | J-172 | 140 | 33.8 | KC
93 | P-222 | J-21 | J-22 | 63 | 9 | KC
94 | P-135 | J-60 | J-37 | 63 | 370 | KC
95 | P-156 | J-60 | J-76 | 75 | 156 | KC
96 | P-95 | J-61 | J-60 | 90 | 72.5 | KC
97 | P-200 | J-48 | J-56 | 63 | 41 | KC
*** | P-92 | J-74 | J-99 | 63 | 78 | PVB
[5 empty] | 3.6 | BT
This line(P-92) hold due to incomplete depth.Depth has been founded 700mm above Pipe(OD).This line will be taken by the department after rectify.
POWER MECH PROJECT LIMITED -BRCPCL(JV). |  |  |  | MEDHAJ CONSULTANCY (THERD PARTY INS.) |  |  |  | UTTAR PRADESH JAL NIGAM(RURAL)-CLIENT.
DESIGNATION |  |  |  | DESIGNATION |  |  |  | DESIGNATION
NAME |  |  |  | NAME |  |  |  | NAME
SIGN.with date |  |  |  | SIGN.with date |  |  |  | SIGN.with date